## Summary
Summary of Project List 2015/16 Financial Year
Client Department | Budget Allocation (2015/16) R'000 | Comments
Education | 639674 | Revised plan received through email on 23 Mar 2015 from Nompumeleo. Signed off document NOT RECEIVED
Health | 398512 | Revised plan received through email on 16 Mar 2015 from Mfana. Signed off document NOT RECEIVED
Social Development | 72354 | Final plan received in December 2014.
Culture, Sport and Recreation | 118862 | Plan received by email in February 2015
Community, Safety,Security and Liaison | 114735 | Budget confirmed in 29 May 2014 for MTEF. However confimation for 2015/16 STILL OUTSTANDING
Total | 1344137

## DoE
[19 empty] | GRAND TOTAL | 8808807816.9775 |  | 560778188.4537 | 0 | 0 | 0
[20 empty] | Substitution of Unsafe Structures |  | 160667163 | 125761076 | 17197008.8501 | 35012782.1137
[20 empty] | New Schools |  | 87879192 | 174448736.202 | 54593545.0062 | 36736945
[20 empty] | Special Schools |  | 40078000 | 14841489 | 0 | 380373.9837
[20 empty] | Special Projects |  | 75882446.66 | 67999386.33 | 57583964.5 | 47756814.8283
[20 empty] | Boarding Schools |  | 13464000 | 16784800 | 0 | 350000
[20 empty] | Dinaledi Schools |  | 1832203 | 6126549.296 | 0 | 0
[20 empty] | Technical Schools |  | 25600000 | 32002188 | 0 | 186751.7073
[20 empty] | Storm Damaged Schools |  | 28067931.142 | 69414488.0766 | 2822693.1778 | 568656.47
[20 empty] | Grade R Schools |  | 2400092.604 | 27731283.8 | 0 | 0
[20 empty] | Upgrades & Additions |  | 11700000 | 7258770 | 0 | 72587.7
[20 empty] | Water & Sanitation |  | 1856729.0477 | 389930784.318 | 587774756 | 51298299
[20 empty] | Maintenance |  | 36415715 | 29228010 | 86420000 | 91951600
3999998
70934718
[20 empty] | BUDGET |  | 0 | 2015/16 | 2016/17 | 2017/18
[20 empty] | EIG |  |  | 824216000 | N/A | N/A
[20 empty] | ES |  |  | 177127000 | N/A | N/A
MPUMALANGA PROVINCIAL GOVERNMENT | [19 empty] | Dinaledi & TSSR |  |  | 26700000 | N/A | N/A
Department of Public Works, Roads and Transport | [19 empty] | TOTAL |  |  | 26700000 | N/A | N/A
Education Infrastructure Projects 2015/16 Financial Year | [18 empty] | Project Count / Sub-Total | 77 |  |  | 639673996.326 | 183358505.1463 | 198368192.2186
[10 empty] | Planning and Design |  |  | Construction
No. | Project Name | Infrastructure Type | Project Description | Economic Classification | District Municipality | Circuit | Local Municipality | Project Classification | Date: Start | Duration (Months) | Date: End | Date: Start | Duration (Months) | Date: End | Funding Source | Economic Classification | Planned Status for the 2015/16 Financial Year | Commitment Category | State of Readiness | Project Cost ( R ) |  | MTEF ESTIMATE 2014 / 2015 | Budget Allocation 2015 / 2016 ( R ) | MTEF 2016 / 2017 ( R ) | MTEF 2017 / 2018 ( R ) | Implementing Agent
1 | Temporary Accomodation (Mobile Classrooms) ex Abacus | All | Movable Classrooms | Capital Assets | All | All | All | Special Projects | 2014-09-01 |  |  | 2017-08-30 |  |  | Equitable Share (ES) | New & Replacement Schools |  | A | Active - Contracted | 66200000 | 8000000 | 4212000 | 20200000 | 22000000 | 24000000 | MDoE
2 | Eradication of Basic Services Backlog | All | Construction of Enviro-loo Toilets to 1041 Schools. | Capital Assets | All | All | All | Water & Sanitation | 2015-06-01 |  |  | 2017-03-31 |  |  | Education Infrastructure Grant (EIG) | Upgrades & Additions | Planning / construction | A | Proposed | 1025965988 |  |  | 386892933 | 587774756 | 51298299 | MVULA TRUST
1 | Ezakheni Boarding Phase 2 | BS | CRDP: Construction of Grade R Centres and Phase 2 Scope | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Boarding Schools | N/A | N/A | N/A | 2014-01-07 | 11 | 2014-12-17 | Equitable Share (ES) | Upgrades & Additions | Final account | A | Active - Contracted | 13464000 | 4000000 | 13464000 | 1009800 | 0 | 350000 | DPWRT
2 | Fish Mahlalela | P | CRDP - Planning and Design: Construction of a Grade R Centre, 16 Classrooms, Administration Block, Library, Computer Centre, School Hall, 24 Toilets ,Fence, Electricity, Water, Kitchen, Ramps and Rails, 3 sports grounds and car park. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 38000000 | 0 | 0 | 0 | 0 | 1900000 | 20000000
3 | Huttington | S | CRDP - Planning and Design: Construction of 15 classrooms, administration block, laboratory, library, computer centre, school hall. 22 toilets, fence, electricity, water, kitchen, ramps ans rails, 3 sports grounds, and car park. | Capital Assets | Bohlabela |  | Bushbuckridge | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 36000000 | 0 | 0 | 1800000 | 20200000 | 14000000
4 | Nduma | P | Planning and Design: Construction of a Grade R Centre, 10 Classrooms, Administration Block, Library, Computer Centre, School Hall, 14 Toilets ,Fence, Electricity, Water, Kitchen, Ramps and Rails, 2 sports grounds and car park. | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 27450501.4974 |  | 0 | 0 | 0 | 1935260.3556 | 25515241.1419
5 | Lehlogonolo | P | Planning and Design: Construction of a Grade R Centre, 12 Classrooms | Capital Assets | Bohlabela | Maviljan | Bushbuckridge | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 11092397.89 |  | 0 | 0 | 0 | 782014.0512 | 10310383.8388
6 | Moriting | P | Planning and Design: Construction of a Grade R Centre | Capital Assets | Bohlabela | Casteel | Bushbuckridge | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 2400092.604 |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754
7 | JB Khoza | P | CRDP - Construct 14 Classrooms, Administartion block, library, computer centre, school hall, 22 toilets, kitchen, ramps and rails, fence, electricity, water, 3 sports grounds and car park. | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-03-30 |  | 2017-03-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 34000000 | 0 | 0 | 1700000 | 32300000 | 0 | 276422.7642
2 | Ebuhleni (Phase 2) Primary School | P | Construct 16 Classrooms, Administration block, Library, Computer Centre, School Hall, 24Toilets, Fence, Electricity,Water, Kitchen, Ramps and Rails | Capital Assets | Ehlanzeni | Insikazi | Mbombela | New Schools | N/A | N/A | N/A | 2014-10-21 | 7 | 2015-06-19 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 39463000 | 12000000 | 0 | 32376000 | 7087000 | 0 | DPWRT
3 | Langeloop | S | Planning and Design: Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 46000000 | 0 | 0 | 0 | 2300000 | 24600000 | 19100000
4 | Mbombela | P | Planning and Design: Construct 24 Classrooms, Administration block, library, computer centre, School Hall, 36 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 42000000 | 0 | 0 | 0 | 0 | 2300000 | 24600000
3 | Middelburg Combined School | C | Demolish 42 classrooms and construct 42 classrooms. | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete | Substitution of unsafe structures | N/A | N/A | N/A | 2014-09-01 | 11 | 2015-08-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 42846000 | 4252413.82 | 28323000 | 28479492 | 8766508 | 348341.4634 | DPWRT
4 | MJ Lushaba | S | CRDP - Planning and Design: Construction of 20 classrooms, administration block, laboratory, library, computer center, school hall, 30 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 40000000 | 0 | 0 | 0 | 0 | 2000000 | 20400000
5 | Mmoyila | S | CRDP - Planning and Design: Construction of 28 classrooms, administration block, laboratory, library, computer centre, school hall. 42toilets, fence, electricity, water, kitchen, ramps / rails, 3sports grounds and car park. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 46000000 | 0 | 0 | 2300000 | 20000000 | 23700000
6 | Msholozi | P | CRDP - Planning and Design: Construction of Grade R centre, 20 Classrooms, Administration block, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | New Schools | 2017-04-01 |  | 2017-04-01 | 2018-06-30 |  | 2018-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 40000000 | 0 | 0 | 0 | 2820000 | 34380000 | 2800000
7 | Nyandeni | P | Planning and Design: Renovations to 22 classrooms, administration block and toilets. Construction of library, computer centre, fence, electricity, water, kitchen, ramps / rails, 3 sports grounds and car park. | Capital Assets | Gert Sibande | Stanwest | Lekwa | Upgrades and Additions | 2017-04-01 |  | 2017-04-01 | 2018-03-30 |  | 2018-03-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Active - Contracted | 25000000 | 0 | 0 | 0 | 1250000 | 24700000 | 0
4 | Osizweni Special School | SP | Construction of 8 classrooms, administration block, school hall, 4 workshops, media centre, fence, electricity and water supply. | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki | Special Schools | N/A | N/A | N/A | 2013-08-19 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 46786000 | 5000000 | 40078000 | 14841489 | 0 | 380373.9837 | DPWRT
5 | School for the Deaf | SP | All buildings to be sound proof. Construction of 30 classrooms with supporting facilities, ablution block with 15 toilets, administration block with a staff room for 40 educators, boardroom for 30 people, multi purpose hall with supporting facilities including fitness centre, laboratory, library, e-learning centre, 6 workshops, 3 therapy rooms with offices, counselling room, office for professional nurse with dispensary, 4 sickrooms and 3 toilets inclusive of a toilet for persons with disability, audiology room, art theater, covered walkways, fence, electricity, water, dining hall, car park, garages, hostel cluster with supporting facilities, 2 guest rooms and flats, 6 sports grounds and swimming pool with 2 cloak rooms. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Special Schools | TBA |  | #VALUE! | TBA |  | #VALUE! | Equitable Share (ES) | New & Replacement Schools |  | B | Active - Contracted | 250000000 | 3000000 | 0 | 129222610 | 65777390 | 55000000 | DPWRT
6 | Silulu | S | crdp - Planning and Design: Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 48000000 | 0 | 0 | 2400000 | 21125000 | 24475000 | 0 |  |  | 15200000 | [24 empty] | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667
5 | Tekwane North Secondary School | S | Construct 24 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | New Schools | N/A | N/A | N/A | 2015-01-16 | 12 | 2016-01-19 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 70000000 | 0 | 0 | 39759087 | 23597302 | 0 | DPWRT
6 | Tekwane South Secondary School | S | Construct 24 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | New Schools | N/A | N/A | N/A | 2013-04-05 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 48857000 | 13000000 | 26798192 | 12495808 | 0 | 488570 | DPWRT
7 | Ubuhle Buzile Secondary School | S | CRDP: Construction of 28 classrooms, administration block, laboratory, library, computer centre, School Hall, 40Toilets, Fence, Electricity, Watre, Kitchen, ramps / rails, 3 Sports Grounds & Car Park. | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | New Schools | N/A | N/A | N/A | 2012-10-23 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 45489000 | 26687000 | 13809000 | 5000000 | 369829.2683 | 0 | DPWRT
8 | Vezikgono | P | Planning and Design: Construct 24 Classroomss, Administration block, library, computer centre, School Hall, 36 Toilets, Fence, Elelctricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | Capital Assets | Nkangala | KwaMhlanga North East | Thembisile Hani | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 42000000 | 0 | 0 | 2961000 | 39039000 | 2520000 | 0
9 | White River | S | Planning and Design: Construct 28 Classroomss, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Elelctricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | Capital Assets | Ehlanzeni | White River | Mbombela | New Schools | 2015-04-01 |  | 2015-04-01 | 2016-06-30 |  | 2016-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 47933162 | 0 | 0 | 3379287.921 | 44553874.079 | 2875989.72 | 0
10 | Berbice (Phase 2) | P | Planning and Design: Grade R Centre, small administration block, computer centre, fence, electrical work, ramps and rails. | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Substitution of unsafe structures | 2016-04-01 |  | 2016-04-01 | 2017-03-30 |  | 2017-03-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 8400462 |  | 0 | 856000 | 7123154 | 421308 | 0 |  |  | 151791.1354 | 252985.2257 | 354179.3159 | 455373.4062 | 556567.4965 | 657761.5867 | 758955.677 | 860149.7673 | 961343.8575 | 1062537.9478 | 1163732.038 | 1264926.1283 | 1366120.2186 | 1467314.3088 | 1568508.3991 | 1669702.4894 | 1770896.5796 | 1872090.6699 | 1973284.7602 | 2074478.8504 | 2175465.3631 | 2136752.1368 | 1978474.2007 | 1820196.2646 | 1661918.3286 | 1503640.3925 | 1345362.4565 | 1187084.5204 | 1028806.5844 | 870528.6483 | 712250.7123 | 553972.7762 | 395694.8401 | 237416.9041 | 79138.968
8 | Netherlands Park [Wesselton] Secondary School | S | Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | New Schools | N/A | N/A | N/A | 2012-09-05 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 44065185 | 12311000 | 22915000 | 0 | 358253.5366 | 0 | DPWRT
9 | New Coronation [Klarinet] Secondary School | S | Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni | New Schools | TBC | TBC | TBC | 2012-09-07 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 46644000 | 22904000 | 24357000 | 0 | 379219.5122 | 0 | DPWRT
10 | Ramantsho | P | CRDP - Special Projects: MEDT. Substitution of buildings: 5classroom, administration block, library, computer centre and kitchen. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Special Projects | 2016-04-01 |  | 2016-04-01 | 2017-03-31 |  | 2017-03-31 | Equitable Share (ES) | Upgrades & Additions |  | B | Active - Contracted | 13139901.4547 | 1500000 | 0 | 926363.0526 | 11556543.3294 | 656995.0727 | 0
10 | Education Facilities Management System [EFMS] | All | Infrastructure Management | Capital Assets | All | All | All | Special Projects | 2011-09-01 |  | 2011-09-01 | 2015-03-31 |  | 2015-03-31 | Equitable Share (ES) | Goods & Services |  | A | Active - Contracted | 13791032 | 2408731 | 3766232 | 1277303 | 0 | 0 | MDoE
9 | Ndebele College | TT | Maintenance | Capital Assets | Nkangala | - | Dr JS Moroka | Maintenance | 2014-04-01 |  | 2014-04-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Maintenance & Repairs |  | B | Active - Contracted | 16000000 | 2000000 | 2000000 | 0 | 2420000 | 2662000 | 2928200
11 | Programme Management Unit | All | Infrastructure Management | Capital Assets | All | All | All | Special Projects | 2013-05-02 |  | 2013-05-02 | 2016-04-30 |  | 2016-04-30 | Equitable Share (ES) | Goods & Services |  | A | Active - Contracted | 28000000 | 7777778 | 10764443 | 9333333.33 | 672777 | 0 | MDoE
12 | DORA Compensation | All | Infrastructure Management | Current Paymens | All | All | All | Special Projects | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Goods & Services |  | A | Active - Contracted | 0 | 7777778 | 9487000 | 12600000 | 13608000 | 0 | MDoE
13 | Infrastructure Equipment | All | Infrastructure Functionality Management : Supply of furniture to completed facilities | Current Paymens | All | All | All | Special Projects | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Goods & Services |  | A | Active - Contracted | 0 | 7777778 | 17807000 | 8000000 | 21000000 | 23100000 | MDoE
14 | Highveld Comprehensive | Tec | CRDP: Construction of 1 new workshop and refurbishment of 1 workshops. | Capital Assets | Gert Sibande | Highveld Ridge East | Albert Luthuli | Technical Schools | 2014-09-01 |  | 2014-09-01 | 2015-08-31 |  | 2015-08-31 | MST - Technical Recapitalisation | Upgrades & Additions |  | A | Active - Contracted | 11270460 | 3000000 | 3500000 | 7902188 | 0 | 91629.7561 | MDoE
15 | Acorns To Oaks Comprehensive (addition to current scope) | S | CRDP: Construction of 18 Classrooms, Administration block, Laboratory, Media Centre, Computer Centre, School Hall, Electricity, Fence, Water, 5 Toilets Blocks | Capital Assets | Bohlabela [Ehlanzeni] | Greenvalley | Bushbuckridge | Special Projects | 2012-06-01 |  | 2012-06-01 | 2015-02-27 |  | 2015-02-27 | Equitable Share (ES) | New & Replacement Schools |  | A | Active - Contracted | 41631558.25 |  | 9845771.66 | 300000 | 0 | 338467.9533 | MDoE
10 | Mbhandule Secondary School | S | CRDP: Phase 1 - Construction of 8 classrooms, administration block, fencing, guard house, ablution block, water & electricity. Phase 2 - Construction of 20 classroom, laboratory, library, computer centre, school hall, kitchen, ablution blocks and sports grounds. | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2013-11-18 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 42890000 | 4885000 | 12800812 | 8300000 | 0 | 33912300 | DPWRT
11 | Sabeka Primary School | P | CRDP: Construction of 12 classrooms, administration block, library, computer centre, kitchen, 3 sports grounds and car park on a new site. | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2013-07-31 | 19 | 2015-02-25 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 26610948 | 3000000 | 23732000 | 0 | 216349.1707 | 0 | DPWRT
12 | Chueu Primary School | P | CRDP: Construction of 10 classrooms, administration block, 15 toilets, fence, library, Grade R Centre with 4 toilets and fence, 3 sports grounds and car park. | Capital Assets | Bohlabela | Arthurseat | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2013-11-18 | TBC | TBC | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 27817974 | 3316000 | 24732000 | 7900000 | 0 | 226162.3902 | DPWRT
13 | Seabe Secondary School | S | CRDP: Construction of 10 classrooms, administration block,laboratory, library, fence, electricity, water, 16 toilets, kitchen, 3 sports grounds and car park on a new site. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Substitution of unsafe structures | N/A | N/A | N/A | 2013-02-21 | 18 | 2014-08-18 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Final account | A | Active - Contracted | 27821822.568 | 12912000 | 11603000 | 0 | 226193.6794 | 0 | DPWRT
14 | Hazyview Combined School | C | Construction of 1 workshop and renovations and refurbishment to 3 other workshops. | Capital Assets | Ehlanzeni | White Hazy | Mbombela | Technical Schools | N/A | N/A | N/A | 2014-11-11 | 12 | 2015-11-11 | MST - Technical Recapitalisation | Upgrades & Additions | Construction | A | Active - Contracted | 11700000 | 1200000 | 8100000 | 3600000 | 0 | 95121.9512 | DPWRT
23 | FET and MRTT (Backlog Maintenance) | All | Maintenance | Capital Assets | All | All | All | Maintenance | 2013-04-01 |  | 2013-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Maintenance & Repairs | Planning / construction | A | Proposed | 335397875 | 84000000 | 27175715 | 28142010 | 84000000 | 89000000 | MRTT & GS COLLEGE
15 | Cana Combined Combined School | C | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2290318.8 | 2290318.8 | 0 | 2290318.8 | 0 | 0 | DPWRT
16 | Mugena Secondary School | S | CRDP: Construction of a laboratory. | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Dinaledi Schools | N/A | N/A | N/A | 2015-02-15 | 6 | 2015-08-14 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Active - Contracted | 1979439.83 | 1900000 | 1832203 | 1583551.864 | 0 | 0 | DPWRT
17 | Daggakraal Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2951758.7 | 2951758.7 | 0 | 2951758.7 | 0 | 0 | DPWRT
18 | Esibusisweni Combined School | C | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2422051.5 | 2422051.5 | 0 | 2422051.5 | 0 | 0 | DPWRT
19 | Kemp Siding Combined School | C | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 9 | 2016-02-05 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 5530311.6 | 1900000 | 0 | 5530311.6 | 0 | 0 | DPWRT
20 | Matikinya Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 3247889.7 | 1900000 | 0 | 3247889.7 | 0 | 0 | DPWRT
21 | Nwa Macingele Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2878734.1 | 1900000 | 0 | 2878734.1 | 0 | 0 | DPWRT
22 | Sinetjhudu Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2753297.8 | 1900000 | 0 | 2753297.8 | 0 | 0 | DPWRT
23 | Sizenzele Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2825830.7 | 1900000 | 0 | 2825830.7 | 0 | 0 | DPWRT
24 | Somlingo Primary School | P | CRDP: Construction of a Grade R Center with toilets and fence. | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Grade R Centres | N/A | N/A | N/A | 2015-05-04 | 6 | 2015-11-06 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 2831090.9 | 1900000 | 0 | 2831090.9 | 0 | 0 | DPWRT
25 | Hlomani Secondary School | S | 800005421 | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Dinaledi Schools | N/A | N/A | N/A | 2015-02-15 | 6 | 2015-08-14 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Active - Contracted | 1928746.79 | 0 | 0 | 1542997.432 | 0 | 0 | DPWRT
26 | Chief Fana Dlamini | S | Planning and Design: Construction of 24 Classrooms, administration block, laboratory, library, computer centre, 30 toilets, School Hall, Elelctricity, Water, 3 Sports Grounds & Car Park. | Capital Assets | Ehlanzeni | Nkululeko | Mbombela | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-03-30 |  | 2017-03-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Active - Contracted | 42000000 | 0 | 0 | 0 | 2961000 | 23439000 | 15600000
27 | Emjindini | S | Planning and Design: Construction of 7 classrooms, 10 toilets, school hall, kitchen, ramps and rails, 3 sports grounds and car park. | Capital Assets | Ehlanzeni | Barberton | Umjindi | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-03-30 |  | 2016-03-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Contracted | 9767160.9 | 0 | 0 | 688584.8434 | 9078576.0565 | 0 | 97671.609 |  |  | 6938334.3929 | 54765.2381 | 164295.7142 | 273826.1904 | 383356.6665 | 492887.1427 | 602417.6188 | 711948.095 | 821478.5711 | 931009.0473 | 1040539.5234 | 1150069.9995 | 1259600.4757 | 1369130.9518 | 1478661.428 | 1588191.9041 | 1697722.3803 | 1807252.8564 | 1916783.3326 | 2026313.8087 | 2135844.2849 | 2139088.0721 | 1970144.3338 | 1798827.4352 | 1627510.5366 | 1456193.638 | 1284876.7394 | 1113559.8408 | 942242.9422 | 770926.0437 | 599609.1451 | 428292.2465 | 256975.3479 | 85658.4493
28 | Eric Nxumalo | S | CRDP: Planning and Design: Refurbishment of workshops to comply with safety standards. | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Technical Schools | 2016-05-01 |  | 2016-05-01 | 2017-03-31 |  | 2017-03-31 | MST - Technical Recapitalisation | Rehabilitation, Renovation & Refurbishment |  | C | Active - Not Contracted | 10800000 | 0 | 0 | 0 | 10800000 | 0 | 0
23 | Hlelimfundo | S | CRDP: Planning and Design of 6 classrooms, laboratory, library, computer centre, upgrade electricity, ramps and rails, kitchen, school hall, 3 sports grounds and car park. | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | Upgrades and Additions | 2015-06-01 |  | 2015-06-01 | 2016-05-31 |  | 2016-05-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 12486148.4 | 0 | 0 | 11861841 | 624307.42 | 0 | 124861.484
24 | Ilanga [Bosfontein] | S | CRDP - Planning and Design: Construction of 12 classrooms, administration block, laboratory, library, computer centre, school hall, 18 toilets, fence, electricity, water, kitchen, ramps and rails, 3 sports ground and car park. | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | New Schools | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Not Contracted | 21177012.78 | 0 | 0 | 500000 | 16177013 | 4500000 | 0
25 | Lehlabile | S | CRDP: Planning and Design: Construction of administration block, computer centre, kitchen, laboratory, 12 toilets, School Hall, upgrade electricity, 3 Sports Grounds and Car Park and renovations of 16 classrooms. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Upgrades and Additions | 2013-08-01 |  | 2013-08-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Active - Not Contracted | 17361941.0002 | 0 | 0 | 0 | 1224016.8405 | 15096207.6997 | 1041716.46
26 | Louwra | P | Supply of electricity and renovation of a house in the school yard for conversion to an administration block or kitchen and storeroom and fence. | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | Upgrades and Additions | 2014-11-01 |  | 2014-11-01 | 2015-05-31 |  | 2015-05-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 1800000 | 0 | 0 | 1800000 | 0 | 0 | DPWRT
27 | Nalithuba | S | Planning and Design: Construction of school hall, library, computer centre, kitchen, laboratory, sports grounds and car park. | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Upgrades and Additions | 2015-06-01 |  | 2015-06-01 | 2016-05-31 |  | 2016-05-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 20000000 | 0 | 0 | 17175000 | 2825000 | 0
28 | Ndlamakhosi | S | CRDP: Planning and Design - Construction of 2 classrooms, laboratory, library, computer centre, 4 toilets, electricity, ramps and rails, 3 sports grounds and car park. Substitution of 10 pit toilets. | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Active - Not Contracted | 7130098.08 | 0 | 0 | 0 | 356505 | 6773593 | 0
29 | Seme | S | CRDP - Planning and Design: Construction of a computer centre, kitchen, ramps and rails, upgrade of electricity, school hall and laboratory. | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Upgrades and Additions | 2013-08-01 |  | 2013-08-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 20000000 | 0 | 0 | 1410000 | 17390000 | 1200000 | 0
30 | Shayaza | S | CRDP: Planning and Design: Addition of 10 classrooms, Library, Computer Centre, School Hall, 16 toilets, Fence, Kitchen, 3 Sports Grounds, Car Park and renovation of 18 Classrooms | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Upgrades and Additions | 2013-08-01 |  | 2013-08-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Active - Not Contracted | 26703946.1744 | 0 | 0 | 0 | 1882628.2053 | 23486120.6604 | 1335197.3087
26 | Shongwe Boarding School | BS | CRDP: Bulk services upgrade (Phase 1) Construction of a Grade R Center with toilets and fence, addition of hostels and upgrading of existing hostels and toilets. (Phase 2) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | Boarding Schools | N/A | N/A | N/A | 2015-05-11 | 12 | 2016-05-12 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Not Contracted | 71541100 | 5000000 | 0 | 15775000 | 0 | 55766100 | DPWRT
27 | Hlalakahle | S | CRDP - Planning and Design: Construction of administration block, computer centre, School Hall, kitchen, laboratory, 12 toilets, 3 Sports Grounds and Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | Upgrades and Additions | 2013-08-01 |  | 2013-08-01 | 2014-12-31 |  | 2014-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 20000000 | 0 | 0 | 935000 | 16823000 | 2242000 | 0
34 | Hoërskool Middelburg | S | Completion of the renovations of the school. | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete | Refurbishment and Renovations | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B | Active - Not Contracted | 15000000 | Term Contractor | 0 | 15000000 | 0 | 282460 | 0
35 | Mehlobomvu | S | CRDP - Planning and Design: Renovation of 16 Classrooms. Construction of additional 4 classrooms and administration block, laboratory, library, computer centre, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2014-06-01 |  | 2014-06-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 20000000 | 0 | 0 | 1800000 | 17200000 | 1000000
36 | Mkhanyo | P | CRDP - Planning and Design: Construction of a Grade R centre, 8 classrooms, library, computer centre, fence and kitchen. | Capital Assets | Nkangala | KwaMhlanga South West | Thembisile Hani | Upgrades and Additions | 2014-10-01 |  | 2014-10-01 | 2016-06-30 |  | 2016-06-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Not Contracted | 14674714.0236 | 0 | 0 | 1320724.2621 | 10978989.7614 | 2375000
27 | Moses Mnisi Secondary School | S | CRDP - Planning and Design: Substitution of unsafe 28 Crms, administration block, laboratory, library, computer centre, School Hall, kitchen, 3 Sports Grounds and Car Park. | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2014-03-25 | 14 | 2015-05-02 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 52597826 | 3612000 | 34161000 | 16994915 | 0 | 525978.26 | DPWRT
28 | Mpisana Primary School | P | CRDP: Demolish existing classrooms and construct 12 classrooms and 18 toilets, administration block, library, kitchen, school hall, computer centre, ramps and rails, 3 sports grounds and car park. | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2014-03-01 | 14 | 2015-05-25 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 36091802 | 3547000 | 25315351 | 18315481 | 0 | 0 | DPWRT
29 | Mugidi | P | CRDP - Planning and Design: Demolition of 10 classrooms and the construction of 10 classrooms, administration block, library, kitchen, computer centre, ramps and rails, 3 sports grounds and car park. | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | Substitution of unsafe structures | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 15025620.72 | 0 | 0 | 751281.036 | 14274339.684 | 0 | 150256.2072
37 | Thathakusa | P | Planning, design and construction: 2 Classrooms | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Upgrades and Additions | 2014-11-20 |  | 2014-11-20 | 2015-05-30 |  | 2015-05-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B | Active - Contracted | 1502788.785 | 0 | 0 | 1502788.785 | 0 | 0 | 0
38 | Sibonelo | P | CRDP - Planning and Design: Replace 10 classrooms and renovations of 5 classrooms. Construction of an administration block, library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Substitution of unsafe structures | 2016-04-01 |  | 2016-04-01 | 2017-06-30 |  | 2017-06-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Active - Contracted | 19986140.3238 | 0 | 0 | 1649400 | 17137571.9044 | 1199168.4194 | 0
29 | Tenteleni Primary School | P | Phase 1 - Construction of a Grade R Centre with toilets and fence, kitchen and library (by Education) Multi-purpose centre (COGTA) Phase 2 - Administration block and upgrade of sports facilities. | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Upgrades and Additions | N/A | N/A | N/A | 2015-05-11 | 9 | 2016-02-14 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | A | Active - Contracted | 7258770 | 0 | 6000000 | 7258770 | 0 | 72587.7 | DPWRT
30 | Thabana | P* | CRDP - Planning and Design: Renovation of 2 classrooms and the substitution of 3 classrooms and 10 toilets. Addition of a scaled down administration block, kitchen, computer centre, ramps and rails, 2 sports grounds, car park and library. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Substitution of unsafe structures | 2016-04-01 |  | 2016-04-01 | 2017-01-31 |  | 2017-01-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Proposed | 14904999.4409 | 0 | 0 | 1050802.4606 | 12959897.0138 | 894299.9665 | 0
30 | Welverdiend Primary School | P | Phase 1: Project concept planning and Design & Construction 15 Classroom, 22 Toilets, Palisade Fencing and Provision of Basic Services. | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Upgrades and Additions | 2015-05-27 | 9 | 2016-03-01 | 2015-09-01 | 6 | 2016-03-05 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | B | Proposed | 18905782.18 | 0 | 5000000 | 15722286 | 1555001 | 0 | DPWRT
32 | Ehlanzeni and other District Office | CIR | Refurbishment, maintenance and repairs to 4 district offices. | Capital Assets | Ehlanzeni | Ehlanzeni | Mbombela | Maintenance | 2015-04-01 |  | 2015-04-01 | 2015-11-30 |  | 2015-11-30 | Education Infrastructure Grant (EIG) | Maintenance & Repairs | Planning / construction | B | Active - Contracted | 7240000 | 0 | 7240000 | 1086000 | 0 | 289600 | DPWRT
31 | Aerorand Primary School | P | Phase 1: Project concept planning and construction of palisade fencing plus provision of basic services. Phase 2 : Planning and Design: Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, electricity upgrade, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete | New Schools | 2015-05-27 | 9 | 2016-03-01 | 2015-09-01 | 6 | 2016-03-05 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Planning / Construction | B | Active - Not Contracted | 44500000 |  | 0 | 4591500 | 3660125 | 36248375 | DPWRT
32 | Mtfophi (Daantjie) | P | Planning and Design: Construction of a Grade R centre, 24classrooms, administration block, library, computer centre, scholl hall. 36toilets, fence, electricity, water, kitchen, ramps & rails, 3 sports grounds & car park. | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | New Schools | 2015-05-01 |  | 2015-05-01 | 2017-03-31 |  | 2017-03-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B | Proposed | 42000000 |  | 0 | 35800000 | 6200000 | 0 | 420000
33 | Yinhlelentfo | P | Construction of a Grade R Centre, 16classroom, administration block, library, computer centre, School Hall, 24Toilets, Fence, Electricity, Watre, Kitchen, ramps / rails, 3 Sports Grounds & Car Park. | Capital Assets | Ehlanzeni | White Hazy | Mbombela | New Schools | 2015-04-01 |  | 2015-04-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C | Proposed | 30000000 |  | 0 | 0 | 1500000 | 28500000 | 0
34 | Balfour | P | CRDP - Planning and Design: Construction of 10 classrooms, administration block, library, kitchen, ramps and rails, 15 toilets and the renovations to 14 classrooms, computer centre, 14 toilets, sports grounds and car park. | Capital Assets | Gert Sibande | Balfour | Dipaleseng | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Proposed | 22000000 |  | 0 | 0 | 600000 | 21400000 | 0
35 | Bukhosibetfu | P | Planning and Design: Renovations of 19 classrooms and the construction of 5 classrooms, library, computer centre, kitchen, ramps and rails, 8 toilets, palisade fence and a skills centre for learners with disability. | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | Refurbishment and Renovations | 2016-04-01 |  | 2016-04-01 | 2017-03-31 |  | 2017-03-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B | Proposed | 18000000 |  | 0 | 900000 | 17100000 | 0 | 0
36 | Chief Makunyula | C | CRDP - Planning and Design: Construction 2 Grade R Centres with toilets and fence, 8 classrooms, administration block, library, laboratory, 24 toilets, computer centre, kitchen, ramps and rails, 15 toilets, 3 sports grounds, car park and the renovations to 16 classrooms. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Proposed | 23000000 |  | 0 | 0 | 1150000 | 21850000 | 0
37 | Dunbar | P | Planning and Design: Construction of 14 classrooms, administration block, library, computer centre, kitchen, 22 toilets, ramps and rails, 3 sports grounds and car park. Renovations to 9 existing classrooms and 12 toilets. | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-03-31 |  | 2017-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C | Active - Not Contracted | 26155402.0873 |  | 0 | 0 | 1843955.8472 | 22742122.1149 | 1569324.1252
38 | Hlangu-Phala | P | Construction of library, computer centre, upgrade electricity, ramps and rails, kitchen, school hall, 3 sports grounds and car park. Renovations to 25 classrooms and administration block. | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 19507392.132 |  | 0 | 0 | 1375271.1453 | 16961677.4588 | 1170443.5279
39 | Ikhwezi | P | Planning and Design: Construction 1 Grade R center, 12 Classrooms,administration block, library, computer centre, ramps and rails, kitchen, 12 toilets, 3 sports ground, car parking | Capital Assets | Gert Sibande | Bethal | Govan Mbeki | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 23737560.2036 |  | 0 | 0 | 1673497.9944 | 20639808.597 | 1424253.6122
32 | Jackie Manana Primary School | P | Planning and Design: Construction of Grade R Centre, 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande |  | Govan Mbeki | New Schools | TBC | TBC | TBC | 2015-06-01 | 15 | 2016-04-26 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | B | Active - Not Contracted | 48000000 |  | 0 | 33910000 | 13440000 | 0 | DPWRT
33 | Kamaqhekeza | P | CRDP - Planning and Design: Construction of 8 classrooms, library, computer centre, kitchen, school hall, upgrade electricity, ramps and rails, 20 toilets, 3 sports grounds and car park. Renovation to 16 classrooms and administration block | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18000000 |  | 0 | 0 | 1269000 | 15651000 | 1080000
34 | Khula | S | CRDP - Planning and Design: Construction of 7 classrooms, library, laboratory, school hall, computer centre, kitchen, ramps and rails, 20 toilets, 3 sports grounds, car park and the renovations to 21 classrooms and 10 toilets. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 30000000 |  | 0 | 0 | 0 | 2115000 | 27885000
35 | Khuphukani | P* | Planning and Design: Construction of a library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 16 existing classrooms and administration block. | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 8000000 |  | 0 | 0 | 400000 | 7600000 | 0
36 | Kwalodakada | P | CRDP - Planning and Design: Construction 2 Grade R Centres with toilets and fence, 4 classrooms, administration block, library, computer centre, kitchen, upgrade electricity, ramps and rails, 15 toilets, 3 sports grounds, car park and the renovations to 12 classrooms and 14 toilets. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18000000 |  | 0 | 0 | 900000 | 17100000 | 0
37 | Magogeni# | P | CRDP - Planning and Design: Renovations of 20 classrooms, administration block, Home Economics Centre and substitution of 4 unsafe structures. | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | Upgrades and Additions | 2014-06-01 |  | 2014-06-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 14026010.2626 |  | 0 | 0 | 6311704.6181 | 7714305.6444
38 | Makata | S | CRDP: Planning and Design - Construction of an administration block, laboratory, library, school hall, 16 toilets, kitchen, ramps and rails, upgrade of electricity, 3 sports grounds and car park. Renovations to 11 classrooms. | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 12000000 |  | 0 | 0 | 600000 | 11400000 | 0
39 | Maloka | P | CRDP - Planning and Design: Construction of a Grade R Centre, administration block, library, computer centre, kitchen, 10 toilets, electricity, water, fence, 2 sports grounds, car park, ramps and rails and the renovation of 6 classrooms. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Upgrades and Additions | 2016-06-01 |  | 2016-06-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18985658.1296 |  | 0 | 0 | 1338488.8981 | 16508029.7437 | 1139139.4878
40 | Malontone | P | CRDP - Planning and Design: Construction of a Grade R Centre, 10 Classrooms , administration block, library, computer centre, kitchen, 28 toilets, electricity, water, fence, 3 sports grounds, car park, ramps and rails. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Upgrades and Additions | 2014-06-01 |  | 2014-06-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 26853078.96 |  | 0 | 0 | 0 | 1893142.0667 | 24959936.8934
41 | Mapala | C | Planning and Design: Construction of 5 classrooms, administration block, laboratory, library, school hall, 20 toilets, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 14 classrooms. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-03-31 |  | 2017-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 27834587.5673 |  | 0 | 0 | 0 | 1962338.4235 | 25872249.1438
42 | Maqhekeza | P | Planning and Design: Construction 10 Classrooms, Administration Block, library, computer centre, Multi Media Center, Music room, School hall, ramps and rails, fence, kitchen, water, 13 toilets, 2 sports grounds & car parking | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 31040193.1076 |  | 0 | 0 | 0 | 2188333.6141 | 28851859.4935
43 | Masizakhe |  | Construction of Grade R Centre library , kitchen , 16 toilets . Renovation and refurbishment of 16 existing classrooms . | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-03-31 |  | 2017-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 10601841.7577 |  | 0 | 0 | 747429.8439 | 9324319.8259 | 530092.0879
44 | Mathule | P | CRDP: Planning and Design - Construction of 2 Grade R Centers with toilets and fence and 6 classrooms, administration block, library, computer centre, 10 toilets, kitchen, and car park. Substitute current pit toilets with 20 Enviroloo toilets. | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 18206609.4 |  | 0 | 1283565.9627 | 15830646.8733 | 1092396.564 | 0
45 | Mbangwane | C | CRDP - Planning and Design: Construction of 2 Grade R Centres with toilets and fence, | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2409849.078 |  | 0 | 0 | 169894.36 | 2239954.718 | 0
46 | Mdladla | P | CRDP - Planning and Design: Construction 2 Grade R Centres with toiltes and fence, 9 classrooms, library, computer centre, 36 toilets, kitchen, ramps and rails, 3 sports grounds, car park and the renovations to 15 classrooms. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 26000000 |  | 0 | 0 | 2181000 | 22259000 | 1560000
47 | Mjokwane | S | CRDP - Planning and Design: Construction of 3 classrooms, 30 toilets, kitchen, upgrade electricity and the renovations to 25 classrooms, laboratory, library, computer centre, upgrade electricity, ramps and rails, 20 toilets, 3 sports grounds and car park. Renovation to 21 classrooms, school hall and administration block | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18000000 |  | 0 | 0 | 1269000 | 15831000 | 900000
48 | Mlamlankunzi | P | CRDP - Planning and Design: Construction of a kitchen, and the renovations to 23 classrooms, library, computer centre, ramps and rails, 45 toilets, 3 sports grounds and car park. | Capital Assets | Gert Sibande | Balfour | Dipaleseng | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 30000000 |  | 0 | 0 | 2115000 | 26085000 | 1800000
49 | Mothaileng Mashego | P | CRDP: Planning and Design - Construction of 2 Grade R Centres, construction of 8 Classrooms, administration block, library, computer centre, kitchen, 12 Toilets, ramps and rails, 2 sports grounds and car park. | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 19852125.3 |  | 0 | 0 | 1399574.8336 | 17261422.9484 | 1191127.518
33 | Nwa Mahumana Primary School | P | CRDP - Planning and Design: Demolition of 14 Classrooms and Construction of 10 Classrooms, Administration Block, Library, kitchen, Ramps and Rails, 3 Sports Grounds and Car Park.. | Capital Assets | Bohlabela | Marite | Bushbuckridge | Upgrades and Additions | TBC | TBC | TBC | 2016-07-15 | 12 | 2017-04-05 | Education Infrastructure Grant (EIG) | Upgrades & Additions | Construction | B |  | 29011782 |  | 700000 | 16305308 | 4076327 | 8630147 | DPWRT
34 | Panorama | S | Planning and Design: Construction of 2 classrooms, ramps and rails, sports grounds and car park and renovations to an administration block, laboratory, library, computer centre, kitchen. | Capital Assets | Bohlabela | Sabie | Thaba Chueu | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 8000000 |  | 0 | 0 | 564000 | 7036000 | 400000
35 | Panyana | P | CRDP- Planning and Design: Construction of administration block, library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 11492257.5855 |  | 0 | 0 | 0 | 0 | 0 |  | 689535.4551
36 | Perdekop Agricultural | S | Planning and Design: Renovation of 6 classrooms, administration block, library and the construction of a laboratory, ramps and rails, 2 sports grounds and car park. | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | Refurbishment and Renovations | 2017-04-01 |  | 2017-04-01 | 2018-03-31 |  | 2018-03-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 15000000 |  | 0 | 0 | 750000 | 13350000 | 900000 |  |  | 0 | 39845.173 | 119535.5191 | 199225.8652 | 278916.2113 | 358606.5574 | 438296.9035 | 517987.2495 | 597677.5956 | 677367.9417 | 757058.2878 | 836748.6339 | 916438.98 | 996129.326 | 1075819.6721 | 1142269.1607 | 1059472.9345 | 934829.0598 | 810185.1852 | 685541.3105 | 560897.4359 | 436253.5613 | 311609.6866 | 186965.812 | 62321.9373
37 | Pilgrims Rest | P | CRDP - Planning and Design: Demolition of 8 classrooms, kitchen and the Construction of 5 classrooms, a kitchen, computer centre. Renovations to administration block. | Capital Assets | Bohlabela | Sabie | Thaba Chueu | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 7421900.5295 |  | 0 | 0 | 523243.9873 | 6898656.5421 | 0
38 | Sekusile | P | Planning and Design: Construction Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, water, 23 toilets, 2 sports grounds & car parking | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 20807182.5508 |  | 0 | 0 | 1466906.3698 | 18299917.0534 | 1040359.1275
39 | Seruane | S | CRDP - Planning and Design: Renovations of 14 classrooms and administration block and the construction of a laboratory, library, computer centre, school hall, kitchen and 3 sports grounds. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Refurbishment and Renovations | 2017-04-01 |  | 2017-04-01 | 2018-03-31 |  | 2018-03-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 17209361.8407 |  | 0 | 0 | 7744212.8283 | 9465149.0124
40 | Sibongile | P | CRDP: Planning and Design: Renovations of 8 classrooms and alterations to cater for the Circuit Office. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Refurbishment and Renovations | 2016-04-01 |  | 2016-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 3000000 |  | 0 | 211500 | 2788500 | 0 | 0
41 | Siyeta | P | CRDP: Construction of a Grade R Center with toilets and fence, library, computer centre, 24 toilets, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 16 classrooms and administration block. | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18000000 |  | 0 | 0 | 900000 | 17100000 | 0
34 | Zinikeleni Secondary School | S | CRDP: Construction of 2 workshops and refurbishment of 2 workshops to comply with safety standards. | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Technical Schools | N/A | N/A | N/A | 2014-11-11 | 12 | 2015-11-11 | MST - Technical Recapitalisation | Upgrades & Additions | Construction | A | Active - Contracted | 12400000 |  | 7000000 | 5400000 | 0 | 0 | DPWRT
35 | Daniye | P | CRDP - Planning and Design: Renovation of 5 classrooms and the substitution of 5 classrooms and 18 toilets. Addition of an administration block, kitchen, computer centre, ramps and rails, 3 sports grounds, car park and library. | Capital Assets | Bohlabela | Agincourt | Bushbuckridge | Substitution of unsafe structures | 2015-05-01 |  | 2015-05-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 20000000 |  | 0 | 0 | 1410000 | 17390000 | 1200000
35 | DD Mabuza Secondary School | S | CRDP: Construct of 4 new Workshops. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Technical Schools | N/A | N/A | N/A | 2014-11-11 | 12 | 2015-11-11 | MST - Technical Recapitalisation | Upgrades & Additions | Construction | A | Active - Contracted | 14000000 |  | 7000000 | 7000000 | 0 | 0 | DPWRT
36 | Ditholo Combined | Combined | CRDP - Planning and Design: Demolition of 14 classrooms and the construction of 14 classrooms, library, computer centre, kitchen, 22 toilets, school hall, 3 sports grounds and car park. Renovation to the existing administration block. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Substitution of unsafe structures | 2016-05-01 |  | 2016-05-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 27463497.2952 |  | 0 | 0 | 1936176.5593 | 23879510.8981 | 1647809.8377
37 | Dyondzekani | P | CRDP - Planning and Design: Demolition of 13 classrooms and the construction of 18 classrooms, administration block, library, computer centre, kitchen, 28 toilets, school hall, 3 sports grounds and car park. | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures | 2015-05-01 |  | 2015-05-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 28000000 |  | 0 | 0 | 1974000 | 24346000 | 1680000
38 | Godide | P | CRDP - Planning and Design: Demolition of 12 classrooms and the construction 10 classrooms, laboratory, library, computer centre, school hall, kitchen, ramps and rails, Renovate existing administration block. | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Upgrades and Additions | 2015-05-01 |  | 2015-05-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 36000000 |  | 0 | 800000 | 17700000 | 17500000 | 0
39 | Kufakwezwe | S* | Substitution of unsafe structures: 12 classrooms, administration, 1 toilets, fence, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Substitution of unsafe structures | 2014-09-01 |  | 2014-09-01 | 2015-09-30 |  | 2015-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 19047138.8637 |  | 0 | 1342823.2899 | 17704315.5738 | 1142828.3318 | 0
40 | Lungelo (Phase 2) | P | Planning and Design: Replace 5 classrooms and the renovations to 4 classrooms and the construction of a Grade R Centre, library, computer centre, ramps and rails, 2 sports grounds and car park. | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Substitution of unsafe structures | 2014-04-01 |  | 2014-04-01 | 2015-12-30 |  | 2015-12-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 18000000 |  | 0 | 200000 | 17800000 | 0 | 180000
41 | Madiba | S | Substitution of unsafe structures: 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 15 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 29670352.3994 |  | 0 | 0 | 0 | 0 | 0
42 | Mhlahle | P | Substitution of unsafe structures: 1 Grade R, 10 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 17 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 28413785.6398 |  | 0 | 0 | 0 | 0 | 0
43 | Apols chiloana | P | Substitution of unsafe structures: 1 Grade R, 9 classrooms, electricity | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 9708981.5685 |  | 0 | 684483.2006 | 8539049.2895 | 485449.0784 | 0
44 | Rhandzekile | P | Substitution of unsafe structures: 1 Grade R, 15 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 30402297.8108 |  | 0 | 0 | 0 | 2143361.9957 | 28258935.8151
45 | Hlangalezwe | P | Substitution of unsafe structures: 14 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 8 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 29362549.585 |  | 0 | 0 | 0 | 2070059.7457 | 27292489.8393
46 | MO Mashego | P | Substitution of unsafe structures: 15 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 14 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 30663360.7229 |  | 0 | 0 | 0 | 2161766.931 | 28501593.7919
47 | Casteel | P | Substitution of unsafe structures: 8 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 8 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 25016396.942 |  | 0 | 0 | 0 | 1763655.9844 | 23252740.9576
48 | Kennen | C | Substitution of unsafe structures: 1 Grade R, 19 classrooms, administration block, library, laboratory, computer centre, multi-media centre, multi-purpose centre, music room, home economics, workshop, school hall, 18 toilets, fence, electricty, water, kitchen, ramps and rails, 2 sports grounds and car parking | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 47477561.3549 |  | 0 | 0 | 0 | 3347168.0755 | 44130393.2793
49 | Lydenburg | P | Substitution of unsafe structures 4 classrooms | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2957437.2642 |  | 0 | 0 | 0 | 0 | 208499.3271
50 | Spekboom | P | Substitution of unsafe structures 3 classrooms | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2453832.9153 |  | 0 | 0 | 0 | 172995.2205 | 2280837.6948
51 | Matlolane | P | Substitution of unsafe structures: 6 classrooms, administration block, computer centre, 6 toilets, electricity, water, kitchen, car parking | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14110749.2132 |  | 0 | 0 | 0 | 0 | 994807.8195
52 | Relane | P | Substitution of unsafe structures: 8 classrooms, administration block, 8 toilets, fence, kitchen | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14575647.9803 |  | 0 | 0 | 0 | 0 | 0 |  | 874538.8788
53 | Serisha | S | Substitution of unsafe structures: 20 classrooms, administration block, 8 toilets, water, kitchen | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 21951853.2663 |  | 0 | 0 | 0 | 0 | 0
54 | Sibambayana | P | Substitution of unsafe structures: 1 Grade R, 8 classrooms, administration, 1 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 16773061.3723 |  | 0 | 0 | 0 | 0 | 0
55 | Makgahlishe | P | Substitution of unsafe structures: 1 Grade R, 17 classrooms, 4 toilets, fence, electricity | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 18823057.2753 |  | 0 | 0 | 0 | 0 | 1327025.5379
56 | Sebosegolo | P | Substitution of unsafe structures: 1 Grade R, 3 classrooms, school hall, 1 toilets, fence, electricity | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14038555.3625 |  | 0 | 0 | 0 | 0 | 0
57 | Mahlale | S | Substitution of unsafe structures 12 classrooms, administration block, computer centre, 8 toilets | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 16584454.5492 |  | 0 | 0 | 0 | 0 | 0
58 | Munyamane | P | Substitution of unsafe structures 4 classrooms | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14038555.3625 |  | 0 | 0 | 0 | 0 | 989718.1531
59 | Matikinya | P | Substitution of unsafe structures 12 classrooms, 4 toilets | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 10370727.1773 |  | 0 | 0 | 0 | 731136.266 | 9639590.9113
60 | Londhindha | P | Substitution of unsafe structures 10 classrooms | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7930908.0948 |  | 0 | 0 | 0 | 0 | 0
61 | Thwasani | P | Substitution of unsafe structures 10 classrooms | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7930908.0948 |  | 0 | 0 | 0 | 0 | 559129.0207
62 | Matikwana | P | Substitution of unsafe structures 10 classrooms | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7930908.0948
63 | Shakwaneng | P | Substitution of unsafe structures 8 classrooms | Capital Assets | Bohlabela | Sabie | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 6046484.5284 |  | 0 | 0 | 0 | 0 | 0
64 | Matibidi | P | Substitution of unsafe structures 6 classrooms | Capital Assets | Bohlabela | Sabie | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 4907665.8306
65 | Pilgrims City | S | Substitution of unsafe structures 1 classrooms | Capital Assets | Bohlabela | Sabie | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 790163.7738 |  | 0 | 0 | 0 | 0 | 55706.5461
66 | Malavutela | S | Substitution of unsafe structures: 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, workshop, school hall, fence, kitchen, ramps and rails, 1 sports grounds and car parking | Capital Assets | Bohlabela | Marite | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 30109919.1766 |  | 0 | 0 | 0 | 2122749.302 | 27987169.8746
67 | Marcia Mokoena | S | Substitution of unsafe structures: 14 classrooms, library, computer centre, multi-purpose centre, music room, home economics, workshop, school hall, fence, electricty, water, kitchen, ramps and rails, 1 sports grounds and car parking | Capital Assets | Bohlabela | Maviljan | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 32808931.7243 |  | 0 | 0 | 0 | 2313029.6866 | 30495902.0377
68 | Mabonwana | P | Substitution of unsafe structures Grade R centre, 2 classrooms, administration block, school hall, 16 toilets, fence | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 17886809.9528 |  | 0 | 0 | 0 | 0 | 0
69 | Khokhovela | P | Substitution of unsafe structures Grade R centre, 21 classrooms, school hall, 16 toilets, fence | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 26912074.0617 |  | 0 | 0 | 0 | 0 | 1897301.2214
70 | Floraphophe | P | Substitution of unsafe structures: of a Grade R centre, 8 classrooms, administration block, library, computer centre, music room, multi-media centre, multi-purpose centre, 22 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. | Capital Assets | Bohlabela | Rolle | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 29766099.1862 |  | 0 | 0 | 0 | 2098509.9926 | 27667589.1936
71 | Songeni | P | Substitution of unsafe structures: of a Grade R centre, 8 classrooms, administration block, library, laboratory, computer centre, music room, multi-media centre, home ecomonic, workshop, multi-purpose centre, school hall, 12 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 39069176.1493 |  | 0 | 0 | 0 | 2754376.9185 | 36314799.2307 |  | 2344150.569
72 | Jan Rikhotso | P | Substitution of unsafe structures: of a Grade R centre, 9 classrooms, administration block, library, computer centre, music room, multi-media centre, home ecomonic, workshop, multi-purpose centre, school hall, 24 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. | Capital Assets | Bohlabela | Kildare | Bushbuckridge | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 40946439.6512 |  | 0 | 0 | 0 | 0 | 0
73 | Manyakatana | P | CRDP: Planning and Design - Substitution of unsafe structures and the construction of a Grade R Centre with toilets and fence, 15 classrooms, administration block, library, computer centre, school hall, 22 toilets, kitchen, ramps and rails, upgrade electricity, 3 sports grounds and car park. | Capital Assets | Bohlabela | Agincourt | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 33121116.3683 |  | 0 | 2335038.704 | 28798810.6822 | 1987266.9821 | 0
74 | Masana | S | CRDP - Planning and Design: Construction of 15 classrooms, laboratory, library, computer centre, school hall, 22 toilets, kitchen, ablution blocks, 3 sports grounds and car park. Renovations to 10 classrooms and an administration block. | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Upgrades and Additions | 2013-04-01 |  | 2013-04-01 | 2013-09-04 |  | 2013-09-04 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 30048182.1164 |  | 0 | 950000 | 27295291.1894 | 1802890.927 | 0
75 | Jongilanga | P | Renovations of 1 Grade R Centre, 15 Classroom , administration block, laboratory, library, computer centre, mutli media centre, music room, home economic, mutli purpose centre, school hall, 26 toilets, fence, kitchen, ramps & rails, 2 sports grounds and 10 car park. | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 11570960.1283 |  | 0 | 0 | 5206932.0577 | 6364028.0706 | 115709.6013
76 | Magudu | p | Renovations of 1 Grade R Centre, 13 Classroom, laboratory, library, computer centre, mutli media centre, music room, home economic, mutli purpose centre, school hall, 20 toilets, kitchen, ramps & rails, 2 sports grounds and 8 car park. | Capital Assets | Bohlabela | ximhungwe | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 9154979.8661 |  | 0 | 0 | 0 | 0 | 0
77 | Moholoholo | S | Renovations of 4 Classroom , administration block, laboratory, library, fence, kitchen | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4108200 |  |  |  |  | 289628.1 | 3818571.9
78 | NP. Mathabela | P | Renovations of 4 Classroom , administration block, laboratory, library, fence, kitchen | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4108200 |  | 0 | 0 | 0 | 4108200 | 0
79 | Senianya | P | Renovations of 9 Classroom, kitchen | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2472300 |  | 0 | 0 | 0 | 0 | 0
80 | Mashishing | S | Renovations of 26 Classroom, administration block, 1 toilet, fence | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6851100 |  | 0 | 0 | 0 | 0 | 483002.55
81 | Spekboom | P | Renovations of 4 Classroom, 1 toilet | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 1254600 |  | 0 | 0 | 1254600 | 0 | 0
82 | Hambanathi | P | Renovations of 5 Classroom, administration block | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6851100 |  | 0 | 0 | 3082995 | 3768105 | 68511
83 | Kellysville | P | Renovations of 15 Classroom, administration block, library | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4391100 |  | 0 | 0 | 0 | 309572.55 | 4081527.45
84 | Marifaan | P | Renovations of 18 Classroom, administration block | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4760100 |  | 0 | 0 | 2142045 | 2618055 | 47601
85 | Matlalong | P | Renovations of 10 Classroom, administration block, electricity, kitchen | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 3419400 |  | 0 | 0 | 0 | 0 | 241067.7
86 | Boikhutso | P | Renovations of 21 Classroom, administration block, computer centre, 11 toilets, fence, car parking | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 7773600 |  | 0 | 0 | 3498120 | 4275480 | 77736
87 | Narishe | P | Renovations of 21 Classroom, administration block, computer centre, 10 toilets | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 5916300 |  | 0 | 0 | 2662335 | 3253965 | 59163
45 | Lehlasedi | S | Renovations of 24 Classroom, 16 toilets, fence, electricity, water, kitchen (ex Storm Damage School) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Refurbishment and Renovations | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 8819100 |  | 0 | 8819100 | 0 | 0 | 0
46 | Mgangedwa | P | Renovations of 4 Classroom, adminstration block, 1 toilets, kitchen, ramp & rails, 2 sport field, car parking | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2521500 |  | 0 | 0 | 0 | 0 | 0
47 | Mkhweyantaba | P | Renovations of 4 Classroom, adminstration block, 1 toilets, kitchen, ramp & rails, 2 sport field, car parking | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2521500 |  | 0 | 0 | 0 | 0 | 0
48 | Beretta | P | Renovations of 3 Grade R, 23 Classrooms | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 6309900 |  | 0 | 0 | 2839455 | 3470445 | 63099
49 | Chayiwe | P | Renovations of 2 Grade R, 16 Classrooms | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4206600 |  | 0 | 0 | 0 | 296565.3 | 3910034.7
50 | Funjwa | P | Renovations of 4 Grade R, 5 Classrooms | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2103300 |  | 0 | 0 | 0 | 148282.65 | 1955017.35
51 | Dayimani | S | Renovations of 12 Classrooms, 12 toilets | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2952000 |  | 0 | 0 | 0 | 0 | 208116
52 | Nyamazane | S | Renovations of 12 Classrooms | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2804400 |  | 0 | 0 | 0 | 0 | 0
53 | Shiviti | P | Renovations of 8 Classrooms, administration block, 12 toilets, fence | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4231200 |  | 0 | 0 | 0 | 0 | 298299.6
54 | Hobo | H | Renovations of 4 Classroom, laboratory, computer centre, kitchen | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 1771200 |  | 0 | 0 | 1771200 | 0 | 0
55 | Hoyohoyo | H | Renovations of laboratory, school hall, 1 toilet | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 1008600 |  | 0 | 0 | 0 | 0 | 1008600
56 | James Khosa | H | Renovations of 16 classrooms, administration block, 8 toilets | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4391100 |  | 0 | 0 | 0 | 0 | 309572.55
57 | LM Kganane | S | Renovations of 4 Classroom, adminstration block, laboratory, mutli- purpose centre, 14 toilets, fence, water, kitchen, ramp & rails, 2 sport field, car parking | Capital Assets | Bohlabela | Sabie | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 5485800 |  | 0 | 0 | 0 | 0 | 0
58 | Makorompne | p | Renovations of 10 Classroom , administration block, laboratory, library, computer centre, mutli media centre | Capital Assets | Bohlabela | Marite | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4440300 |  | 0 | 0 | 0 | 0 | 0
59 | Nembe | P | Renovations of Grade R, 4 Classroom, adminstration block, laboratory, library, mutli- purpose centre, music room, school hall, home economic, kitchen, ramp & rails, 2 sport field, car parking | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 5129100 |  | 0 | 0 | 0 | 0 | 361601.55
60 | Lebadishang | P | Renovations of Grade R, 26 Classroom, adminstration block, laboratory, library, mutli- purpose centre, music room, 1 workshop, school hall, home economic, 12 toilets, fence, water, electricity, kitchen, ramp & rails, 2 sport field, car parking | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Refurbishment and Renovations | 2016-10-01 |  | 2016-10-01 | 2017-09-30 |  | 2017-09-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 14809200 |  | 0 | 0 | 6664140 | 8145060 | 148092
36 | Mathibela Secondary School | S* | CRDP - Planning and Design: Construction of 2 classrooms, administration block, laboratory, library, computer centre, school hall, kitchen, 28 toilets, upgrade the electricity, ramps and rails 3 sports grounds and car park. Renovations to 16 classrooms. | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | Substitution of unsafe structures | N/A | N/A | N/A | 2015-01-13 | 12 | 2016-01-13 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | A | Active - Contracted | 59759146 |  | 0 | 45771188 | 7987958 |  | DPWRT
37 | Matlushe | P | CRDP: Construction of 2 Grade R Centres, administration block, library, computer centre, 20 toilets, upgrade of electricity, ramps and rails, 3 sports grounds and car park. Renovations to 13 existing classrooms. | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-12-14 |  | 2016-12-14 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 6000000 |  | 0 | 0 | 0 | 300000
38 | Mmagobana | C* | Planing and Design: Substitution of 7 unsafe structures and construction of Grade R Centre Centre, 4t and F, administration block, library, computer centre, kitchen, 28 toilets, 3 Sports Grounds and Car Park. Renovations of 7 classrooms. | Capital Assets | Nkangala | Emalahleni 1 | Emalahleni | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-12-30 |  | 2016-12-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 20231138.24 |  | 0 | 1011556.91 | 18005713.0356 | 1213868.2944 | 0
39 | Mphephethe | P | Planning and Design: Substitution of unsafe 14 Crms and construct a cc, kitchen, Grade R Centre, 4T and F. | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete | Substitution of unsafe structures | 2014-09-01 |  | 2014-09-01 | 2015-09-30 |  | 2015-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 17000000 |  | 0 | 0 | 1198500 | 14951500 | 850000
46 | Mpisi | P | Substitution of unsafe structures: of a Grade R centre, 19 classrooms, administration block, library, laboratory, computer centre, music room, multi-media centre, multi-purpose centre, 24 toilets, kitchen, ramps and rails, water, 2 sports grounds and car park. | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Refurbishment and Renovations | 2017-04-01 |  | 2017-04-01 | 2018-03-31 |  | 2018-03-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 35359801.4864 |  | 0 | 12375930.5202 | 22983870.9662 | 0 | 353598.0149
47 | Njonjela | P* | Substitution of unsafe structures: 1 Grade R, 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 18 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Substitution of unsafe structures | 2014-04-01 |  | 2014-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 29958578.5814 |  | 0 | 1217258.03 | 15000000 | 8127902.56 | 0
48 | Pungutsha | S | CRDP: Planning and Design - Construction of a computer centre and renovations to 16 classrooms, administration block laboratory, library, ramps and rails and upgrading of 3 sports grounds. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Upgrades and Additions | 2016-04-01 |  | 2016-04-01 | 2017-12-31 |  | 2017-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 7841573.3793 |  | 0 | 0 | 552830.9232 | 7288742.4561 | 0
49 | Thulamahashe | P* | CRDP - Planning and Design: Demolition of 12 classrooms and the construction 12 classrooms, administration block, library, computer centre, school hall, kitchen, ramps and rails, 3 sports grounds and car park. | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 20552705.46 |  | 0 | 0 | 0 | 1448965.7349 | 19103739.7251
50 | Uthaka | S* | CRDP - Planning and Design: Construction of 13 classrooms, computer centre, kitchen, 20 toilets, school hall, 3 sports grounds and car park. Fitting of shelves and counter in the library and necessary shelves and gas tubes in the laboratory. | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Upgrades and Additions | 2014-04-01 |  | 2014-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 25000000 |  | 0 | 0 | 1762500 | 21987500 | 1250000
51 | Vukubone | P | CRDP - Planning and Design: Demolition of 15 classrooms and the construction of 15 classrooms, administration block, library, computer centre, kitchen, 36 toilets, school hall, 3 sports grounds and car park. | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Substitution of unsafe structures | 2015-05-01 |  | 2015-05-01 | 2016-12-31 |  | 2016-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 26554248 |  | 0 | 0 | 0 | 1872074.484 | 24682173.516
47 | Badlangaye | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Maviljan | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
48 | Bantomu | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
49 | Bhekimfundo | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni |  | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
50 | Buyisonto | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Dwarsloop | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1305240 |  | 0 | 1305240 | 0 | 0 | 0
51 | Ezrom | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Thulamahashe | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1184550 |  | 0 | 1184550 | 0 | 0 | 0
52 | Halemela | S | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
53 | Hlulani | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 2842920 |  | 0 | 2842920 | 0 | 0 | 0
54 | Homuzeya | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 295020 |  | 0 | 295020 | 0 | 0 | 0
55 | Letsamaile | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 84930 |  | 0 | 84930 | 0 | 0 | 0
56 | Londhindha | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1636020 |  | 0 | 1636020 | 0 | 0 | 0
57 | Madille | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 4188390 |  | 0 | 4188390 | 0 | 0 | 0
58 | Madukulushe | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) and completion of 8 Enviro-Loo toilets | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 3339090 |  | 0 | 4042081 | 0 | 0 | 0
59 | Magolane |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni |  | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 411240 |  | 0 | 411240 | 0 | 0 | 0
60 | Makhosana Manzini | S | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 438060 |  | 0 | 438060 | 0 | 0 | 0
61 | Makorompane | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
62 | Malengeza | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1725420 |  | 0 | 1725420 | 0 | 0 | 0
63 | Mapaleni | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
64 | Matlalong | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Shatale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 3289920 |  | 0 | 3289920 | 0 | 0 | 0
65 | Matlolane |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni |  | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 2842920 |  | 0 | 2842920 | 0 | 0 | 0
66 | Mbatini | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
67 | Mkhumbini | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
68 | Morage | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 273027.6 |  | 0 | 273027.6 | 0 | 0 | 0
69 | Morithing | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Casteel | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 1090680 |  | 0 | 1090680 | 0 | 0 | 0
70 | Relane | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Shatale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 2552370 |  | 0 | 2552370 | 0 | 0 | 0
71 | Sebosekgolo sa mapulane | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 3303330 |  | 0 | 3303330 | 0 | 0 | 0
72 | Sihlekisi | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | B |  | 4188390 |  | 0 | 4188390 | 0 | 0 | 0
73 | Tfolinhlanhla | P | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | Capital Assets | Ehlanzeni | White Hazy | Mbombela | Substitution of unsafe structures | 2015-06-01 |  | 2015-06-01 | 2015-10-31 |  | 2015-10-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | o |  | 2407509 |  | 0 | 2407509 | 0 | 0 | 0
74 | Dlomodlomo | S | Planning and Design: Construction 9 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, water, 6 toilets, fence, 3 sports ground, car parking | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 23309358.1692 |  | 0 | 0 | 0 | 1643309.7509 | 21666048.4183
75 | Letabogiye | P | 4 Classrroms, Adminstration, Lab, Lib, Computer Room, Multi-Media Room, Music Room, Home Economic, Technical/Workshop, Multi Purpose Center, School Hall, 12 Toilets, Fence, Electricity, Water, Kitchen, Ramp&Rails, Sport Field LRG, Sport Field SML | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | New Schools | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 25479700 |  | 0 | 0 | 0 | 0 | 1796318.85
76 | Ekuphakameni Primary | P | CRDP. Construction of a Grade R Centre, 16 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 29843647.663 |  | 0 | 1044527.6682 | 23427263.4154 | 5371856.5793 | 298436.4766
37 | Duvha Primary School | P | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park in partnership with Eskom | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni | Substitution of unsafe structures | 2015-03-12 | 2 | 2015-05-13 | 2015-08-01 | 12 | 2016-04-21 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Construction | B |  | 43025355.8489 |  | 0 | 16066575 | 0 | 26958781 | DPWRT
38 | Laerskool Onverwacht | P | Demolition of 14 asbestos structures and construction of 14 classrooms. Refurbishment of other existing structures. | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 32112953.4144 |  | 0 | 0 | 0 | 2263963.2157 | 29848990.1987
39 | Mokebe Secondary | S | CRDP. Demolition of existing structures and Construction of 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 30697138.3667 |  | 0 | 0 | 0 | 2164148.2549 | 28532990.1119
40 | Witbank High | S | Demolition of 6 asbestos classrooms and construction of 6 classrooms. Refurbishment and renovation of existing 26 classrooms , 1 administration block, 5 special centres , 1 library , 1 school hall and 45 toilets. | Capital Assets | Nkangala |  | eMalahleni | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14420898.143 |  | 0 | 0 | 0 | 0 | 1016673.3191
41 | J Mdaka | P | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 16477348.9149 |  | 0 | 0 | 0 | 0 | 1161653.0985
42 | Borolo Primary School | P | CRDP. Demolition of 5 classrooms and construction of 5 classrooms , Grade R Centre , Administration block , Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 19293517.3212 |  | 0 | 0 | 0 | 0 | 1360192.9711
43 | Fakazi | P | 16 Classrooms, Administration block | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 14788800 |  | 0 | 0 | 0 | 0 | 1042610.4
44 | Numbi | P | 4 Classrooms | Capital Assets | Ehlanzeni | White Hazy | Mbombela | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2015-03-31 |  | 2015-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2947200 |  | 0 | 0 | 0 | 0 | 207777.6
45 | Thanda | C | Construction of 16 Classrooms, Administration block, Laboratory, Library, Computer Centre,Multi-Media Centre, Music Room, Home Economic, Technical/Workshops, Multi-Purpose Center, School Hall, Kitchen, Elelctricity,Water, 24 Toilets,Ramps & Rails, Fence, 1 Sport Field SML, 1 Sport Field LRG, Parking, Guard House | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | New Schools | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 34808800 |  | 0 | 0 | 2454020.4 | 30614339.6 | 1740440
46 | Shishila | P | Administration Block | Capital Assets | Ehlanzeni | Sikhulile | Mbombela | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 4815091.3566 |  | 0 | 0 | 0 | 0 | 0
47 | Buyani | C | 12 Classrooms, Administration block, 20 Toilets | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 11255100 |  | 0 | 0 | 0 | 0 | 793484.55
48 | Bashele Primary School | p | 12 Classrooms, 10 Toilets,Fence, 21 REN, Guard house | Capital Assets | Gert Sibande | Ermelo | Msukaligwa | Refurbishment and Renovations | 2019-04-01 |  | 2019-04-01 | 2020-03-30 |  | 2020-03-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 17341600 |  | 0 | 0 | 0 | 1222582.8 | 16119017.2
74 | Carolina Combined | C | 1 Grade R | Capital Assets | Gert Sibande | Caroline | Albert Luthuli | Grade R Centres | 2015-04-01 |  | 2015-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 2235200 |  | 0 | 2235200 | 0 | 0 | 0
75 | Esithembisweni | P | 1 Grade R | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Grade R Centres | 2015-04-01 |  | 2015-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0
76 | Sakhisizwe Primary | P | 8 Classrooms, Admin Block, MP, Computer Centre, Kitchen, Ramps & Rails, 3 Sport Fields, Parking, 1 Grade R | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 23444876.7147 |  | 0 | 0 | 0 | 1652863.8084 | 21792012.9063
77 | Violet Jiyane Secondary | S | Planning and Design: Construction 12 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, 18 toilets, 3 sports ground, car parking | Capital Assets | Gert Sibande | Caroline | Albert Luthuli | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 24397969.2188 |  | 0 | 0 | 0 | 0 | 1720056.8299
78 | Thuto-thebe | S | Planning and Design: Construction 6 Classrooms, library, computer centre, kitchen, 4 toilets, fence, school hall, ramps & rails, 3 sports ground, car parking | Capital Assets | Gert Sibande | Stanwest | Lekwa | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 18841836.351 |  | 0 | 0 | 0 | 1328349.4627 | 17513486.8883
79 | Simunye | p | 8 Classrooms, Admin Block,10 Toilets | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Refurbishment and Renovations | 2019-04-01 |  | 2019-04-01 | 2020-03-30 |  | 2020-03-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 7907900 |  | 0 | 0 | 0 | 0 | 0
80 | Makhosonke | P | 1 Grade R | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Grade R Centres | 2015-04-01 |  | 2015-04-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 169206.5286
81 | Isu Elihle | P | 5 Classrooms, 1 Grade R Centre | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | Substitution of unsafe structures | 2015-04-01 |  | 2015-04-01 | 2016-09-30 |  | 2016-09-30 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 6175636.4732 |  | 0 | 0 | 0 | 0 | 435382.3714
44 | MST Academy (Witbank) | N/A | Refurbishment to existing buildings and conversion of existing offices to 2 lecture rooms, 4 technology centre, administration offices, toilets per MST Specifications | Capital Assets | Nkangala | Emalahleni 1 | Emalahleni | Special Projects | 2014-06-01 |  | 2014-06-01 | 2015-09-30 |  | 2015-09-30 | Equitable Share (ES) | Upgrades & Additions |  | B | Active - Contracted | 20000000 |  | 20000000 | 16000000 | 0 | 0 | MDoE
45 | Pelonolo Special | C | TBA | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Upgrades and Additions | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) |  |  | C |  | TBA |  | 0 | 0 | 0 | 0 | 0
46 | Joseph Mathebula | S | CRDP: Repairs to roof structure undermined by termites and general maintenance | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | Maintenance | 2015-04-01 |  | 2015-04-01 | 2016-03-31 |  | 2016-03-31 | Education Infrastructure Grant (EIG) |  |  | C |  | TBA |  | 0 | 0 | 0 | 0 | 0
48 | Final Account (2014/15 projects) | All | Retention and final payments for 2014/15 Projects | Capital Assets | All | All | All | All | 2015-04-01 |  | 2015-04-01 | 2015-09-30 |  | 2015-09-30 | All | All | Final account | A |  | 0 |  | 70934718 | TBC | 0 | 0 | 0
49 | Other Circuits (Mmamethlake, Nokaneng, Badplaas) | All | Planning and Design: Refurbishment and Renovations | Capital Assets | All | All | All | Refurbishment and Renovations | 2014-04-01 |  | 2014-04-01 | 2020-03-30 |  | 2020-03-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 30000000 |  | 3999998 | 3999999 | 15000000 | 16050000 | 17173500
50 | Valencia | C | 4 Classrooms | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2760022.2642 |  | 0 | 0 | 0 | 0 | 0
51 | Laerskool BTN | P | 3 Classrooms | Capital Assets | Ehlanzeni | Barberton | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2256417.9153 |  | 0 | 0 | 0 | 0 | 159077.463
52 | L/S Laeveld | P | 4 Classrooms | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2760022.2642 |  | 0 | 0 | 0 | 0 | 194581.5696
53 | Matsulu | P | 16 Classrooms, Administration block, 9 Toilets | Capital Assets | Ehlanzeni | Nkululeko | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 17269510.284 |  | 0 | 0 | 0 | 1217500.475 | 16052009.809
54 | Mbombo | C | 4 Classrooms | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2760022.2642 |  | 0 | 0 | 0 | 2300000 | 24600000
55 | Mtfonjeni | P | 12 Classrooms | Capital Assets | Ehlanzeni | Insikazi | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 8280066.7926 |  | 0 | 0 | 0 | 0 | 0
56 | Magogeni | P | 5 Classrooms | Capital Assets | Ehlanzeni | Khulangwane | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 3759206.7003 |  | 0 | 0 | 0 | 0 | 0
57 | Schoemansdal | P | 12 Classrooms, Fence | Capital Assets | Ehlanzeni | Malelane | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 10056801.7926 |  | 0 | 0 | 0 | 709004.5264 | 9347797.2662
75 | Lundanda | C | 12 Toilets | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela | Substitution of unsafe structures | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | o |  | 1152904.7281 |  | 0 | 0 | 0 | 0 | 0
76 | Mambane | S | 5 Classrooms | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 3759206.7003 |  | 0 | 0 | 0 | 0 | 0
77 | Thembeka | P | 23 Classrooms | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 16660251.7982 |  | 0 | 0 | 0 | 0 | 0
76 | Hoyi | P | 12 Toilets | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Substitution of unsafe structures | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | o |  | 1152904.7281 |  | 0 | 0 | 0 | 0 | 0
77 | Evimbilanga | P | 10 Classrooms, Administration block, Computer Centre, Library, School Hall, 28 Toilets, Fence, Water, Kitchen, Ramp & rail, Large Sport Field & parking | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 27308213.9781 |  | 0 | 0 | 0 | 1925229.0855 | 25382984.8927
78 | Ndlaphu | P | 24 Classrooms | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 16560133.5852 |  | 0 | 0 | 0 | 0 | 1167489.4178
79 | Sindzawonye | P | 4 Classrooms | Capital Assets | Ehlanzeni | Sikhulile | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 2760022.2642 |  | 0 | 0 | 0 | 0 | 0
80 | Klipspringer | P | 10 Classrooms, Administration block, Computer Centre, School Hall and construction of 3 classrooms | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 6032517.9153 |  |  |  | 0 | 425292.513 | 5607225.4023
77 | Emjindini | S | Planning and Design: Construction 4 toilets | Capital Assets | Ehlanzeni | Barberton | Umjindi | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 384301.576 |  | 0 | 0 | 0 | 0 | 0
78 | H/S Barberton | S | Planning and Design: Construction 11 toilets, fence & supply water | Capital Assets | Ehlanzeni | Barberton | Umjindi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 3294199.3341 |  | 0 | 0 | 0 | 0 | 232241.0531
79 | Kwa-Jelusa |  | Planning and Design: Construction of Kitchen | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1222933.281 |  | 0 | 0 | 0 | 0 | 0
80 | Evimbilanga | P | Planning and Design: Construction 10 classrooms, Administration Block, Laboratory, library, computer centre, School hall, ramps and rails, fence, water, 28 toilets, 2 sports grounds. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 29147288.6868 |  | 0 | 0 | 0 | 2054883.8524 | 27092404.8344
81 | Masibonisane | P | Planning and Design: Construction 12 Classroom, Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, water, 12 toilets, 1 sport field | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 28574268.5027 |  | 0 | 0 | 0 | 2014485.9294 | 26559782.5732
82 | Mpumelelo | P | Planning and Design: Construction 7 Classroom, Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, 20 toilets, 1 sport field | Capital Assets | Ehlanzeni | Khulangwane | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 24865612.7856 |  | 0 | 0 | 0 | 1753025.7014 | 23112587.0842
78 | Sabatha | P | Supply water | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 553500 |  | 0 | 0 | 0 | 0 | 0
79 | Amon Nkosi | P | Planning and Design: Construction 8 Classroom, library, computer centre, School hall, ramps and rails, fence, water, electricty, kitchen, 24 toilets, 1 sport field | Capital Assets | Ehlanzeni | Barberton | Umjindi | Upgrades and Additions | 2017-04-01 |  | 2017-04-01 | 2018-03-31 |  | 2018-03-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 22870111.7788 |  | 0 | 0 | 1612342.8804 | 20114263.3095 | 1143505.5889
80 | Mayibuye | S | Planning and Design: Construction 4 Classrooms | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2760022.2642 |  | 0 | 0 | 0 | 0 | 194581.5696
81 | S'bongile | P | Planning and Design: Construction 1 Grade R center, 10 classrooms, Administration Block, library, multi media centre, Multi purpose, School hall, ramps and rails, kitchen, 10 toilets, 1 sports ground, car parking | Capital Assets | Ehlanzeni | Nkululeko | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 29137016.1503 |  | 0 | 0 | 0 | 2054159.6386 | 27082856.5117
82 | Camalaza | S | Planning and Design: Construction 12 Classrooms | Capital Assets | Ehlanzeni | Khulangwane | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 8280066.7926 |  | 0 | 0 | 0 | 0 | 583744.7089
83 | MC Zitha | P | Planning and Design: Construction 1 Grade R Centre, 12 Classrooms | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 10680159.3966 |  | 0 | 0 | 0 | 0 | 752951.2375
84 | Gutjwa | P | Planning and Design: Construction 1 Grade R center, 8 Classrooms Administration Block, library, computer center, multi media centre, music room | Capital Assets | Ehlanzeni | Insikazi | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 20045483.8578 |  | 0 | 0 | 0 | 0 | 0
85 | Emtfonjeni | P | Planning and Design: Construction 1 Grade R center, 12 Classrooms Administration Block, library, computer center, multi media centre, music room | Capital Assets | Ehlanzeni | Insikazi | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 22942918.9531 |  | 0 | 0 | 0 | 0 | 1617475.7862
86 | Phola | S | Planning and Design: Construction 12 Classrooms, library, computer center, 8 toilets | Capital Assets | Ehlanzeni | White Hazy 2 | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 16496338.1446 |  | 0 | 0 | 0 | 0 | 1162991.8392
87 | Malekutu | P | Planning and Design: Construction 2 Classrooms, Administration Block, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 10 toilets, 2 sports ground, car parking | Capital Assets | Ehlanzeni | White River | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 17062245.8318 |  | 0 | 0 | 0 | 0 | 0
88 | Hlanganani | S | Planning and Design: Construction 5 Classrooms, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 10 toilets, 2 sports ground, car parking | Capital Assets | Ehlanzeni | White River | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 14420230.7967 |  | 0 | 0 | 0 | 0 | 1016626.2712
89 | Lwaleng | P | Planning and Design: Construction 5 Classrooms, Administration block, library, computer centre, ramps and rails, kitchen, 4 toilets, 2 sports ground, car parking | Capital Assets | Ehlanzeni | White River | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 15103523.0307 |  | 0 | 0 | 0 | 0 | 0
90 | Bhekiswayo | S | Planning and Design: Construction 8 Classrooms, computer centre, multi purpose, 10 toilets, car parking | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 10508385.8893 |  |  |  | 0 | 0 | 740841.2052
91 | Thula | P | Planning and Design: Construction Administration block, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 6 toilets, 2 sports ground, car parking | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 15229226.7081 |  | 0 | 0 | 0 | 0 | 0
79 | Lowveld High | S | 43 Classrooms | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-06-30 |  | 2016-06-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 10049100 | 0 | 0 | 3517185 | 6531915 | 0 | 100491
80 | Ndindindi | P | 15 Classrooms | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 3505500 |  | 0 | 0 | 247137.75 | 3258362.25 | 0
81 | Mtungwa | S | 22 Classrooms, Administration block, Laboratory, Library, Computer Centre | Capital Assets | Ehlanzeni | White River | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6691200 |  | 0 | 0 | 471729.6 | 5884910.4 | 334560
82 | Sidlamafa | S | 20 Classrooms, Administration block, Laboratory, Library, Computer Centre | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6223800 |  | 0 | 0 | 0 | 0 | 0
83 | Tiphembeleni | P | 1 Grade R, 8 Classrooms | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2103300 |  | 0 | 0 | 148282.65 | 1955017.35 | 0
80 | Mayibuye | S | 20 Classrooms, 16 Toilets, Fence | Capital Assets | Ehlanzeni | Mgwenya | Mbombela | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-06-30 |  | 2016-06-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6531300 |  | 0 | 0 | 6531300 | 0 | 65313
38 | Khumbula Secondary School | S | Refurbishment of a Technology & Computer Centre; Construction of 4 Laboratories for Maths, Physics, Chemistry & Life Sciences; and Fencing | Capital Assets | Ehlanzeni | White River | Mbombela | Upgrades and Additions | 2015-03-05 | 3 | 2015-06-05 | 2015-06-15 | 9 | 2016-03-20 | Equitable Share (ES) | Upgrades & Additions | Planning / Construction | A |  | 14130251 |  | 0 | 13282436 | 847815 | 0 | DPWRT
39 | KwaNdebele Science Combined School | C | Refurbishment of a Computer & Science Centre, 4 Laboratories for Maths, Physics, Chemistry & Life Sciences; and Construction of a Perimeter Palisade Fencing |  | Nkangala | Siyabuswa | Dr JS Moroka | Upgrades and Additions | N/A | N/A | N/A | 2015-03-10 | 8 | 2015-11-13 | Equitable Share (ES) | Upgrades & Additions | Construction | A |  | 9336705 |  |  | 9336705 | 0 | 0 | DPWRT
40 | Trichardsfontein Primary School | P | Phase 1: Project concept planning and construction of palisade fencing plus provision of basic services. Phase 2 : Planning and Design: Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, electricity upgrade, school hall, kitchen, 3 sports grounds and car park. |  | Gert Sibande | Highveld East | Govan Mbeki | New Schools | 2015-05-27 | 12 | 2016-06-02 | 2015-09-01 | 6 | 2016-03-05 | Education Infrastructure Grant (EIG) | New & Replacement Schools | Planning / Construction | A |  | 44500000 |  |  | 4591500 | 3660125 | 35317000 | DPWRT
39 | Laerskool BTN | P | 27 Classrooms | Capital Assets | Ehlanzeni | Barberton | Umjindi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6309900 |  | 0 | 0 | 0 | 0 | 444847.95
81 | Hoechst | P | 4 Grade R, 16 Classrooms, 12 Toilets, Fence | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-06-30 |  | 2016-06-30 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 6482100 |  | 0 | 0 | 6482100 | 0 | 64821
82 | Sihlangu | P | 14 Classrooms, 16 Toilets | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 3468600 |  | 0 | 0 | 0 | 0 | 0
83 | Vukasambe | P | 16 Classrooms | Capital Assets | Ehlanzeni | Sikhulile | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 3739200 |  | 0 | 0 | 0 | 0 | 263613.6
84 | Joseph Mathebula | S | 22 Classrooms, Administration block | Capital Assets | Ehlanzeni | Khulangwane | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 5694900 |  | 0 | 0 | 0 | 0 | 0
85 | Sekusile | P | 16 Classrooms, 28 Toilets | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4083600 |  | 0 | 0 | 0 | 0 | 287893.8
86 | Khanyisani | S | 5 Classrooms, Electricity | Capital Assets | Ehlanzeni | White Hazy 2 | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 1476000 |  | 0 | 0 | 0 | 0 | 1476000
87 | Kusile | C | 12 Classrooms, 12 Toilets | Capital Assets | Ehlanzeni | White River | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2952000 |  | 0 | 0 | 0 | 208116 | 2743884
82 | Etimbondvweni | P | 10 Toilets | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 123000 |  | 0 | 0 | 0 | 0 | 0
83 | Salubindza | P | 12 Classrooms | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2804400 |  | 0 | 0 | 0 | 0 | 0
84 | Zakheleni | P | 14 Classrooms, Administration block, 10 Toilets, Fence | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 5608800 |  | 0 | 0 | 0 | 0 | 395420.4
85 | Mpumelelo | P | 10Classrooms, 6 Toilets | Capital Assets | Ehlanzeni | Khulangwane | Mbombela | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2410800 |  | 0 | 0 | 2410800 | 0 | 0
86 | Enzani | P | 16 Classrooms, Administration block, 12 Toilets, Kitchen | Capital Assets | Ehlanzeni | Nkululeko | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4612500 |  | 0 | 0 | 0 | 325181.25 | 4287318.75
87 | Matsamo | P | 17 Classrooms, Administration block | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 4526400 |  | 0 | 0 | 0 | 0 | 319111.2
88 | Njeyeza | S | Laboratory | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Refurbishment and Renovations |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 332100 |  | 0 | 0 | 0 | 0 | 0
89 | Kwadela Secondary | S | Planning and Design: Construction 9 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, 18 toilets, fence, 3 sports ground, car parking | Capital Assets | Gert Sibande | Ermelo 2 | Msukaligwa | Upgrades and Additions | 2018-04-01 |  | 2018-04-01 | 2019-03-30 |  | 2019-03-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 24001627.8973 |  | 0 | 0 | 0 | 1692114.7668 | 22309513.1306
90 | Cana Combined | C | Planning and Design: Construction 1 Grade R center, 8 Classrooms, administration block, laboratory, library, school hall, kitchen, 10 toilets, fence, ramps & rails, 3 sports ground | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 27748761.5527 |  | 0 | 0 | 0 | 1956287.6895 | 25792473.8633
91 | Mpuluzi Secondary | S | Planning and Design: Construction Laboratory, library, school hall, home economics, kitchen, 10 toilets, ramps & rails, water, kitchen, 3 sports ground | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 15200280.7808 |  | 0 | 0 | 0 | 0 | 1071619.795
92 | Tokoloho Primary | P | Planning and Design: Construction 1 Grade R center, 6 Classrooms, administration block, library, computer centre, kitchen, 6 toilets, fence, kitchen, ramps & rails, 2 sports ground, car parking | Capital Assets | Gert Sibande | Balfour | Dipaleseng | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 20196860.1965 |  | 0 | 0 | 0 | 0 | 0
93 | Malibongwe Primary | P | Planning and Design: Construction 1 Grade R center, 5 Classrooms, administration block, library, computer centre, kitchen, 10 toilets, fence, kitchen, ramps & rails, 3 sports ground, car parking | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 20251632.9987 |  | 0 | 0 | 0 | 0 | 0
94 | Zamokuhle Primary | P | Planning and Design: Construction 1 Grade R center, 4 Classrooms, administration block, library, laboratory, computer centre, kitchen, 12 toilets, fence, kitchen, ramps & rails, 3 sports ground, car parking | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 21361084.7216 |  | 0 | 0 | 0 | 0 | 0 |  | 1281665.0833
95 | Imizamoyethu Primary | P | Planning and Design: Construction 1 Grade R center, 3 Classrooms, library, computer centre, kitchen, 4 toilets, fence, kitchen, 1 sports ground, car parking | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 12226881.7304 |  | 0 | 0 | 0 | 0 | 861995.162
96 | Ithole Primary | P | 12 Classrooms, 12 Toilets | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 10634870.0141 |  | 0 | 0 | 0 | 0 | 749758.336
97 | Zamokuhle | P | 12 Classrooms | Capital Assets | Gert Sibande | Highveldridge east | Govan Mbeki | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 9481965.286 |  | 0 | 0 | 0 | 0 | 668478.5527
98 | Msinyane Secondary | S | 10 Classrooms | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7901637.7383 |  | 0 | 0 | 0 | 0 | 0
99 | Phaphamani Primary | P | 9 Classrooms | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7111473.9645 |  | 0 | 0 | 0 | 0 | 501358.9145
100 | Yellowstone | P | 9 Classrooms | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 7111473.9645 |  | 0 | 0 | 0 | 0 | 501358.9145
101 | Isifisosethu Primary | P | 8 Classrooms, Fence | Capital Assets | Gert Sibande | Stanwest | Lekwa | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 8098045.1907 |  | 0 | 0 | 0 | 0 | 570912.1859
102 | The Gem | C | 8 Classrooms | Capital Assets | Gert Sibande | Breyten | Msukaligwa | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 6321310.1907 |  | 0 | 0 | 0 | 0 | 0
103 | Jeug krag Primary | P | 5 Classrooms | Capital Assets | Gert Sibande | Staneast | Lekwa | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 3950818.8692 |  | 0 | 0 | 0 | 0 | 278532.7303
104 | Carolina Combined | P | 2 Classrooms | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Substitution of unsafe structures |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 1580327.5477 |  | 0 | 0 | 0 | 111413.0921 | 1580327.5477
83 | Peter Mabuza Primary | P | 24 Toilets, water | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 2766444.4562 |  | 0 | 0 | 0 | 0 | 0
84 | Ithole Primary | P | 20 Toilets, water | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 2382142.8801 |  | 0 | 0 | 0 | 0 | 0
85 | Sisukumile Secondary | S | 20 Toilets | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1921507.8801 |  | 0 | 0 | 0 | 0 | 0
86 | Sakhisizwe Primary | P | 20 Toilets | Capital Assets | Gert Sibande | Bethal | Govan Mbeki | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1921507.8801 |  | 0 | 0 | 0 | 0 | 0
87 | Ligugu Secondary | S | 16 Toilets | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Water & Sanitation | 2015-06-01 |  | 2015-06-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1537206.3041 |  | 0 | 0 | 0 | 0 | 0
88 | Cebisa Secondary | S | 20 Toilets | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1921507.8801 |  | 0 | 0 | 0 | 0 | 0
89 | Libhaba | P | 10 Toilets | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Water & Sanitation | 2015-06-01 |  | 2015-06-01 | 2015-12-31 |  | 2015-12-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 960753.9401 |  | 0 | 0 | 0 | 0 | 0
90 | Eluyengweni Primary | P | 10 Toilets, water | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1421388.9401 |  | 0 | 0 | 0 | 0 | 0
91 | Salem Combined | C | 10 toilets | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 960753.9401 |  | 0 | 0 | 0 | 0 | 0
92 | Bhekithemba Primary | P | 8 Toilets | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 768603.1521 |  | 0 | 0 | 0 | 0 | 0
93 | Sibongangwane | P | 6 Toilets, water | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 1037087.364 |  | 0 | 0 | 0 | 0 | 0
94 | Mabombe Primary School | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Grade R Centres | 2015-09-01 |  | 2015-09-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 2400092.604 |  | 2400092.604 | 2400092.604 | 0 | 0 | 0
95 | New Ermelo Primary | P | 2 Grade R Centre | Capital Assets | Gert Sibande | Ermelo 2 | Msukaligwa | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 4800185.208 |  | 0 | 0 | 0 | 0 | 338413.0572
96 | Kwachibikhulu Primary | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Breyten | Msukaligwa | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754
97 | T.P Stratten | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 169206.5286
98 | Phumula Primary | P | 2 Grade R Centre | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 4800185.208 |  | 0 | 0 | 0 | 0 | 338413.0572
99 | Welgevond | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 0
100 | Thandeka Primary | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Stanwest | Lekwa | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 169206.5286
101 | Lamlile Primary | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Bethal | Govan Mbeki | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754
102 | Vuka Primary | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 169206.5286
103 | SS Mshayisa Primary | P | 1 Grade R Centre | Capital Assets | Gert Sibande | Highveld Ridge West | Govan Mbeki | Grade R Centres |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2400092.604 |  | 0 | 0 | 0 | 0 | 0
104 | Leseli Combined | C | Rehabilitation of damages to 24 classrooms, 32 Toilets, Fence | Capital Assets | Gert Sibande | Stanwest | Lekwa | Storm Damaged Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 7662900 |  | 0 | 540234.45 | 7122665.55 | 0 | 76629
105 | Nthoroane Secondary | P | Rehabilitation of damages to 16 classrooms, 24 Toilets | Capital Assets | Gert Sibande | Balfour | Dipaleseng | Storm Damaged Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | B |  | 4034400 |  | 0 | 284425.2 | 3749974.8 | 0 | 0
95 | Mbalenhle Primary | P | Rehabilitation of damages to 24 Toilets | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 295200 |  | 0 | 0 | 0 | 0 | 0
96 | Elangwane Secondary | S | Rehabilitation of damages to 22 Toilets | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 270600 |  | 0 | 0 | 0 | 0 | 0
97 | Zinikeleni Secondary | S | Rehabilitation of damages to 16 Toilets | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 196800 |  | 0 | 0 | 0 | 0 | 0
98 | Sobhuza Primary | P | Rehabilitation of damages to 5 classrooms, 15 Toilets | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 1353000 |  | 0 | 0 | 0 | 0 | 0
99 | Klein Vrystad Primary | P | Rehabilitation of damages to 2 classrooms, 15 Toilets | Capital Assets | Gert Sibande | Piet-Retief | Msukaligwa | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 651900 |  | 0 | 0 | 0 | 0 | 0
100 | Chief T.D Secondary School | S | Rehabilitation of damages to 12 classrooms, 10 Toilets | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 2927400 |  | 0 | 0 | 0 | 0 | 0
101 | Sunduza Primary | S | Rehabilitation of damages to 3 classrooms, 10 Toilets | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | C |  | 824100 |  | 0 | 0 | 0 | 0 | 0
102 | Baadjiesbult Combined | P | Rehabilitation of damages to 10 toilets | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 123000 |  | 0 | 0 | 0 | 0 | 0
103 | Khuphukani Primary | P | Rehabilitation of damages to 8 toilets | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 98400 |  | 0 | 0 | 0 | 0 | 0
104 | Bhekimfundvo Primary | P | Rehabilitation of damages to 8 toilets | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Storm Damaged Schools | 2015-05-01 |  | 2015-05-01 | 2015-08-31 |  | 2015-08-31 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 98400 |  | 0 | 0 | 0 | 0 | 0
41 | Lindzalokuhle Primary School | P | Rehabilitation of damages to 8 toilets | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Water & Sanitation | N/A | N/A | N/A | 2015-01-19 | 4 | 2015-05-15 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 1271442 |  | 0 | 1017153.6 | 0 | 0 | DPWRT
42 | Imisebeyelanga Primary | P | Rehabilitation of damages to 6 toilets | Capital Assets | Gert Sibande | Stan East | Lekwa | Storm Damaged Schools | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment |  | o |  | 73800 |  | 0 | 0 | 0 | 0 | 0
43 | Reggie Masuku Secondary | S | Fence | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 1660500 | 0 | 0
44 | Siyabonga Secondary | S | Fence | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 0 | 1660500 | 0
45 | Phembindlela Primary | P | Fence | Capital Assets | Gert Sibande | Volksrust | Dr Pixley Ka Isaka Seme | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 1660500 | 0 | 0
46 | Rev SA Nkosi Secondary | S | Fence | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 1660500 | 0 | 0
47 | Mkhomazi primary | P | Fence | Capital Assets | Gert Sibande | Breyten | Msukaligwa | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 0 | 0 | 1660500
48 | Diepgezet Primary | P | Fence | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 0 | 0 | 1660500
49 | Maqhwauzela Combined | C | Fence | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 1660500 | 0 | 0
50 | MD coovidia Combined | C | Fence | Capital Assets | Gert Sibande | Bethal | Govan Mbeki | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 0 | 1660500 | 0
107 | Siphumelele Combined | C | Electricity | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | Upgrades and Additions | 2015-06-01 |  | 2015-06-01 | 2016-01-31 |  | 2016-01-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 799500 |  | 0 | 0 | 0 | 0 | 0
108 | Silindzile Primary | P | Fence | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 0 | 0 | 1660500
109 | Buhlebuyeza Primary | P | Fence | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 1660500 |  | 0 | 0 | 1660500 | 0 | 0
108 | Ziwelile Primary | P | Electricity | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | Upgrades and Additions | 2015-06-01 |  | 2015-06-01 | 2016-01-31 |  | 2016-01-31 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | o |  | 799500 |  | 0 | 0 | 0 | 0 | 0
109 | Isiyalu Primary | P | Fence, electricity | Capital Assets | Gert Sibande | Stan East | Lekwa | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2460000 |  | 0 | 0 | 0 | 0 | 0
110 | Nokuthula Primary | P | Fence, electricity | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | Upgrades and Additions |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | C |  | 2460000 |  | 0 | 0 | 2460000 | 0 | 0
42 | Basizeni Special School | SP | Dismantling and carting away of existing damaged prefab buildings and construction of 8 New Special School Classrooms | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki | Storm Damaged Schools | TBC | TBC | TBC | 2015-04-22 | 6 | 2015-10-25 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment | Construction | B | Active - Not Contracted | 11658541.2544 |  | 345261 | 10842443.3666 | 816097.8878 | 0 | DPWRT | RIU
43 | Tsandzanani Primary School | P | Rehabilitation of Storm Damaged Structures. Demolishing of 18 unsafe classrooms and construction of 18 new classrooms and 20 Enviro-loo toilets. | Capital Assets | Ehlanzeni | Nkululeko | Mbombela | Storm Damaged Schools | N/A | N/A | N/A | 2015-03-01 | 12 | 2016-03-01 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 17676833 |  | 15732381.37 | 16439454.69 | 1237378.31 | 176768.33 | DPWRT | RIU
44 | Panyana Primary School | P | CRDP: Rehabilitation of Storm Damaged Structures. Demolishing of 12 unsafe classrooms and construction of 12 new classrooms and 22 Enviro-loo toilets. | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | Storm Damaged Schools | N/A | N/A | N/A | 2015-03-01 | 12 | 2016-03-01 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 10988814 |  | 9780044.46 | 10219597.02 | 769216.98 | 109888.14 | DPWRT
45 | Mayflower Secondary School | S | Replacement of damaged roof covering & purlins to 4 Classrooms and Ablutions. Replacement of ceilings and servicing of damaged electricals | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Storm Damaged Schools | N/A | N/A | N/A | 2015-02-16 | 3 | 2015-05-29 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 774345 |  |  | 774345 |  |  | RIU / DPWRT
46 | Dundonald Circuit Office |  | Replace damaged purlins, roof covering (klip-lok) to 2 Blocks in isolated panels. Replacement of damaged ridge capping, fascia & barge boards and damaged ceilings. Fixing, securing and repositioning water tank. Remedial works to ablutions. | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 3 | 2015-08-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 408291 |  |  | 408291 |  |  | RIU / DPWRT | Term contractors
47 | Salubindza Primary School | P | Replace roof structure and covering to 4 Classroom Block. Remedial works to walls and floors. Fixing, servicing and restoration of electrical fittings and cabling. | Capital Assets | Ehlanzeni | White Hazy | Mbombela | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 3 | 2015-08-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 732108 |  |  | 732108 |  |  | RIU / DPWRT | Term contractors
48 | Sivumelene Primary School | P | Installation of a sub-soil/stormwater drainage system and cutting berms around affected buildings with concerete channels | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 3 | 2015-08-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 642000 |  |  | 642000 |  |  | RIU / DPWRT
49 | Mantwani Primary School | P | Installation of a sub-soil/stormwater drainage system and cutting berms around affected buildings with concerete channels | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 263000 |  |  | 263000 |  |  | RIU / DPWRT
50 | Leonard Ntshutshe Secondary School | S | Replace part of roof structure and complete roof covering to 4 Classroom Blocks. Fix damaged rafters & end purlins and ridge capping to 2 x 4 Classroom Blocks & Laboratory. Remedial works to floors, walls and replacement of ceilings 4 Classsroom Block. Fixing, servicing and restoration of electrical fittings and cabling. | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 3 | 2015-08-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 788424 |  | 788424 | 788424 | 0 | 0 | RIU / DPWRT
51 | Ngilandi Secondary School | S | Rehabilitation of Storm Damaged Structures. (Scope of works currently being finalized) | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | Storm Damaged Schools | N/A | N/A | N/A | 2015-05-11 | 3 | 2015-08-12 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Contracted | 1512574.8 |  | 1421820.312 | 1512575 | 0 | 0 | DPWRT
52 | Maridili Primary School | P | Rehabilitation of storm damage | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | Storm Damaged Schools | N/A | N/A | N/A | 2015-05-11 | 3 | 2015-08-12 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Not Contracted | 437979 |  |  | 437979 | 0 | 0 | DPWRT | Term contractors
53 | Magudu Primary School | P | Rehabilitation of storm damage | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Storm Damaged Schools | N/A | N/A | N/A | 2015-05-11 | 4 | 2015-09-12 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Not Contracted | 1781170 |  |  | 1781170 | 0 | 0 | DPWRT | Term contractors
54 | Mosipa Secondary School | S | Rehabilitation of storm damage | Capital Assets | Bohlabela | Casteel | Bushbuckridge | Storm Damaged Schools | N/A | N/A | N/A | 2015-05-11 | 4 | 2015-09-12 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Not Contracted | 2374893 |  |  | 2374893 | 0 | 0 | DPWRT | Term contractors
55 | Njonjela Primary School | P | Rehabilitation of storm damage | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Storm Damaged Schools | 2015-04-01 | 1 | 2015-04-23 | 2015-07-07 | 3 | 2015-10-08 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | B | Active - Not Contracted | 4007633 |  |  | 4007633 | 0 | 0 | DPWRT | Term contractors
56 | Floraphophe Primary School | P | Rehabilitation of storm damage | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | Storm Damaged Schools | N/A | N/A | N/A | 2015-05-11 | 3 | 2015-08-12 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A | Active - Not Contracted | 1335878 |  |  | 1335878 | 0 | 0 | DPWRT | Term contractors
57 | Bethamoya Primary School | P | Demolishing of 4 Damaged Classrooms and 1 shack classroom and construction 5 new classrooms | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaiah Seme | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 4 | 2015-09-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 3943144 |  |  | 3943144 | 0 | 0 | RIU / DPWRT
58 | Landulwazi Combined School | C | Rehabilitation of storm damage | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 3 | 2015-08-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 980484 |  |  | 980484 |  |  | DPWRT
59 | Magotshwa Primary School | P | Rehabilitation of storm damage | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 4 | 2015-09-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 3467500 |  |  | 3467500 |  |  | DPWRT
60 | Malelane Circuit Office | CIR | Rehabilitation of storm damage | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 4 | 2015-09-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 1512229 |  |  | 1512229 |  |  | DPWRT
61 | Bambisana Primary School | P | Rehabilitation of storm damage | Capital Assets | Nkangala | Delmas | Victor Khanye (Delmas) | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 612340 |  |  | 612340 |  |  | DPWRT
62 | Dikotelo Primary School | P | Rehabilitation of storm damage | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 413000 |  |  | 413000 |  |  | DPWRT
63 | Sivumelene Secondary School | S | Rehabilitation of storm damage | Capital Assets | Nkangala | Wiltevrede | Dr JS Moroka | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 642000 |  |  | 642000 |  |  | DPWRT
64 | Velangezwi Primary School | P | Rehabilitation of storm damage | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 642000 |  |  | 642000 |  |  | DPWRT
65 | Vezimfundo Primary School | P | Rehabilitation of storm damage | Capital Assets | Nkangala | Delmas | Victor Khanye (Delmas) | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 | 2 | 2015-07-30 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 642000 |  |  | 642000 |  |  | DPWRT
66 | Mholo Primary School |  |  |  | Gert Sibande | Badplaas | Albert Luthuli | Storm Damaged Schools | 2015-03-29 | 1 | 2015-04-29 | 2015-05-29 |  |  | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A |  | 0 |  |  | TBA | 0 | 0 | DPWRT
78 | Lugedlane Primary School |  |  |  | Ehlanzeni | Nkomazi West | Nkomazi | Storm Damaged Schools |  |  | 0 |  |  | 0 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A |  | 0 |  |  | TBA
79 | Bongokuhle Primary School | [6 empty] | Storm Damaged Schools |  |  | 0 |  |  | 0 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A |  | 0 |  |  | TBA
67 | Mugena High School | H | Planning, Demolition of existing structures and Construction of 24 Classrooms, Administration block, Library, Computer centre, School Hall, Ablutions, Fence, Upgrade Water and Electricity supply, Kitchen, Ramps + rails, 3 Sports grounds and Car park. | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | New Schools | N/A | N/A | N/A | 2015-01-13 | 12 | 2016-01-20 | Equitable Share (ES) | New & Replacement Schools | Construction | A | Active - Contracted | 57018156.8912 |  | 0 | 46316341.202 | 5701815.6891 | 0 | DPWRT
68 | Umzimvelo Secondary School | S | CRDP: Construction of 14 Enviro-Loo toilets | Capital Assets | Gert Sibande | Breyten | Msukaligwa | Water & Sanitation | N/A | N/A | N/A | 2015-01-19 | 4 | 2015-05-15 | #REF! | Upgrades & Additions | Construction | A | Active - Contracted | 409345.77 | 0 | 0 | 245607.462 | 0 | 0 | DPWRT
69 | Siligane Secondary School | S | 800021105 | Capital Assets | Ehlanzeni | Insikazi | Mbombela | Water & Sanitation | N/A | N/A | N/A | 2015-01-19 | 3 | 2015-04-23 | #REF! | Upgrades & Additions | Construction | A | Active - Contracted | 919940.46 |  | 0 | 551964.276 | 0 | 0 | DPWRT
70 | EJ Singwane Secondary School | S | 800003178 | Capital Assets | Ehlanzeni | Sikhulile | Mbombela | Water & Sanitation | N/A | N/A | N/A | 2015-01-19 | 3 | 2015-04-22 | #REF! | Upgrades & Additions | Construction | A | Active - Contracted | 2038543.3 |  | 0 | 1223125.98 | 0 | 0 | DPWRT
71 | Shalamuka | P | Completion of 12 Enviro-Loo toilets | Capital Assets | Bohlabela | Mkhulhu | Bushbuckridge | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 |  | Upgrades & Additions |  | o |  | 1054486.0318 |  | 0 | 1054486.0318 | 0 | 0 | 0
72 | Samson Sibuyi | P | Completion of 8 Enviro-Loo toilets | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 |  | Upgrades & Additions |  | o |  | 702990.6879 |  | 0 | 702990.6879 | 0 | 0 | 0
73 | Salani | P | Completion of 8 Enviro-Loo toilets | Capital Assets | Bohlabela | Clare A | Bushbuckridge | Water & Sanitation | 2015-10-01 |  | 2015-10-01 | 2016-02-28 |  | 2016-02-28 |  | Upgrades & Additions |  | o |  | 702990.6879 |  | 0 | 702990.6879 | 0 | 0 | 0
74 | Hundzukani | P | CRDP: Construction of 8 Enviro-Loo toilets | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Water & Sanitation | 2014-04-01 |  | 2014-04-01 | 2014-09-30 |  | 2014-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 702990.6879 | 0 | 702990.6879 | 0 | 0 | 0 | 0
75 | Ian Mackenzie | S | CRDP: Construction of 10 Enviro-Loo toilets | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | Water & Sanitation | 2014-04-01 |  | 2014-04-01 | 2014-09-30 |  | 2014-09-30 | Education Infrastructure Grant (EIG) | Upgrades & Additions |  | B |  | 878738.3598 | 0 | 878738.3598 | 0 | 0 | 0 | 0
84 | EPWP - Data Capturing | N/A | Data capturing and reports for EPWP projects | Capital Assets | All | All | All | Special Projects | 2014-04-01 |  | 2014-04-01 | 2015-03-31 |  | 2015-03-31 | Extended Public Works Programme (EPWP) | Upgrades & Additions |  | A | Active - Contracted | 0 |  | 275000 | 288750 | 303187.5 | 318346.875 | MDoE
71 | Sinethemba Secondary School | S | CRDP: Construction of 1 new workshop and refurbishment of 3 workshops. | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | Technical Schools | 2015-04-01 | 3 | 2015-07-03 | 2015-08-06 | 14 | 2016-10-13 | MST - Technical Recapitalisation | Upgrades & Additions | Planning / construction | A | Proposed | 11600000 | 3000000 | 0 | 8100000 | 3500000 | 0 | DPWRT | Determine contracting strategy prefarably RIU
72 | Bonginsimbi ComprehensiveSchool | S | Refurbishment of 4 workshops to comply with safety standards. | Capital Assets | Nkangala | eMalahleni 1 | Emalahleni | Technical Schools | 2016-06-01 |  | 2016-06-01 | 2017-05-31 |  | 2017-05-31 | MST - Technical Recapitalisation | Upgrades & Additions |  | C |  | 10800000 | 3000000 | 0 | 0 | 10800000 | 0 | 0
73 | Kusasalethu Secondary School | S | Refurbishment of 4 workshops to comply with safety standards. | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki | Technical Schools | 2017-06-01 |  | 2017-06-01 | 2018-05-31 |  | 2018-05-31 | MST - Technical Recapitalisation | Upgrades & Additions |  | C |  | 10800000 | 3000000 | 0 | 0 | 0 | 10800000 | 0
74 | Masizakhe Secondary School | S | Construction of 2 new workshops and refurbishment of 2 workshops to comply with safety standards. | Capital Assets | Gert Sibande | Breyten | Msukaligwa | Technical Schools | 2017-06-01 |  | 2017-06-01 | 2018-05-31 |  | 2018-05-31 | MST - Technical Recapitalisation | Upgrades & Additions |  | C |  | 12400000 | 3000000 | 0 | 0 | 0 | 12400000 | 0
72 | Sophungane Combined School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Planning / construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
73 | Lugebhuta Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Ehlanzeni | Malelane | Nkomazi | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Planning / construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
74 | Mjokwane Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Planning / construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
75 | Thomas Nhlabathi Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Highveld Ridge West | Govan Mbeki | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Planning / construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
76 | Zinikeleni Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
77 | Lindile Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
78 | Bonginsimbi Comprehensive School | S | Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | eMalahleni 1 | Emalahleni | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
79 | Ramoshidi Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
80 | Sofunda Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
81 | Khamane Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Dinaledi Schools | 2015-04-01 | 2 | 2015-06-01 | 2015-07-01 | 2 | 2015-09-01 | MST - Dinaledi Grant | Upgrades & Additions | Construction | A | Proposed | 300000 |  | 0 | 300000 | 0 | 0 | DPWRT | Term contractors
82 | Lehlasedi High School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Bohlabela | Shatale | Bushbuckridge | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
83 | Inkomazi Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
84 | Khutsalani Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Ehlanzeni | Insikazi | Mbombela | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
85 | Alpheus D Nkosi Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Bethal | Govan Mbeki | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0
86 | Takheni Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
87 | Highveld Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
88 | Mmametlhake Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
89 | Sozama Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
90 | Allendale Secondary School | S | Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | eMalahleni 3 | Emalahleni | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
91 | Kwamhlanga Secondary School | S | CRDP: Renovation and furnishing of science laboratory. | Capital Assets | Nkangala | KwaMhlanga South West | Thembisile Hani | Dinaledi Schools | 2016-06-01 |  | 2016-06-01 | 2017-01-31 |  | 2017-01-31 | MST - Dinaledi Grant | Upgrades & Additions |  | C |  | 300000 |  | 0 | 0 | 300000 | 0 | 0
92 | District Administration | CIR | District Administered Maintenance | Capital Assets | All | All | All | Maintenance | 2014-04-01 |  | 2014-04-01 | 2015-03-31 |  | 2015-03-31 | Equitable Share (ES) | Maintenance & Repairs |  | C |  | 0 | 0 | 0 | 0 | 0 | 0
93 | Vulamehlo Primary | Primary | CRDP. Demolition of 16 precast classrooms and Construction 16 Classrooms, administration block, library, computer centre, 20 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | T/Fontein N | Thembisile Hani | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 33819626.7501 |  | 0 | 0 | 0 | 2384283.6859 | 31435343.0642
94 | Bonginhlanhla Primary | Primary | Demolition of 24 asbestos structures and Construction of a Grade R Centre, 18 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 39468863.2059 |  | 0 | 0 | 0 | 2782554.856 | 36686308.3498
95 | Mphephethe Primary | Primary | Demolition of 17 asbestos structures and construction of 14 classrooms , Grade R Centre kitchen , library , computer centre , 12 toilets , car park and 3 sports grounds. | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 20535698.8947 |  | 0 | 0 | 0 | 0 | 0
96 | HTS Middelburg | Secondary | Replacement of 7 asbestos structures and construction of 6 classrooms. | Capital Assets | Nkangala | Steve Tshwete 1 | Steve Tshwete | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 4576470.143 |  | 0 | 0 | 0 | 32264.1145 | 4544206.0285
97 | Thushanang Primary | Primary | Demolition of existing asbestos structures and construction of 1 Grade R Centre, kitchen , fence, library , car park and 3 sports grounds. | Capital Assets | Nkangala | Steve Tshwete 3 | Steve Tshwete | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 8747295.4536 |  | 0 | 0 | 0 | 0 | 0
98 | Laeskool Delmas | Primary | Demolotion of 8 asbestos structures and construction of 8 classrooms. | Capital Assets | Nkangala | Victor Khanye | Victor Khanye | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 6058090.1907 |  | 0 | 0 | 0 | 0 | 427095.3584
99 | Mmadimo Primary | Primary | CRDP. Construction of a Grade R Centre, 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 26946212.5676 |  | 0 | 0 | 0 | 0 | 1899707.986
100 | Makhosoke Primary | Primary | CRDP. Demolition of 12 delapidated classrooms and 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 30598430.8667 |  | 0 | 0 | 0 | 2157189.3761 | 28441241.4906
101 | Laerskool Ellof | Primary | Demolition of 5 asbestos classrooms , Construction of 5 classrooms , Grade R Centre , administration block , completion of an existing School Hall and refurbishment of & renovation of 13 classrooms. | Capital Assets | Nkangala | Victor Khanye | Victor Khanye | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 20535698.8947 |  | 0 | 0 | 0 | 0 | 1447766.7721
102 | Benzangani Primary | Primary | CRDP. Construction of a Grade R Centre, 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 27788602.1141 |  | 0 | 0 | 0 | 1959096.449 | 25829505.6651
103 | Laerskool Klipfontein | Primary | Demolition of 10 asbestos classrooms , 1 laboratory and construction of 10 classrooms and laboratory . Refurbishment of other existing structures. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 10629079.947 |  | 0 | 0 | 0 | 0 | 749350.1363
104 | Laerskool Kragbron | Primary | Replacement of 12 asbestos classrooms and construction 8 classrooms. | Capital Assets | Nkangala | Emalahleni 1 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 6387115.1907 |  | 0 | 0 | 0 | 0 | 450291.6209
105 | Tjhidelani Primary | Primary | Construction of Grade R Centre , library ,kitchen, demolition of 18 asbestos toilets and construction of 24 toilets. | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 7749693.9098 |  | 0 | 0 | 0 | 546353.4206 | 7203340.4891
106 | Robert Carruthers | P | Replacement of 5 asbestos classrooms and construction of 5 classrooms. Refurbishment and rehabilitation of 36 classrooms , 1 administration , 1 library , 1 laboratory , 3 computer centres | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 18779204.2383 |  | 0 | 0 | 0 | 0 | 0
107 | Laerskool Krielpark | Primary | Demolition of 2 asbestos classrooms and construction of 2 classrooms. Refurbishment and renovation of existing 21 classrooms , 1 administration block, 2 special centres , 1 library , 1 lab and 49 toilets. | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 9101839.0477 |  | 0 | 0 | 0 | 0 | 641679.6529
108 | Laerskool Balmoral | Primary | Demolition of 3 asbestos classrooms , 1 school hall and construction of 3 classrooms and 1 school hall. Refurbishment and renovation of existing facilities. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Substitution of unsafe structures |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 9311169.7246 |  | 0 | 0 | 0 | 0 | 656437.4656
109 | Buhlebemfundo Primary School | P | CRDP. Demolition of 16 precast classrooms and Construction 16 Classrooms, administration block, library, computer centre, 20 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Kwaggafontein West | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 33819626.7501 |  | 0 | 0 | 2384283.6859 | 29067969.1917 | 2367373.8725
110 | Mabothe Secondary | Secondary | Construction of 5 additional classrooms , 10 toilets, kitchen and renovation of existing structures. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 7121581.0902 |  | 0 | 0 | 0 | 0 | 502071.4669
111 | Siphumule Primary | Primary | Construction of 5 classrooms , Grade R Centre administration block , library , kitchen, School Hall , fence , 12 toilets , 2 Sports Grounds , Car Park and renovation of classrooms. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 24850031.3106 |  | 0 | 0 | 0 | 1751927.2074 | 23098104.1032
112 | Somabedlana Primary | Primary | Construction of 20 classrooms , administration block , Library , Grade R Centre , 12 toilets , Fence , Kitchen , 3 Sports Grounds and Car Park. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 29136662.015 |  | 0 | 0 | 0 | 2054134.6721 | 27082527.3429
113 | Mkhulu Combined | Combined | Construction of 5 classrooms , Grade R Centre administration block , library , kitchen, fence , 12 toilets , 2 Sports Grounds , Car Park and renovation of classrooms. | Capital Assets | Nkangala | Middelburg 3 | Steve Tshwete | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 19192550.4075 |  | 0 | 0 | 0 | 0 | 1353074.8037
114 | Sikhulisiwe Primary | Primary | CRDP. Construction of 6 Classrooms , administration block , library , kitchen , laboratory fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms. | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 20658830.286 |  | 0 | 0 | 0 | 1456447.5352 | 19202382.7508
115 | Entokozweni Secondary | Secondary | Construction of 8 classrooms , Life Science Laboratory , Kitchen , Library , 12 toilets , 3 Sports Grounds and palisade fence. | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 14673417.4771 |  | 0 | 0 | 0 | 0 | 1034475.9321
116 | Sithenjisiwe Secondary | Secondary | CRDP. Construction of administration block , library, Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16739092.9149 |  | 0 | 0 | 0 | 0 | 0
117 | Masobye Primary | Primary | CRDP . Construction of administration block , library , Computer Centre , kitchen and Grade R Centre , 2 Sports Grounds ,Car Park. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 13102690.1895 |  | 0 | 0 | 0 | 0 | 923739.6584
118 | Sukumani | Primary | Construction of administration block , library , Computer Centre , kitchen and Grade R Centre , 2 Sports Grounds ,Car Park. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 13102690.1895 |  | 0 | 0 | 0 | 0 | 0
119 | Matempule Primary | Primary | CRDP.Construction of Grade R Centre , Administration block , Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 15796054.6209 |  | 0 | 0 | 0 | 0 | 0
120 | Sobantu Secondary | Secondary | CRDP.Completion of Administration block construnction of Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 10004408.6351 |  | 0 | 0 | 0 | 0 | 0
121 | Ndayi Primary | Primary | CRDP. Construction of Grade R Centre , library , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms and 1 administration block. | Capital Assets | Nkangala | KwaMhlanga North East | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 12547775.1817 |  | 0 | 0 | 0 | 0 | 884618.1503
122 | Hlalakahle Secondary | Secondary | CRDP - Planning and Design: Construction of administration block, computer centre, School Hall, kitchen, laboratory, 12 toilets, 3 Sports Grounds and Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 21586263.3568 |  | 0 | 0 | 0 | 1521831.5667 | 20064431.7901
123 | Ziphakamiseni Secondary | Secondary | CRDP. Construction of 12 additional classrooms , library ,Fence laboratory , kitchen, ramp & rails , water , electricity , 3 Sports Grounds , Car Park and renovation of 15 classrooms. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 24347471.6151 |  | 0 | 0 | 0 | 0 | 0
124 | Phumzile Secondary | S | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | Tweefoontein North | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16477348.9149 |  | 0 | 0 | 0 | 0 | 1161653.0985
125 | Sibongimpumelelo Primary | Primary | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16477348.9149 |  | 0 | 0 | 1161653.0985 | 14491828.3707 | 823867.4457
126 | LD Moetanalo Secondary | Secondary | Construction of 8 classrooms , Life Science Laboratory , Kitchen , Library , 12 toilets , fence, 3 Sports Grounds and palisade fence. | Capital Assets | Nkangala | Steve Tshwete 1 | Steve Tshwete | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 14398591.8148 |  | 0 | 0 | 0 | 0 | 1015100.7229
127 | Sothembani Primary | Primary | Demolition of 5 unsafe classrooms , Construction of 5 classrooms , administration block, library , laboratory , kitchen , fence , 12 ablution facilities, car park and 2 sports grounds . Renovation of 8 classrooms. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 19125030.3433 |  | 0 | 0 | 0 | 1348314.6392 | 17776715.7041 |  | 1147501.8206
128 | Zakheni Secondary | S | Construction of administration block , library , kitchen , 12 toilets , 2 Sports Grounds and Car Park. Renovation of existing 16 classrooms. | Capital Assets | Nkangala | kwaMhlanga S/W | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 13817028.9343 |  | 0 | 0 | 0 | 0 | 0
129 | Vukuzame Secondary | S | Construction of 3 additional classrooms , 1 administration block , 1 library , kitchen , School hall , 3 sports grounds and car park. Renovation of existing 16 classrooms , computer cenre and laboratory. | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 21637053.0246 |  | 0 | 0 | 0 | 0 | 1525412.2382
130 | Ramodiegi Primary | P | Construction of administration block , library ,computer centre Grade R Centre , fence and 12 ablution facilities.Refurbishment and renovation of 7 existing classrooms. | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 15260806.6366 |  | 0 | 0 | 0 | 0 | 0
131 | Makerana Primary | Primary | Construction of administration block , library , Kitchen , Computer Centre , Grade R Centre , fence and 12 ablution facilities.Refurbishment and renovation of 16 classrooms. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 18587039.9176 |  | 0 | 0 | 0 | 0 | 1310386.3142
132 | Poolzee Combined | Combined | Construction of 5 Classrooms , administration block , laboratory, library, Kitchen, Fence, Car park and 2 Sports Grounds and refurbishment of 13 classrooms. | Capital Assets | Nkangala | Steve Tshwete 3 | Steve Tshwete | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 19140625.6152 |  | 0 | 0 | 0 | 0 | 1349414.1059
133 | Sizamakwethu Primary | Primary | CRDP. Construction of administration block , library , computer centre , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms . | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16186947.3136 |  | 0 | 0 | 0 | 0 | 0
134 | Zidobhele Secondary | Secondary | Construction of 4 classrooms , 1 administration block , library , laboratory , computer centre , School Hall , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 23691400.1896 |  | 0 | 0 | 0 | 0 | 0
135 | Musi Primary | Primary | Construction of Grade R facilities, library , Kithchen , Computer Centre , Fence , ramp & rails . | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 14089765.1895 |  | 0 | 0 | 0 | 0 | 993328.4459
136 | Andries Mashile Primary | Primary | Construction of 3 classrooms , 1 administration block , library , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 14110981.8496 |  | 0 | 0 | 0 | 994824.2204 | 14110981.8496
137 | Mafa Max Motloung | Secondary | Construction of 3 classrooms , laboratory , library , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. | Capital Assets | Nkangala | Victor Khanye | Victor Khanye | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 10937550.2017 |  | 0 | 0 | 0 | 0 | 0
138 | Nkosiphile Primary | Primary | Demolition of 5 unsafe classrooms , Construction of 5 classrooms , administration block , kitchen , fence , 12 ablution facilities, car park and 2 sports grounds . Renovation of 8 classrooms. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 15934711.066 |  | 0 | 0 | 0 | 0 | 0
139 | Somlingo Primary | Primary | CRDP. Construction of a library , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms and 1 administration block. | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 10147682.5777 |  | 0 | 0 | 0 | 0 | 0
140 | Hlonipha Secondary | S | Construction of 4 additional classrooms , library , kitchen , computer centre 1 fence , 12 toilets , car park and 3 sports grounds. Renovation and refurbishment of 16 existing classrooms , 1 administration block and laboratory. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16596798.2212 |  | 0 | 0 | 0 | 0 | 1170074.2746
141 | Somtshongweni Primary | Primary | Construction of Grade R Centre , administration block , library , kitchen , fence , ablution facilities and renovation and refurbishment of 16 existing classrooms. | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16809366.5383 |  | 0 | 0 | 0 | 0 | 0 |  | 1008561.9923
142 | Mpilonhle Primary | Primary | Construction of Grade R Centre , administration block , library , kitchen , fence . Renovation and refurbishment of 20 existing classrooms and 24 existing ablution facilities . | Capital Assets | Nkangala | Emakhazeni | eMakhazeni | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 16886461.8102 |  | 0 | 0 | 0 | 0 | 1190495.5576
143 | Mapule Sindane | Primary | Construction of a kitchen, fence. Renovation and refurbishment of 23 existing classrooms and 18 existing ablution facilities. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 8596168.281 |  | 0 | 0 | 0 | 0 | 606029.8638
144 | Siyathokoza Primary | Primary | Construction of Grade R Centre , 3 classrooms , library , kitchen , 16 toilets . Renovation and refurbishment of 20 existing classrooms and 24 existing ablution facilities . | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Upgrades and Additions |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | C |  | 14088259.673 |  | 0 | 0 | 0 | 0 | 0
133 | Lehlaka Combined | Combined | Renovations of 16 classrooms , library , laboratory and computer centre. Construction of kitchen , fence , car park and 3 sports grounds. | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 9314488.281 |  | 0 | 3260070.8983 | 6054417.3827 | 0 | 93144.8828
134 | Nyabela Primary | Primary | CRDP. Renovations of 16 classrooms, Administration Block, and Construction of 12 toilets , 2 sports grounds , fence and Car Park . | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 8406829.7281 |  | 0 | 0 | 0 | 0 | 0
134 | Duduzile Secondary | Secondary | Refurbishment of existing 16 classrooms , administration block , Laboratory , Library , 1 School Hall , and Construction of kitchen , 12 ablution facilities fence , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 10847463.0091 |  | 0 | 3796612.0532 | 7050850.9559 | 0 | 108474.6301
135 | Botleng Secondary School | S | Refurbishment of existing 33 classrooms , 1 administration block , Library , 4 laboratories , 1 Computer Centre , 9 ablution blocks and Construction of kitchen , School Hall and 2 Sports grounds. | Capital Assets | Nkangala | Victor Khanye | Victor Khanye | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 16165950.885 |  | 0 | 5658082.8098 | 10507868.0752 | 0 | 161659.5089
136 | Sibukosethu Primary | Primary | Refurbishment of existing 25 classrooms , administration block , Library , 1 School Hall , 35 toilets and Construction of Grade R Centre kitchen , fence , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 14296350.885 |  | 0 | 0 | 0 | 0 | 0
137 | Zithuthukiseni Primary | Primary | CRDP. Renovation of existing 16 classrooms , administration block , construction of library , library , Kitchen , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 10179267.8496 |  | 0 | 0 | 0 | 0 | 0
136 | Ebhudlweni | Primary | Renovations of 35 classrooms , administration block, library and 17 toilets. Construction of kitchen , computer centre fence , car park and 3 sports grounds. | Capital Assets | Nkangala | Emakhazeni | Emakhazeni | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 15630861.6603 |  | 0 | 5470801.5811 | 10160060.0792 | 0 | 156308.6166
137 | Mmutle Primary | P | CRDP. Renovation of 10 classrooms , and construction of administration block , library , kitchen , 12 ablution facilities , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 14191563.9343 |  | 0 | 0 | 1000505.2574 | 12481480.4802 | 709578.1967
138 | Siphendulwe Primary | Primary | Construction of administration block , kitchen , library , 2 sports grounds , car park and renovation of 24 classrooms. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 14533724.2062 |  | 0 | 0 | 0 | 0 | 0
139 | Dumeleni Secondary | Secondary | CRDP. Renovation of 16 classrooms , administration block , toilets , laboratory and construction of library , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 9583634.5686 |  | 0 | 0 | 0 | 0 | 675646.2371
140 | P Ndimande Secondary | Secondary | Renovation and refurbishment of existing classrooms , administration block , library , laboratory ablution facilities. | Capital Assets | Nkangala | Emalahleni 2 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 8056500 |  | 0 | 0 | 0 | 0 | 0
141 | Itireleng Primary | Primary | Refurbishment and renovation of 18 classrooms , 1 administration block , fence , 22 ablution facilities and construction of library , kitchen , car park and 2 sports grounds. | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 10801032.8496 |  | 0 | 0 | 761472.8159 | 10039560.0337 | 0
142 | Nancy Shiba | Primary | Refurbishment and renovation of 23 classrooms , 1 administration block , fence , 18 ablution facilities and construction of kitchen , 2 sports grounds and car park. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 10217923.281 |  | 0 | 0 | 0 | 0 | 720363.5913
143 | Zidli Primary | P | CRDP. Renovation of 10 classrooms , and construction of administration block , library , kitchen , 12 ablution facilities , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 30182178.9343 |  | 0 | 0 | 0 | 0 | 0
137 | Tsiki Naledi Secondary | Secondary | Refurbishment and renovation of 16 classrooms , 1 administration block , fence , sports facilities , 18 ablution facilities and construction of kitchen | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 18403934.2182 |  | 0 | 6441376.9764 | 11962557.2418 | 0 | 184039.3422
138 | Ukhwezi Primary | Primary | Refurbishment and renovation of 30 classrooms , 1 administration block , fence , 22 ablution facilities and construction of Grade R Centre , library , kitchen , car park and 2 sports grounds. | Capital Assets | Nkangala | Emakhazeni | Emakhazeni | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 14345025.4536 |  | 0 | 5020758.9088 | 9324266.5448 | 0 | 143450.2545
139 | Gugulethu Primary | Primary | CRDP. Renovation of 16 classrooms , administration block and construction of library , 12 toilets , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Tweefontein S | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 10109239.2967 |  | 0 | 0 | 0 | 0 | 0
139 | Njomane Primary | Primary | CRDP. Renovation of 16 classrooms , construction of administration block , toilets , Grade R Centre , library , 2 sports grounds , car park and fence. | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 17923827.9854 |  | 0 | 6273339.7949 | 11650488.1905 | 0 | 179238.2799
140 | Dikotelo Primary | Primary | CRDP. Renovation of 15 classroom, 1 administration block. Construction of kitchen, library , Computer Centre , 2 Sports Grounds , Car Park and Fence | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 11723241.2289 |  | 0 | 4103134.4301 | 7620106.7988 | 0 | 117232.4123
141 | Khonzimfundo C | C | Refurbishment of existing 24 classrooms, 1 administration block , 1 library , 1 kitchen , 1 school hall and 24 toilets. | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 7515300 |  | 0 | 0 | 0 | 0 | 529828.65
142 | Mandlethu Secondary | Secondary | Refurbishment of existing 16 classrooms, 1 administration block , 1 library , 1 laboratory 12 toilets. | Capital Assets | Nkangala | Tweefontein N | Thembisile Hani | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 5104500 |  | 0 | 0 | 0 | 0 | 359867.25
141 | Hoerskool Delmas | Secondary | Refurbishment of existing 17 classrooms, 1 administration block , 1 library , 1 kitchen , 2 computer centres , 4 laboratories , 1 school hall and existing toilets. | Capital Assets | Nkangala | Victor Khanye | Victor Khanye | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 8462400 |  | 0 | 2961840 | 5500560 | 0 | 84624
142 | Hoerskool Kanonkop | Secondary | Refurbishment of existing 17 classrooms, 1 administration block , 1 library , 1 kitchen , 2 computer centres , 4 laboratories , 1 school hall and existing toilets. | Capital Assets | Nkangala | Steve Tswete 3 | Steve Tshwete | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 6494400 |  | 0 | 2273040 | 4221360 | 0 | 64944
143 | Thulani Primary | Primary | Refurbishment of existing 16 classrooms , . Construction of administration block , Library , Computer Centre Grade R Centre kitchen , fence , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 18880369.1895 |  | 0 | 6608129.2163 | 12272239.9732 | 0 | 188803.6919
144 | Khamane Secondary | Secondary | Refurbishment of existing 24 classroom , administration block , Library , Computer Centre , fence , and construction of kitchen , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 10736928.3 |  | 0 | 3757924.905 | 6979003.395 | 0 | 107369.283
145 | Sibisi Primary | Primary | Renovation and refurbishment of 10 classrooms , construction of Grade R Centre , administration block , 10 ablution facilities, fence and computer centre. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | Refurbishment and Renovations | 2015-10-01 |  | 2015-10-01 | 2016-09-30 |  | 2016-09-30 |  | Rehabilitation, Renovation & Refurbishment |  | B |  | 14230936.28 |  | 0 | 4980827.698 | 9250108.582 | 0 | 142309.3628
146 | Mabande Secondary | Secondary | Refurbishment of existing 32 classroom , administration block , Library , Computer Centre , fence , technical centres and construction of kitchen , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 12606528.3 |  | 0 | 0 | 0 | 0 | 888760.2451
147 | Imemeza Secondary | Secondary | Refurbishment of existing 20 classroom , administration block, Library, fence, and construction of kitchen , Car Park and 2 Sports grounds. | Capital Assets | Nkangala | Emakhazeni | Emakhazeni | Refurbishment and Renovations |  |  | 0 |  |  | 0 |  | Rehabilitation, Renovation & Refurbishment |  | C |  | 9470028.3 |  | 0 | 0 | 0 | 0 | 667636.9951
148 | Ext 24 Primary School ( New) | p | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete | New Schools |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 43025355.8489 |  | 0 | 0 | 0 | 0 | 0
82 | New Klarinet Primary School (Mokgalithwa) | p | Phase 2 : Design and Provision of Basic Services and Fencing Phase 3: Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, electricity upgrade, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni | New Schools | 2015-05-29 | 9 | 2016-03-03 | NA | NA | NA | Education Infrastructure Grant (EIG) | New & Replacement Schools | Planning & design | A |  | 44500000 |  | 0 | 2091500 | 3660125 | 40317000 | DPWRT
97 | 11 Schools Sanitation Intervention Projects |  | Construction of Enviro-loo Toilets to 11 Schools in Gert Sibande District |  | Gert Sibande | All | All | Water & Sanitation |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | A |  | 10440486 |  |  | 0 | 0 | 0 | GS College
98 | 23 Schools Sanitation Intervention Projects |  | Construction of Enviro-loo Toilets to 23 Schools in Nkangala District |  | Nkangala | All | All | Water & Sanitation |  |  | 0 |  |  | 0 |  | Upgrades & Additions |  | A |  | 19886148 |  |  | 0 | 0 | 0 | MRTT
83 | Mountainview Primary ( New School) | p | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | New Schools |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 43025355.8489 |  | 0 | 0 | 0 | 0 | 0
84 | Kwaguqa New Primary | p | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | EMalahleni 3 | eMalahleni | New Schools |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 43025355.8489 |  | 0 | 0 | 0 | 0 | 3033287.5873
85 | De Beersprut ( New School) | p | Construction of 16 Classrooms, administration block, library, computer centre, 26 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | New Schools |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 33869639.1141 |  | 0 | 0 | 0 | 0 | 0
86 | New Primary (Sheldon ) | p | Construction of 16 Classrooms, administration block, library, computer centre, 26 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | New Schools |  |  | 0 |  |  | 0 |  | New & Replacement Schools |  | C |  | 33409004.1141 |  | 0 | 0 | 0 | 0 | 0
87 | Langa | S | Planning and Design: Construction of 16 Classrooms, administration block, laboratory, library, computer centre, 20 toilets, School Hall, Electricity, Water, Ramps and Rails, 2 Sports Grounds & Car Park. | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 32330008.1778 |  | 0 | 0 | 0 | 0 | 2279265.5765
88 | Shabalala | S | Planning and Design: Construction of 20 Classrooms, administration block, laboratory, library, computer centre, 30 toilets, School Hall, Elelctricity, Water, Ramps and Rails, 2 Sports Grounds & Car Park. | Capital Assets | Ehlanzeni | White Hazy | Mbombela | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 44982735.6848 |  | 0 | 0 | 3171282.8658 | 39562316.0348 | 2249136.7842
89 | Volksrust Primary School | P | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. (PHASE 2) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | New Schools |  |  | 0 |  |  | 0 | Equitable Share (ES) | New & Replacement Schools |  | C |  | 34159222.5817 | 0 | 0 | 0 | 0 | 0 | 0
90 | New Daggakraal Primary | P | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 37186252.5817 |  | 0 | 0 | 2621630.807 | 32705309.1456 | 1859312.6291
91 | New Primary(Hlanganani) | P | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 37186252.5817 |  | 0 | 0 | 2621630.807 | 32705309.1456 | 1859312.6291
92 | New Secondary School | S | Planning and Design: Construction of 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 44982735.6848 |  | 0 | 0 | 3171282.8658 | 39562316.0348 | 2249136.7842
93 | ThusiVille Primary | P | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, laboratory, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | Capital Assets | Gert Sibande | Ermelo1 | Msukaligwa | New Schools |  |  | 0 |  |  | 0 | Education Infrastructure Grant (EIG) | New & Replacement Schools |  | C |  | 38827912.2904 |  | 0 | 0 | 2737367.8165 | 34149148.8594 | 1941395.6145
83 | Early Childhood Development Institute (Phase 2) | N/A | Renovation and conversion of Mapulaneng College into ECDI (Phase 2) |  | Bohlabela | Maviljan | Bushbuckridge | Refurbishment and Renovations | 2015-04-01 | 3 | 2015-07-03 | 2015-04-14 | 12 | 2016-04-20 | Equitable Share (ES) | Rehabilitation, Renovation & Refurbishment | Construction | A |  | 41611804 |  |  | 34218388 | 4993416 | 0 | DPWRT / RIU
84 | Mbombela Circuit Office | N/A | Minor repairs to roof canopy at verandahs and remedial works to finishes and waterproofing/sealing of leaks to roof covering. | Capital Assets | Ehlanzeni | Mbombela | Mbombela | Storm Damaged Schools | 2015-03-29 | 2 | 2015-05-29 | 2015-06-22 | 4 | 2015-10-24 | Education Infrastructure Grant (EIG) | Rehabilitation, Renovation & Refurbishment | Planning / construction | A | Active - Not Contracted | 4000000 | 0 | 0 | 4000000 | 0 | 282000 | DPWRT
[20 empty] | 8493540893.3945 | 12000000 | 560778188.4537 | 1429761339.2022 | 1755537208.8275 | 1541044867.3182 | 1353102582.2781
Complied: | [5 empty] | Department of Education - PRFP - Deputy Director | [8 empty] | Ms NN Ntuli
85 | New Boarding School |  | Phase1: Bulk services, Fence, Admin, Grade R Centre, 24 Classrooms, 42 Toilets, Boarding Facilities, Kitchen and Dining hall. Phase2: Other facilities |  | Nkangala | TBC | TBC | New Schools | 2015-03-29 | 9 | 2016-01-02 | 2016-01-26 | 18 | 2017-08-06 | Equitable Share (ES) | New School | Planning & design | A |  | 300000000 |  |  | 160000000 | 110000000 | 30000000 | DPWRT
Recommended / Not Recommended: |  |  |  | Ms NN Ntuli
Recommended / Not Recommended: |  |  |  | Ms KR Morena
Approved / Not Approved: |  |  |  | Mrs MOC Mhlabane
Formulas:
Date: End = [Date: Start]+([Duration (Months)]*22)
Note on U52: sinugo: NO BUDGET.IDT TO CONFIRM
Note on V53: sinugo: begind scheduel. Non payment. Its a new school IDT
Note on V96: sinugo: ready for tender but reprioritize for 2014/15 need to chek 612, what for?
Note on V97: sinugo: planning
Note on M103: ukono: Commencement of fencing
Note on U103: sinugo: TO BE CONFIRMED
Note on M105: ukono: Commencement of fencing
Note on B226: Mpeps:
Note on M321: ukono: Construction to commencement
Note on M406: Phumelele C. Zulu: RIU FAST TRACK
Note on M407: Phumelele C. Zulu: RIU FAST TRACK
Note on M408: Phumelele C. Zulu: RIU FAST TRACK
Note on M409: Phumelele C. Zulu: RIU FAST TRACK
Note on M410: Phumelele C. Zulu: RIU FAST TRACK
Note on M411: Phumelele C. Zulu: RIU/TERM CONTRACTS FAST TRACK HOWEVER IF NORMAL TENDER APPLIES TIMEFRAMES MUST BE 3 MONTHS LONGER (51-56)
Note on M417: Phumelele C. Zulu: RUI FAST TRACK
Note on K439: Phumelele C. Zulu: Procurement only through the tender bulletin
Note on M443: Phumelele C. Zulu: RIU/TERM CONTRACTS FAST TRACK HOWEVER IF NORMAL TENDER APPLIES TIMEFRAMES MUST BE 3 MONTHS LONGER (72-81)
Note on K563: Phumelele C. Zulu: Minimum 6 months planning (land acqusition, eia, zoning, geotech, survey, etc) plus 3 months procurement/tendering process

## DoH
MPUMALANGA PROVINCIAL GOVERNMENT
Department of Public Works, Roads and Transport
Health Infrastructure Projects 2015/16 Financial Year
[6 empty] | Planning and Design |  |  | Construction | [6 empty] | 462737 | 0
Nr | Project Name and Description | District Municipality | Local Municipality | Infrastructure Type | Date: Start | Duration (Months) | Date: End | Date: Start | Duration (Months) | Date: End | Funding Source | Economic Classification | Planned Status for the 2015/16 Financial Year | Project Cost R'000 | BUDGET FOR 2014/2015 (R000) | Budget Allocation 2015/16 R'000 | MTEF 2016/17 R'000 | In/Out?
1 | Rob Ferreira hospital-Completion of works for statutory compliance | Ehlanzeni | Mbombela | Hospital | 2015-04-01 | 11 | 2016-03-07 | 2015-04-01 | 23.6129 | 2017-04-02 | Health Facilities Revitalisation Grant | Upgrade & Additions | Planning / Construction | 150000 |  | 5000 |  | In
2 | Themba hospital-Construction of a new maternity ward | Ehlanzeni | Mbombela | Ward | 2015-04-01 | 3 | 2015-07-03 | 2015-08-03 | 24 | 2017-11-02 | Health Facilities Revitalisation Grant | New and replacement | Construction | 214000 |  | 12400 |  | In
3 | Themba hospital -Construction of a new resource centre | Ehlanzeni | Mbombela | Resource centre | 2015-04-01 | 3 | 2015-07-03 | 2015-08-03 | 24 | 2017-03-30 | Health Facilities Revitalisation Grant | New and replacement | Construction | 98865 |  | 24554 |  | In
4 | Themba hospital-Renovation of X-rays and other wards | Ehlanzeni | Mbombela | Mechanical equipment | N/A | N/A | N/A | 2013-06-01 | 30.871 | 2016-01-14 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Construction | 77899 |  | 59606 |  | In
5 | Ermelo hospital-Construction of a new resource centre | Gert Sibande | Msukaligwa | Resource centre | 2015-04-01 | 3 | 2015-07-03 | 2015-08-03 | 24 | 2016-09-30 | Health Facilities Revitalisation Grant | New and replacement | Construction | 136147 |  | 26401 |  | In
6 | Ermelo hospital-Construction of a new stores,linen room and demolition of old hospital | Gert Sibande | Msukaligwa | Stores | N/A | N/A | N/A | 2013-03-19 | 23.9677 | 2015-04-01 | Health Facilities Revitalisation Grant | New and replacement | Construction | 28753 |  | 3500 |  | In
7 | Marite clinic-Renovations,rehabilitation and refurbishment | Ehlanzeni | Bushbuckridge | Clinic | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 3 | 2015-10-25 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 219470 |  | 2000 |  | In
8 | Mpakeni clinic-Renovations,rehabilitation and refurbishment | Ehlanzeni | Mbombela | Clinic | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 4 | 2015-11-25 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
9 | Ogies clinic-Renovations,rehabilitation and refuburshment | Nkangala | Emalahleni | Clinic | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 4 | 2015-11-25 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
10 | Orinocco clinic-Renovations,rehabilitation and rebursment |  |  | Clinic | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 4 | 2016-01-05 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
11 | Matibidi hospital-Rehabilitation,refurbushment and repairs as identified in the STP | Ehlanzeni | Thaba Chweu | Hospital | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 5000 |  | 5000 |  | In
12 | Extension 8 clinic-Repairs,rehabilitation and refurbishment of the clinic |  |  | Clinic | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 5000 |  | 2000 |  | In
13 | Polly clinic-Repairs,rehabilitation and refurbishment of the clinic |  |  | Clinic | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
14 | Lydenburg hospital-Planning for the upgrade of hospital | Ehlanzeni | Thaba Chweu | Hospital | N/A | N/A | N/A | N/A | N/A | N/A | Health Facilities Revitalisation Grant | Upgrade & Additions | Identified | 2000 |  | 0 |  | In
15 | Barberton hospital-Planning for the upgrade of hospital | Ehlanzeni | Umjindi | Hospital | N/A | N/A | N/A | N/A | N/A | N/A | Health Facilities Revitalisation Grant | Upgrade & Additions | Identified | 2000 |  | 0 |  | In
16 | Tintswalo hospital-Planning for the upgrade of hospital |  |  | Hospital | N/A | N/A | N/A | N/A | N/A | N/A | Health Facilities Revitalisation Grant | Upgrade & Additions | Identified | 2000 |  | 0 |  | In
17 | Kwa-Mhlanga hospital-Planning for the upgrade of hospital | Nkangala | Dr JS Moroka | Hospital | N/A | N/A | N/A | N/A | N/A | N/A | Health Facilities Revitalisation Grant | Upgrade & Additions | Identified | 2000 |  | 0 |  | In
18 | Gert Sibande district office-Repairs rehabilitation & refurbishment | Gert Sibande | Msukaligwa | Offices | N/A | N/A | N/A | N/A | N/A | N/A | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Construction |  |  |  |  | In
19 | Delmas Storm Damage repairs | Nkangala | Victor Khanye | Offices | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Construction | 5000 |  | 672 |  | In
20 | Anderson street Ehlanzeni district office repairs,rehabilitation & refurbishment | Ehlanzeni | Mbombela | Offices | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 6 | 2016-01-26 | Health Facilities Revitalisation Grant | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 672 |  | 5000 |  | In
21 | KaNyamazane CHC-Construction | Ehlanzeni | Mbombela | CHC | 2015-04-01 | 6 | 2015-08-05 | 2015-09-02 | 12 | 2016-09-08 | Equitable Share | New and replacement | Planning / Construction | 35000 |  | 5000 |  | In
22 | Bethal hospital-Site establishment,demolition of asbesto and major upgrade of hospital construction of rehabilitation and stepdown | Gert Sibande | Govan Mbeki | Hospital | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 60 | 2020-08-26 | Equitable Share | Upgrade & Additions | Construction | 679369 |  | 10000 |  | In
23 | Mammetlake hospital-Planning the upgrading of the hospital | Nkangala | Dr JS Moroka | Hospital | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 3 | 2015-10-25 | Equitable Share | Upgrade & Additions | Construction | 600000 |  | 35000 |  | In
24 | Maintenance of Ehlanzeni district facilities | Ehlanzeni | Mbombela | Offices | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Health Facilities Revitalisation Grant | Maintenance | Construction | 219470 |  | 17419 |  | In
25 | Maintenance of Gert Sibande district facilities | Gert Sibande |  | Offices | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Health Facilities Revitalisation Grant | Maintenance | Construction | 219470 |  | 18039 |  | In
26 | Maintenance of Nkangala District facilities | Nkangala |  | Offices | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Health Facilities Revitalisation Grant | Maintenance | Construction | 219470 |  | 27224 |  | In
27 | Mapulaneng hospital-Construction of a new hospital | Ehlanzeni | Bushbuckridge | Hospital | 2015-04-01 | 11 | 2016-03-07 | 2016-04-07 | 24 | 2018-04-21 | Equitable Share | New and replacement | Planning & design | 600000 |  | 5000 |  | In
28 | Sabie hospital-Site establishment demolition of asbestos and construction of wards | Ehlanzeni | Thaba Chweu | Hospital | TBC | TBC | TBC | 2015-01-09 | 11.8065 | 2016-01-10 | Equitable Share | Upgrade & Additions | Construction | 96602 |  | 0 |  | In
29 | Msukaligwa CHC-Construction of new CHC and accomodation units | Gert Sibande | Msukalegwa | CHC | 2014-11-01 | 8 | 2015-07-07 | 2015-07-24 | 12 | 2016-07-30 | Equitable Share | New and replacement | Planning / Construction | 5000 |  | 3000 |  | In
30 | Thandukhanya CHC-Construction of new CHC and accomodation units |  |  | CHC | 2014-11-01 | 8 | 2015-07-07 | 2015-07-24 | 12 | 2016-07-30 | Equitable Share | New and replacement | Planning / Construction | 5000 |  | 3000 |  | In
31 | Nhlazatshe 6 clinic-Construction of new clinic and accomodation units | Gert Sibande |  | Clinic | 2014-11-01 | 8 | 2015-07-07 | 2015-07-24 | 12 | 2016-07-30 | Equitable Share | New and replacement | Planning / Construction | 5000 |  | 3000 |  | In
32 | Vukuzakhe cllinic-Construction of new clinic and accomodation units |  |  | Clinic | 2014-11-01 | 8 | 2015-07-07 | 2015-07-24 | 12 | 2016-07-30 | Equitable Share | New and replacement | Planning / Construction | 5000 |  | 3000 |  | In
33 | Balfour Mini Hospital-Construction of mini hospital and accomodation units | Gert Sibande | Dipaleseng | Mini-hospital | 2014-11-01 | 8 | 2015-07-07 | 2015-07-24 | 18 | 2017-02-01 | Equitable Share | New and replacement | Planning / Construction | 150000 |  | 6502 |  | In
34 | Bethal hospital-Installation of new boiler | Gert Sibande | Govan Mbeki | Mechanical equipment | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | New and replacement | Construction | 9120 |  | 9120 |  | In
35 | Impungwe hospital-rehabilitation,refurbishment & repairs as identified | Nkangala |  | Hospital | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 5000 |  | 5000 |  | In
36 | Nelspruit CHC-Repairs,rehabilitation & refurbishment | Ehlanzeni | Mbombela | CHC | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
37 | Middelburg hospital-Installation of new boiler | Nkangala | Steve Tshwete | Mechanical equipment | N/A | N/A | N/A | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | New and replacement | Planning / Construction | 15000 |  | 15000 |  | In
38 | Khumbula clinic-Renovations,rehabilitation & refurbishment |  |  | Clinic | N/A | N/A | N/A | N/A | N/A | N/A | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
39 | Oakley clinic-Renovation,rehabilitation & refurbishment |  |  | Clinic | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 2000 |  | 2000 |  | In
40 | Rob Ferreira hospital-Repairs,rehabilitation &refurbishment | Ehlanzeni | Mbombela | Hospital | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 5219 |  | 5219 |  | In
41 | Sibange clinic-Repairs,rehabilitation & refurbishment | Ehlanzeni | Mbombela | Clinic | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 1781 |  | 1781 |  | In
42 | Nkangala district office-Repairs,rehabilitation & refurbishment | Nkangala |  | Offices | 2015-04-01 | 4 | 2015-08-03 | 2015-08-24 | 6 | 2016-02-26 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Planning / Construction | 5000 |  | 5000 |  | In
43 | Maintenance of Ehlanzeni district facilities | Ehlanzeni | Mbombela | Offices | N/A | N/A | N/A | 2015-04-01 | 11.8387 | 2016-04-02 | Equitable Share | Maintenance | Construction | 180500 |  | 22566 |  | In
44 | Maintenance of Gert Sibande district facilities | Gert Sibande |  | Offices | N/A | N/A | N/A | 2015-04-01 | 11.8387 | 2016-04-02 | Equitable Share | Maintenance | Construction | 120000 |  | 9414 |  | In
45 | Maintenance of Nkangala District facilities | Nkangala |  | Offices | N/A | N/A | N/A | 2015-04-01 | 11.8387 | 2016-04-02 | Equitable Share | Maintenance | Construction | 95000 |  | 26830 |  | In
46 | Machinery and equipment | [5 empty] | 0 | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | Maintenance | Construction | 120000 |  | 20225 |  | Out
47 | Medical equipment | [5 empty] | 0 | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | Maintenance | Construction | 100000 |  | 17000 |  | Out
48 | Maintenance of generators | [5 empty] | 0 | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | Maintenance | Construction | 155000 |  | 6000 |  | Out
49 | Master plans of all hospitals-drawing of building master plans of all hospitals in Mpumalanga | [5 empty] | 0 | 2015-04-01 | 11.8387 | 2016-04-02 | Equitable Share | N/A | Planning & design | 250000 |  | 15000 |  | Out
50 | Maintenance of sewerage (monthly maintenance) | [5 empty] | 0 | 2015-04-01 | 11.7742 | 2016-03-31 | Equitable Share | Maintenance | Construction | 140000 |  | 6000 |  | Out
51 | Expanded Public Works Programme-Gert Sibande | Gert Sibande |  | EPWP | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | EPWP | Construction | 755 |  | 755 |  | In
52 | Expanded Public Works Programme-Nkangala | Nkangala |  | EPWP | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | EPWP | Construction | 755 |  | 755 |  | In
53 | Expanded Public Works Programme-Ehlanzeni | Ehlanzeni |  | EPWP | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | EPWP | Construction | 755 |  | 755 |  | In
54 | M'africa CHC-Replacement of damaged ceilings and repairs to roofs including passages and consulting rooms | Ehlanzeni | Umjindi | CHC | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Construction | 468 |  | 0 |  | In
55 | Dludluma clinic-Replacement and repairs to ceilings including passages and emergency room |  |  | Clinic | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Construction | 402 |  | 0 |  | In
56 | Sikhwahlane clinic-Replacement and repairs to ceilings,leaking roofs |  |  | Clinic | N/A | N/A | N/A | 2015-04-01 | 11.7419 | 2016-03-30 | Equitable Share | Rehabilitation, Refurbishment, Repairs | Construction | 300 |  | 0 |  | In
-
| TOTAL: Health Infrastructure | [13 empty] | 0 | 462737 | 0
Formulas:
Date: End = [Date: Start]+([Duration (Months)]*31)
Note on G6: Phumelele C. Zulu: design plus procurement
Note on G7: Phumelele C. Zulu: minimum 3 months procurement process
Note on G8: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G10: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G12: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G13: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G14: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G15: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G16: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G17: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G18: Phumelele C. Zulu: minimum 3 months procurement proces
Note on I24: Phumelele C. Zulu: pls check start date on atiles project
Note on G25: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G26: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G27: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G28: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G32: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G41: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G44: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G45: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G46: Phumelele C. Zulu: minimum 3 months procurement proces
Note on G47: Phumelele C. Zulu: minimum 3 months procurement proces

## DSD
MPUMALANGA PROVINCIAL GOVERNMENT
Department of Public Works, Roads and Transport
Social Development Infrastructure Projects 2015/16 Financial Year
[7 empty] | Planning and Design |  |  | Construction | [7 empty] | 72354 | 76994 | 84421
Nr | Name of Project | Project Description | District Municipality | Local Municipality | Infrastrcture Type | Date: Start | Duration (Months) | Date: Finish | Date: Start | Duration (Months) | Date: Finish | Funding Source | Economic Classification | Planned Status for the 2015/16 Financial Year | Project Cost R'000 | Previous years expenditure R'000 | Budget Allocation 2014/15 | Budget Allocation 2015/16 R'000 | MTEF 2016/17 R'000 | MTEF 2017/18 R'000 | In/out?
1 | Marite Branch office | New block x 16 offices |  | Bushbuckridge | Office |  |  |  | 2013-04-01 |  | 2013-11-30 | Equitable share | New and replacement | Complete | 13000 | 5802 | 1000 | 0 | 0 | 0 | Out
1 | Nkangala Inpatient Youth treatment | 10 x Domartories | Nkangala | Emalahleni | Treatment Centre. | 2015-02-25 | 12 | 2016-03-03 | 2015-08-24 | 18 | 2017-03-04 | Equitable share | New and replacement | Planning / Construction | 17000 | 0 | 0 | 2490 | 1578 | 7932 | In
3 | Delmas Sub-district office | New block x 20 offices |  | Delmas | Office |  |  |  | 2012-02-01 | 1900-01-19 13:10 | 2013-10-30 | Equitable share | New and replacement | Complete | 13000 | 5495 | 0 | 0 | 0 | 0 | Out
2 | Ehlanzeni Secure care centre | 60 x Domartories | Ehlanzeni | Mbombela | Secure Care Centre | 2015-04-01 | 11 | 2016-03-07 | 2016-04-07 | 12 | 2017-04-14 | Equitable share | New and replacement | Planning & design | 100000 | 7617 | 4392 | 465 | 5000 | 0 | In
5 | Dagakraal Branch Office | New block x 10 offices |  | Pixley Ka Seme | Office |  |  |  | 2012-05-10 | 1900-01-20 06:12 | 2014-02-28 | Equitable share | New and replacement | Complete | 7791 | 3055 | 2000 | 0 | 0 | 0 | Out
3 | Warburton Branch office | New block x 16 offices | Gert Sibande | Msukaligwa | Office | 2015-04-01 | 3 | 2015-07-03 | 2015-07-24 | 12 | 2016-07-30 | Equitable share | New and replacement | Construction | 26154 | 0 | 1074 | 11000 | 10419 | 3661 | In
4 | Embalenhle branch office | New block x 20 offices | Gert Sibande | Govan Mbeki | Office | N/A | N/A | N/A | N/A | N/A | N/A | Equitable share | New and replacement | Identified | 19080 | 0 | 0 | 0 | 1000 | 18080 | In
5 | Glenmore Branch office | New block x 16 offices | Gert Sibande | Albert Luthuli | Office | N/A | N/A | N/A | 2014-10-06 | 12.4839 | 2015-10-28 | Equitable share | New and replacement | Construction | 24746 | 80 | 10581 | 14165 | 0 | 0 | In
6 | Jerusalem Branch office | New block x 20 offices | Ehlanzeni | Mbombela | Office | N/A | N/A | N/A | 2014-06-19 | 11.7742 | 2015-06-19 | Equitable share | New and replacement | Construction | 24238 | 740 | 9940 | 13298 | 1000 | 0 | In
10 | Lesiding Victim Support | Facility |  | Thembisile | Facility |  |  |  | 2016-04-01 | 1900-01-16 15:29 | 2017-09-30 | Equitable share | New and replacement | Identified | 24006 | 0 | 0 | 0 | 2354 |  | Out
7 | Hendrina Branch office | New block x 16 offices | Nkangala | Steve Tshwete | Office | N/A | N/A | N/A | 2014-02-19 | 15 | 2015-05-30 | Equitable share | New and replacement | Construction | 24879 | 4832 | 12000 | 9876 | 3003 | 0 | In
8 | Maviljane Branch office | New block x 20 offices | Bohlabela | Bushbuckridge | Office | 2016-04-01 | 11 | 2017-03-08 | 2017-08-01 | 12 | 2018-08-08 | Equitable share | New and replacement | Identified | 19089 | 0 | 0 | 0 | 1000 | 6803 | In
9 | Belfast Branch office | New block x 20 offices | Bohlabela | Bushbuckridge | Office | 2016-04-01 | 11 | 2017-03-08 | 2017-07-01 | 12 | 2018-07-08 | Equitable share | New and replacement | Identified | 19089 | 0 | 0 | 0 | 1000 | 7803 | In
10 | Thaba Chwewu Sub- District | New block x 40 offices | Ehlanzeni | Thaba Chweu | Office | 2016-04-01 | 11 | 2017-03-08 | TBC | TBC | TBC | Equitable share | New and replacement | Identified | 37000 | 0 | 0 | 0 | 1500 | 0 | In
11 | Chweni Branch office | New block x 10 offices | Ehlanzeni | Mbombela | Office | 2016-04-01 | 11 | 2017-03-08 | TBC | TBC | TBC | Equitable share | New and replacement | Identified | 12000 | 0 | 0 | 0 | 1500 | 0 | In
12 | Shiba Siding Branch office | New block x 10 offices | Ehlanzeni | Umjindi | Office | 2016-04-01 | 11 | 2017-03-08 | TBC | TBC | TBC | Equitable share | New and replacement | Identified | 12000 | 0 | 0 | 0 | 1500 | 0 | In
13 | Mpakeni Branch office | New block x 10 offices | Ehlanzeni | Mbombela | Office | 2016-04-01 | 11 | 2017-03-08 | 2017-04-01 | 12 | 2018-04-08 | Equitable share | New and replacement | Identified | 12000 | 0 | 0 | 0 | 1500 | 10500 | In
14 | Thulamahashe Children home (Phase 1) | Admin block, kitchen, laundry, gate house, fence and 6 accomodation unit | Bohlabela | Bushbuckridge | Centre | N/A | N/A | N/A | 2016-04-01 | 12 | 2017-04-08 | Equitable share | New and replacement | - | 62133 | 0 | 3000 | 0 | 23000 | 7000 | In
15 | Swartfontein Treatment Centre (Phase 1) | 5x Residential apartment and 1x admin block | Ehlanzeni | Mbombela | Centre | N/A | N/A | N/A | 2014-10-16 | 11.7742 | 2015-10-16 | Equitable share | New and replacement | Construction | 34136 | 0 | 15498 | 18638 | 13994 | 20142 | In
16 | Amsterdam Branch Office | New block x 12 offices | Gert Sibande | Msukaligwa | Office | N/A | N/A | N/A | 2013-10-03 | 11.7742 | 2014-10-03 | Equitable share | New and replacement | Retention | 20879 | 5902 | 12555 | 2422 | 0 | 0 | In
17 | Badplaas Victim Empowerment centre | Centre | Gert Sibande | Albert Luthuli | Centre | TBC | TBC | TBC | 2016-04-01 | 11.7097 | 2017-03-30 | Equitable share | New and replacement | Identified | 3500 | 0 | 0 | 0 | 10000 | 2500 | In
| Maintenance and repairs | [11 empty] | Maintenance and repairs |  |  |  | 4877 | 4578 | 5342 | 5324 | Out
22 | Maintenance projects | 0 |  | Shongwe Branch Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 14797 | 4102 | 489 | 0 | 0 | 0 | Out
23 | Maintenance projects | 0 |  | Tonga Branch Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 220 | 0 | 0 | 0 | Out
24 | Maintenance projects | 0 |  | Tsuvulani sub-District Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 520 | 0 | 0 | 0 | Out
25 | Maintenance projects | 0 |  | Thekwane District Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 350 | 0 | 0 | 0 | Out
26 | Maintenance projects | 0 |  | Louivile Woman support centre | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 210 | 0 | 0 | 0 | Out
27 | Maintenance projects | 0 |  | Gert Sibande District Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 350 | 0 | 0 | 0 | Out
28 | Maintenance projects | 0 |  | Steve Tswete Sub-District Office | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 914 | 0 | 0 | 0 | Out
29 | Maintenance projects | 0 |  | 30 X DSD signasge( 10 x per District | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 987 | 0 | 0 | 0 | Out
30 | Maintenance projects | 0 |  | Provincial Office Son-joy | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 351 | 0 | 0 | 0 | Out
31 | Maintenance projects | 0 |  | OHS issues | Offices |  |  |  | 01/04/2014 |  | 31/03/2015 | Equitable Share | Maintenance and repairs |  | 0 | 0 | 486 | 0 | 0 | 0 | Out
Total: Social Development Infrastructure | [14 empty] | 467923 | 19171 | 69040 | 72354 | 76994 | 84421
f
Formulas:
Date: Finish = [Date: Start]+([Duration (Months)]*31)
Duration (Months) = ([Date: Finish]-[Date: Start])/31
Note on H7: Phumelele C. Zulu: minimum 3 months procurement proces
Note on H9: Phumelele C. Zulu: minimum 3 months procurement proces
Note on H11: Phumelele C. Zulu: minimum 3 months procurement proces

## DCSR
MPUMALANGA PROVINCIAL GOVERNMENT
Department of Public Works, Roads and Transport
Culture, Sport and Recreation Infrastructure Projects 2015/16 Financial Year
[6 empty] | Planning and Design |  |  | Construction |  |  |  |  | 118862 | 118372 | 116556
Nr | Project Name | Project Description | District Municipality | Local Municipality | Date: Start | Duration (Months) | Date: Finish | Date: Start | Duration (Months) | Date: Finish | Funding Source | Economic Classification | Planned Status for the 2015/16 Financial Year | Budget Allocation 2015/16 (R'000) | MTEF 2016/17 R'000 | MTEF 2017/18 R'000 | Remarks
1 | Emthonjeni Library | Construction of new library | Nkangala | Emakhazeni | N/A | N/A | N/A | 2014-07-24 | 8.8387 | 2015-04-24 | Conditional Grant | New & replacement | Construction | 800 | 0 | 0 | Retention
2 | Glenmore / Dundonold Library | Construction of new library | Gert Sibande | Albert Luthuli | N/A | N/A | N/A | 2014-03-25 | 11.3548 | 2015-03-12 | Conditional Grant | New & replacement | Construction | 700 | 0 | 0 | Retention
3 | Emjindini Library | Construction of new library | Ehlanzeni | Umjindi | N/A | N/A | N/A | 2013-10-09 | 9.1935 | 2014-07-21 | Conditional Grant | New & replacement | Final account | 800 | 0 | 0 | Retention
4 | Thusivill dual purpose Library | Construction of new library | Gert Sibande | Msukaligwa | 2015-02-02 | 3 | 2015-05-06 | 2015-06-03 | 12 | 2016-06-09 | Conditional Grant | New & replacement | Construction | 800 | 0 | 0 | Retention
5 | Acornhoek Library | Construction of new library | Bohlabela | Bushbuckridge | 2015-04-02 | 3 | 2015-07-04 | 2015-07-24 | 12 | 2016-07-30 | Conditional Grant | New & replacement | Construction | 10500 | 800 | 0 | Implementation and retention
6 | Mgobodzi Library | Construction of new library | Ehlanzeni | Nkomazi | N/A | N/A | N/A | 2014-10-15 | 9.0968 | 2015-07-24 | Conditional Grant | New & replacement | Construction | 10472 | 800 | 0 | Implementation and retention
7 | Daggakraal Library | Construction of new library | Gert Sibande | Dr Pixley ka Isaka Seme | 2015-04-02 | 3 | 2015-07-04 | 2015-07-24 | 12 | 2016-07-30 | Conditional Grant | New & replacement | Construction | 10500 | 800 | 0 | Implementation and retention
8 | Kanyamazane Library | Construction of new library | Ehlanzeni | Mbombela | 2015-04-02 | 3 | 2015-07-04 | 2015-07-24 | 12 | 2016-07-30 | Conditional Grant | New & replacement | Construction | 10000 | 800 | 0 | Implementation and retention
9 | Boekenhout Library | Construction of new library | Nkangala | Thembisile Hani | 2015-06-10 | 9 | 2016-03-15 | 2016-06-01 | 12 | 2017-06-08 | Conditional Grant | New & replacement | Planning & design | 1100 | 11000 | 900 | Planning phase and implementation
10 | Balfour Library | Construction of new library | Gert Sibande | Dipaleseng | 2015-06-10 | 9 | 2016-03-15 | 2016-06-01 | 12 | 2017-06-08 | Conditional Grant | New & replacement | Planning & design | 1100 | 11000 | 900 | Planning phase, implementation and retention
11 | Mashishing Library | Construction of new library | Bohlabela | Thaba Chweu | 2015-06-10 | 9 | 2016-03-15 | 2016-06-01 | 12 | 2017-06-08 | Conditional Grant | New & replacement | Planning & design | 1100 | 11000 | 900 | Planning phase, implementation and retention
12 | Bushbuckridge dual purpose Library | Construction of new library | Bohlabela | Bushbuckridge | 2015-06-10 | 9 | 2016-03-15 | 2016-06-01 | 12 | 2017-06-08 | Conditional Grant | New & replacement | Planning & design | 1100 | 7000 | 500 | Planning phase, implementation and retention implementation
13 | Pieterskraal | - | Nkangala | Dr JS Moroka | 2016-04-01 | 9 | 2017-01-05 | 2017-04-01 | 12 | 2018-04-08 |  | New & replacement | Identified | 0 | 500 | 12000 | Planning phase and implementation
14 | Manzana | - | Gert Sibande | Chief Albert Luthuli | 2016-04-01 | 9 | 2017-01-05 | 2017-04-01 | 12 | 2018-04-08 |  | New & replacement | Identified | 0 | 500 | 12000 | Planning phase and implementation
15 | Kamhlushwa | - | Ehlanzeni | Nkomazi | 2016-04-01 | 9 | 2017-01-05 | 2017-04-01 | 12 | 2018-04-08 |  | New & replacement | Identified | 0 | 500 | 12000 | Planning phase and implementation
16 | Cultural Hub | Construction of a multi-cultural and recreational hub | Ehlanzeni | Mbombela | 2012-04-01 | 40 | 2015-08-24 | 2015-09-21 | 48 | 2019-10-18 | Equitable Share | New & replacement | Construction | 41080 | 43278 | 45442 | The project should resume construction of phase I and more budget will be needed
17 | High Altitude Training Centre | Construction of a modern and advance sporting and recreation center | Nkangala | Emakhazeni | 2011-04-01 | 54 | 2015-10-31 | 2016-04-01 | 48 | 2020-04-28 | Equitable Share | New & replacement | Identified | 25810 | 27194 | 28554 | The budget for the High Altitude Training Centre has been combined with Cultural Hub as per EXCO resolution of June 2014
18 | Heritage Infrastructure | Establishment of a Liberation struggle Museum/Interpretive center | Nkangala | Nkangala | TBC | TBC | TBC | TBC | TBC | TBC |  | New & replacement | Identified | 0 | 0 | 0 | The project will be at plenary stage to determine budgets that will be needed in the upcoming year 2016
19 | Establishment and unveiling of the Lowveld memorial | Establishment and unveiling of the Lowveld memorial | Ehlanzeni | Mbombela | TBC | TBC | TBC | TBC | TBC | TBC |  | New & replacement | Identified | 0 | 0 | 0 | The project will be at plenary stage to determine budgets that will be needed in the upcoming year 2017
20 | Sport Infrastructure | Sport and Recreation Combo Courts | Gert Sibande | Albert Luthuli x 2 | 2015-04-01 | 1.9355 | 2015-05-31 | 2015-08-14 | 6 | 2016-03-31 |  | New & replacement | Planning / construction | 3000 | 0 | 0 | 3 Sport combo courts will be established per annum
21 | Sport Infrastructure | Sport and Recreation Combo Courts | Bohlabela | Bushbuckridge x1 | 2015-04-01 | 1.9355 | 2015-05-31 |  | 6 |  |  | New & replacement
22 | Sport Infrastructure | Sport and Recreation Combo Courts | Nkangala | Dr JS Moroka x 2 | 2016-04-01 | 2 | 2016-06-02 | 2016-08-14 | 6 | 2017-03-31 |  | New & replacement | Identified | 0 | 3200 | 0
23 | Sport Infrastructure | Sport and Recreation Combo Courts | Gert Sibande | Dipaleseng x 2 | 2017-04-01 | 2 | 2017-06-02 | 2017-08-14 | 6 | 2018-02-28 |  | New & replacement | Identified | 0 | 0 | 3360
24 | Sport Infrastructure | Sport and Recreation Combo Courts | Nkangala | Thembisile Hani x 1 | 2017-04-01 | 2 | 2017-06-02 |  | 6 |  |  | New & replacement
| Total: Culture Sport and Recreation Infrastructure | [12 empty] | 118862 | 118372 | 116556
Formulas:
Date: Finish = [Date: Start]+([Duration (Months)]*31)
Note on O9: Phumelele C. Zulu: ALLOCATION INSUFFICIENT
Note on O13: Phumelele C. Zulu:PORTIN OF THE BUDGET TO BE TRANSFERED TO THUSIVILLE DUAL PURPOSE LIBRARY AS PLANNING IS AHEAD
Note on G21: Phumelele C. Zulu: REPLANNING AND TENDER
Note on O21: ukono: The original allocated amount of R 69 million was split between the Cultural hub and High Altitude Center

## DCSSL
MPUMALANGA PROVINCIAL GOVERNMENT
Department of Public Works, Roads and Transport
Community, Security, Safety and Liaison Infrastructure Projects 2015/16 Financial Year
[10 empty] | 114735 | 20000 | 0
Nr | Project Name | Project Description | District Municipality | Local Municipality | Date: Start | Date: Finish | Funding Source | Economic Classification | Planned Status for the 2015/16 Financial Year | Budget Allocation 2015/16 (R'000) | MTEF 2016/17 R'000 | MTEF 2017/18 R'000 | Remarks
1 | Mpumalanga Traffic College (Phase 2B) | Construction of perimeter concrete palisade fencing | Bohlabela | Bushbuckridge | 2014-07-31 | 2015-05-22 | Equitable Share | New & replacement | Construction | 0 | 0 | 0 | Retention
2 | Mpumalanga Traffic College (Phase 2C) | Construction of main building works | Bohlabela | Bushbuckridge | 2014-10-14 | 2016-10-14 | Equitable Share | New & replacement | Construction | 0 | 0 | 0 | Retention
3 | Mpumalanga Traffic College (Phase 2D) | Construction of civil works | Bohlabela | Bushbuckridge | 2015-01-14 | TBC | Equitable Share | New & replacement | Construction | 0 | 0 | 0 | Retention
| Total: Community, Security, Safety and Liaison Infrastructure | [8 empty] | 0 | 0 | 0