## IDIP SUMMARY
DEPARTMENT OF HEALTH INFRASTRUCTURE PROJECTS
INFRASTRUCTURE DELIVERY IMPROVEMENT PROGRAMME
REPORTING DATE: 31 DEC 2013
SUMMARY : HEALTH INFRASTRACTURE PROJECTS
No. | Programme | Number of Projects | Total Original Allocated Budget 2013/14 (R'000) | Total Revised Allocated Budget 2013/14 (R'000) | Total Expenditure Todate (DEC 2013) (R'000) | Total Projected Expenditure This Year 2013/14 (R'000) | Balance of Projected Expenditure this year 2013/14 R'000 | Percentage Exp Todate 2013/14 (%) | No of Jobs Created (CRDP & EPWP) | Total Project On-hold / Terminated | Planning 0% | 1-50% | 51-75% | 76-99% | 100% | Total Active Projects | Remarks
PLANNING AND DESIGN |  | 29 | 0 | 104474.0356 | 64879.4584 | 108326.4584 | 43447 | 62.1% | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 29
| HEALTH INFRASTRUCTURE GRANT PROJECTS - Planning and Design | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HOSPITAL REVITALISATION GRANT PROJECTS - Planning and Design | 7 | 0 | 14551.5634 | 16697.4584 | 18404.4584 | 1707 | 114.7% | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7
| Ehlanzeni | 4 | 0 | 12844.5634 | 16697.4584 | 16697.4584 | 0 | 130% | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
| Bohlabela | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Gert Sibande | 2 | 0 | 1707 | 0 | 1707 | 1707 | 0% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EQUITABLE SHARE FUNDED PROGRAMME - Planning and Design Projects | 14 | 0 | 81422 | 48182 | 81422 | 33240 | 59.18% | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14
| Ehlanzeni | 3 | 0 | 5200 | 825 | 5200 | 4375 | 15.87% | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| Bohlabela | 1 | 0 | 7500 | 0 | 7500 | 7500 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Gert Sibande | 5 | 0 | 25460 | 14305 | 25460 | 11155 | 56.19% | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
| Nkangala | 5 | 0 | 43262 | 33052 | 43262 | 10210 | 76.4% | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
| EPWP - Planning and Design Projects | 6 | 0 | 3000 | 0 | 3000 | 3000 | 0% | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 5 | 0 | 2500 | 0 | 2500 | 2500 | 0% | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
| Nkangala | 1 | 0 | 500 | 0 | 500 | 500 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| COLLEGE INFRASTRUCTURE - Planning and Design Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NHI PROGRAMME - Planning and Design Projects | 2 | 0 | 5500.4722 | 0 | 5500 | 5500 | 0% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 2 | 0 | 5500.4722 | 0 | 5500 | 5500 | 0% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMPLEMENTATION / CONSTRUCTION |  | 28 | 0 | 239341 | 141500.5076 | 237403.5076 | 95903 | 59.12% | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 28
| HEALTH INFRASTRUCTURE GRANT - Construction Projects | 3 | 0 | 23303 | 23735.7863 | 27705.7863 | 3970 | 101.9% | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 1 | 0 | 1000 | 30 | 1000 | 970 | 3% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Gert Sibande | 1 | 0 | 3000 | 0 | 3000 | 3000 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Nkangala | 1 | 0 | 19303 | 23705.7863 | 23705.7863 | 0 | 122.8% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| HOSPITAL REVITALISATION GRANT - Construction Projects | 7 | 0 | 159141 | 86115.8805 | 152800.8805 | 66685 | 54.11% | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7
| Ehlanzeni | 3 | 0 | 118205 | 62635.1937 | 111865.1937 | 49230 | 52.99% | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 4 | 0 | 40936 | 23480.6869 | 40935.6869 | 17455 | 57.36% | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EQUITABLE SHARE FUNDED PROGRAMME - Construction Projects | 8 | 0 | 45272 | 31584.8408 | 45271.8408 | 13687 | 69.77% | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8
| Ehlanzeni | 1 | 0 | 12796 | 12330 | 12796 | 466 | 96.36% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 3 | 0 | 3700 | 1894 | 3700 | 1806 | 51.19% | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| Nkangala | 4 | 0 | 28776 | 17360.8408 | 28775.8408 | 11415 | 60.33% | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
| EPWP - Construction Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COLLEGE INFRASTRUCTURE - Construction Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NHI GRANT - Construction Projects | 10 | 0 | 11625 | 64 | 11625 | 11561 | 0.5505% | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 10 | 0 | 11625 | 64 | 11625 | 11561 | 0.5505% | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RETENTION / FINAL ACCOUNT |  | 57 | 0 | 152627 | 116551.6106 | 150711.6106 | 34160 | 76.36% | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 57
| HEALTH INFRASTRUCTURE GRANT - Completed Projects | 6 | 0 | 14802 | 9450.5171 | 15528.5171 | 6078 | 63.85% | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
| Ehlanzeni | 2 | 0 | 4802 | 4802.4637 | 4802.4637 | 0 | 100% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Nkangala | 3 | 0 | 10000 | 4648.0534 | 10726.0534 | 6078 | 46.48% | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| HOSPITAL REVITALISATION GRANT - Completed Projects | 21 | 0 | 79320 | 59028.9137 | 79664.9137 | 20636 | 74.42% | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 21
| Ehlanzeni | 11 | 0 | 72383 | 54179.8819 | 72728.8819 | 18549 | 74.85% | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 11
| Bohlabela | 2 | 0 | 573 | 0 | 573 | 573 | 0% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Gert Sibande | 8 | 0 | 6364 | 4849.0318 | 6363.0318 | 1514 | 76.19% | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EQUITABLE SHARE FUNDED PROGRAMME - Completed Projects | 28 | 0 | 55424 | 45791.8937 | 52437.8937 | 6646 | 82.62% | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 28
| Ehlanzeni | 6 | 0 | 15156 | 11461.5919 | 12105.5919 | 644 | 75.62% | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
| Bohlabela | 2 | 0 | 2795 | 1517.2791 | 2795.2791 | 1278 | 54.29% | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Gert Sibande | 12 | 0 | 16057 | 16373.4532 | 16773.4532 | 400 | 102% | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12
| Nkangala | 8 | 0 | 21416 | 16439.5695 | 20763.5695 | 4324 | 76.76% | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8
| EPWP - Completed Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COLLEGE INFRASTRUCTURE - Completed Projects | 1 | 0 | 878 | 877.1427 | 877.1427 | 0 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Ehlanzeni | 1 | 0 | 878 | 877.1427 | 877.1427 | 0 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NHI GRANT - Completed Projects | 1 | 0 | 2203 | 1403.1434 | 2203.1434 | 800 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Ehlanzeni | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gert Sibande | 1 | 0 | 2203 | 1403.1434 | 2203.1434 | 800 | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Nkangala | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL: HEALTH INFRASTRACTURE PROJECTS |  | 114 | 427058.1818 | 496442.0356 | 322931.5766 | 496441.5766 | 173510 | 65.05% | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 114

## PLANNING
KEY
DEPARTMENT OF PUBLIC WORKS, ROADS AND TRANSPORT | [8 empty] | Behind |  |  | Ahead of |  |  | On Schedule
DEPARTMENT OF HEALTH INFRASTRUCTURE PROJECTS | [8 empty] | Schedule |  |  | Schedule
DoH - PROJECTS ON PLANNING STAGE
0
No | Project Description |  | Number of Projects | Service Providers | Scope of Works | Estimate / Awarded Contract Price (R'000) | Estimate / Approved Cons. Fees (R'000) | Total Project Cost (Estimate) (R'000) | Total Project Confirmed Budget CLIENT (R'000) | Total Exp (Previous Financial Years) | Allocated Budget 2013/14 (R'000) | Total Anticipated Exp 2013/14 (R'000) | Exp Todate 2013/14 (R'000) | Total Exp Todate (R'000) |  | Planning 2013/14 | [11 empty] | Start date | End Date | Site Handover Date | Comments | Remedial Action | Service Providers | Scope of Works
[16 empty] | Apr'13 | May'13 | Jun'13 | Jul'13 | Aug'13 | Sept'13 | Oct'13 | Nov'13 | Dec'13 | Jan'14 | Feb'14 | Mar'14
[16 empty] | 1st Qua |  |  | 2nd Qua |  |  | 3rd Qua |  |  | 4th Qua
HEALTH INFRASTRUCTURE GRANT PROJECTS - Planning and Design |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOSPITAL REVITALISATION GRANT PROJECTS - Planning and Design |  |  | 7 |  |  | 466577.1186 | 83983.8814 | 550561 | 0 | 27975 | 14551.5634 | 18404.4584 | 16697.4584 | 44672.4584
EHLANZENI DISTRICT |  |  | 4 |  |  | 334249.1525 | 60164.8475 | 394414 | 0 | 24790 | 12844.5634 | 16697.4584 | 16697.4584 | 41487.4584
1 | Project Description | Themba Hospital (New Maternity Ward) | Yes | Implementing Agent | Themba Hospital: Construction of new maternity ward | 181355.9322 | 32644.0678 | 214000 | 0 | 8793 | 10575 | 10633.8951 | 10633.8951 | 19426.8951 | Planned Exp (R'000) | 0 | 138.6145 | 0 | 0 | 0 | 2289.4374 | 2814.9564 | 5390.8868 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Design and Tender documentation are completed. 2. Project implementation defered to outer years to allow review process by MDoH on scope reduction due to budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-06-28 | 2013-06-30
| Local Municipality | Mbombela |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Afro Architech | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 138.6145 | 0 | 0 | 0 | 2289.4374 | 2814.9564 | 5390.8868 | 0
2 | Project Description | Themba Hospital (New Resource Centre) | Yes | Implementing Agent | Themba Hospital: Construction of new resource centre | 83783.8983 | 15081.1017 | 98865 | 0 | 13416 | 187.5648 | 187.5648 | 187.5648 | 13603.5648 | Planned Exp (R'000) | 0 | 187.5648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Design and Tender documentation are completed. 2. Project implementation defered to outer years to allow review process by MDoH on scope reduction due to budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-31 | 2013-06-02
| Local Municipality | Mbombela |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Afro Architech | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 187.5648 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Project Description | Themba Hospital (X-rays and Other wards) | Yes | Implementing Agent | Themba Hospital: Renovation of X-Rays and other wards | 69109.322 | 12439.678 | 81549 | 0 | 2581 | 2081.9986 | 2081.9986 | 2081.9986 | 4662.9986 | Planned Exp (R'000) | 0 | 2081.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning deferred to next Financial Year due to MDoH budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-31 | 2013-06-02
| Local Municipality | Mbombela |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Afro Architech | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 2081.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Project Description | Barberton Hospital (Hospital Upgrade) | Yes | Implementing Agent | Barberton Hospital: Uplanning for upgrade of Hospital | 0 | 0 | 0 | 0 | 0 | 0 | 3794 | 3794 | 3794 | Planned Exp (R'000) | 0 | 0 | 3104 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning deferred to next Financial Year due to MDoH budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Umjindi |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | TBA | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 3104 | 0 | 690 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Project Description | Lydenburg Hospital (Hospital Upgrade) | Yes | Implementing Agent | Lydenburg Hospital: Planning for upgrade of Hospital | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planned Exp (R'000) | [8 empty] | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning deferred to next Financial Year due to MDoH budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Thaba Chweu |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | TBA | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 2 |  |  | 132327.9661 | 23819.0339 | 156147 | 0 | 3185 | 1707 | 1707 | 0 | 3185
6 | Project Description | Ermelo Hospital (New resource Centre) | Yes | Implementing Agent | Ermelo Hospital: Construction of new resource centre | 115378.8136 | 20768.1864 | 136147 | 0 | 2795 | 1707 | 1707 | 0 | 2795 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Design and Tender documentation are completed. 2. Project implementation defered to outer years to allow review process by MDoH on scope reduction due to budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-06-28 | 2013-06-30
| Local Municipality | Msukaligwa |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | WOJ | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Project Description | Ermelo Hospital (Multi-purpose centre) | Yes | Implementing Agent | ERMELO HOSPITAL: Conversion of Psychiatric wards to multi-purpose centre | 16949.1525 | 3050.8475 | 20000 | 0 | 390 | 0 | 0 | 0 | 390 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning deferred to next Financial Year due to MDoH budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-10-28 | 2013-10-30
| Local Municipality | Msukaligwa |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [28 empty] | Principal Agent
| Budget Source | Hospital Revitalization Grant | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EQUITABLE SHARE FUNDED PROGRAMME - Planning and Design Projects |  |  | 14 |  |  | 1636323.183 | 294538.1729 | 1930861.3559 | 0 | 69967 | 81422 | 81422 | 48182 | 118149
EHLANZENI DISTRICT |  |  | 3 |  |  | 21916.4033 | 3944.9526 | 25861.3559 | 0 | 0 | 5200 | 5200 | 825 | 825
8 | Project Description | Naas Community Health Centre | Yes | Implementing Agent | NaasS CHC: Construction of new CHC and accommodation units | 21916.4033 | 3944.9526 | 25861.3559 | 0 | 0 | 3000 | 3000 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning deferred to next Financial Year due to MDoH budgetary constrain. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Nkomazi |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | ArchiConsult | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Project Description | Shongwe Hospital (Mortuary Upgrade) | Yes | Implementing Agent | SHONGWE HOSPITAL: Upgrading of Mortuary | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 825 | 825 | Planned Exp (R'000) | 0 | 0 | 0 | 330 | 0 | 200 | 0 | 0 | 295 | 0 | 705 | 670 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Assessment to renovate the mortuary to a maintenable state have been conducted 2. Finding report with cost estimate was submitted to MDoH for approval prior implementation. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2014-01-23 | 2014-01-25
| Local Municipality | Nkomazi |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | QS Consulting | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 330 | 0 | 200 | 0 | 0 | 295
10 | Project Description | Matibidi Hospital (Adminstration Block and Accommodation Units) | Yes | Implementing Agent | MATIBIDI HOSPITAL : Construction of admin block and 10x3 accommodation units.(Phase 1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project is on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2014-01-23 | 2014-01-25
| Local Municipality | Thaba Chweu |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Tarch Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 1 |  |  | 271186.4407 | 48813.5593 | 320000 | 0 | 19375 | 7500 | 7500 | 0 | 19375
11 | Project Description | Sabie Hospital (New Wards) | Yes | Implementing Agent | SABIE HOSPITAL : Removal of asbestos and construction of new wards. | 271186.4407 | 48813.5593 | 320000 | 0 | 19375 | 7500 | 7500 | 0 | 19375 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project is on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Thaba Chweu LM |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Phumlile Arch | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 5 |  |  | 817796.6102 | 147203.3898 | 965000 | 0 | 44262 | 25460 | 25460 | 14305 | 58567
12 | Project Description | Bethal Hospital (Hospital Upgrade) | Yes | Implementing Agent | BETHAL HOSPITAL : Removal of asbestos and major upgrade of hospital, construction of rehabilitation, step-down and oral health unit. | 512711.8644 | 92288.1356 | 605000 | 0 | 17415 | 10000 | 10000 | 0 | 17415 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 7500 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project is on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Govan Mbeki |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Tarch Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Project Description | Elsie Ballot (Renovations and Upgrading) | Yes | Implementing Agent | Elsie Ballot: Renovations and upgrading of Elsie Ballot Hospital | 0 | 0 | 0 | 0 | 9184 | 10000 | 10000 | 8845 | 18029 | Planned Exp (R'000) | 0 | 6036 | 0 | 0 | 0 | 0 | 0 | 2809 | 0 | 1155 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project is on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2014-01-23 | 2014-01-25
| Local Municipality | Pixley ka Seme |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Ekuthuleni | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 6036 | 0 | 0 | 0 | 0 | 0 | 2809 | 0
14 | Project Description | Bethal Hospital (Regional Laundry) | Yes | Implementing Agent | BETHAL HOSPITAL: Assessment and planning for construction of new Regional laundry. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project incorporated into the main Bethal project as regional laundry was allowed for in the hospital master plan. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2014-01-23 | 2014-01-25
| Local Municipality | Govan Mbeki |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Tarch Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Project Description | Carolina Hospital (Administration Block, OPD, Paediatric Ward and Threatre) | Yes | Implementing Agent | CAROLINA HOSPITAL : Construction of Admin Block, OPD, Paediatric ward and extension of theatre | 288135.5932 | 51864.4068 | 340000 | 0 | 13228 | 5460 | 5460 | 5460 | 18688 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 3328 | 0 | 2132 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project are on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-07-29 | 2013-07-31
| Local Municipality | Albert Luthuli |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Bharat Trikam Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 3328 | 0 | 2132
16 | Project Description | Siyathemba Community Health Centre | Yes | Implementing Agent | SIYATHEMBA CHC: Construction of new CHC and 2x2 accommodation units | 16949.1525 | 3050.8475 | 20000 | 0 | 4435 | 0 | 0 | 0 | 4435 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project to be implemented through National Department of Health. 2. And Professionnal service provider have been appointed. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2014-01-23 | 2014-01-25
| Local Municipality | Dipaliseng |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | TBA | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 5 |  |  | 525423.7288 | 94576.2712 | 620000 | 0 | 6330 | 43262 | 43262 | 33052 | 39382
17 | Project Description | Pankop Community Health Centre | Yes | Implementing Agent | PANKOP CHC: Construction of new CHC and 2x2 accommodation units | 16949.1525 | 3050.8475 | 20000 | 0 | 0 | 988 | 988 | 988 | 988 | Planned Exp (R'000) | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1, Planning delayed due to relocation of site. 2. Planning has been reprioritized to commence in the 2014-15 financial year. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Dr JS Moroka LM |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Motse LMI- Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0
18 | Project Description | Mmametlhake Hospital (Phase 1 and 2) | Yes | Implementing Agent | MMAMETLHAKE HOSPITAL: Upgrading of the hospital to 172 bed(Phase 1 & 2) | 508474.5763 | 91525.4237 | 600000 | 0 | 6330 | 39274 | 39274 | 30456 | 36786 | Planned Exp (R'000) | 0 | 3070 | 8118 | 0 | 1041 | 10584 | 5085 | 2558 | 0 | 1710 | 5398 | 1710 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Detail design and Tender documentation are ready. 2. Due to MDoH Budgetary constrain project are on hold until further notice. | 1. MDoH to avail budget for project to go ahead. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Dr JS Moroka |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Afro Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 3070 | 8118 | 0 | 1041 | 10584 | 5085 | 2558 | 0
19 | Project Description | Middleburg Hospital (Regional Laundry) | Yes | Implementing Agent | MIDDELBURG HOSPITAL: Assessment and planning for construction of new regional laundry. | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Planning and design in 2013-14 financial year, 2. Detail design underway | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | Steve Tshwete |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Tarch Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Description | Witbank TB Hospital (Mortuary) | Yes | Implementing Agent | WITBANK TB HOSPITAL: Planning of Construction of Mortuary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Project planning reprioritised to 2014-15 during budget re adjustment. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | eMalahleni |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | TBA | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Project Description | Impungwe Hospital (Bulk sewer, water and Electricity) | Yes | Implementing Agent | IMPUNGWE HOSPITAL: Bulk sewer, water and electricity | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1608 | 1608 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 1317 | 0 | 392 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Scoping, design and BoQ are completed. 2. Term contractor to be used. | 1. None. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | TBA | TBA
| Local Municipality | eMalahleni |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Slate Architech | [28 empty] | Principal Agent
| Budget Source | Equitable share | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 1317
EPWP - Planning and Design Projects |  |  | 6 |  |  | 3000 | 0 | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 5 |  |  | 2500 | 0 | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
22 | Project Description | Embhuleni Hospital | Yes | Implementing Agent | Embhuleni Hospital: paving at entrance | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | 2013-03-03 | 2013-05-03 | 2013-08-19
| Local Municipality | Albert Luthuli |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village | heer |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | me str | [12 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Project Description | Sibuyile Clinic | Yes | Implementing Agent | Sibuyile Clinic: Paving at entrance. | 350 | 0 | 350 | 0 | 0 | 350 | 350 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. | 12345 |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | 2013-03-03 | 2013-05-03 | 2013-08-19
| Local Municipality | Albert Luthuli |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village | here |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | I am | [12 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Project Description | Dundonald clinic | Yes | Implementing Agent | Dundonald clinic: paving at entrance. | 350 | 0 | 350 | 0 | 0 | 350 | 350 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-03 | 2013-08-19
| Local Municipality | Albert Luthuli |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Project Description | Botleng clinic | Yes | Implementing Agent | Botleng clinic: paving at entrance. | 300 | 0 | 300 | 0 | 0 | 300 | 300 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-03 | 2013-08-19
| Local Municipality | Victor Khanye |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Project Description | Emthonjeni clinic | Yes | Implementing Agent | Emthonjeni clinic: Plumbing and paving. | 1000 | 0 | 1000 | 0 | 0 | 1000 | 1000 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-03 | 2013-08-19
| Local Municipality | Msukaligwa |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 1 |  |  | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 | 0
27 | Project Description | Middleburg Hospital | Yes | Implementing Agent | Middleburg Hospital: Paving at entrance. | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. BAC approval have been finalised. 2. Contractor appointment have been submitted to supply chain. | 1. Site handover schedule for mid January 2014. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-03 | 2013-08-19
| Local Municipality | Steve Tshwete |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | DPWRT | [28 empty] | Principal Agent
| Budget Source | EPWP | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COLLEGE INFRASTRUCTURE - Planning and Design Projects |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NHI PROGRAMME - Planning and Design Projects |  |  | 2 |  |  | 1615.2326 | 290.7419 | 1905.9745 | 0 | 0 | 5500.4722 | 5500 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 2 |  |  | 1615.2326 | 290.7419 | 1905.9745 | 0 | 0 | 5500.4722 | 5500 | 0 | 0
28 | Project Description | Fernie 2 | Yes | Implementing Agent | Fernie 2 | 1615.2326 | 290.7419 | 1905.9745 | 0 | 0 | 1000.4722 | 1000 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. Quantity Surveyor to reassess BoQ to be aligned with the approved escalated term contract rate. | 1. DPWRT to assess report and cost implication to inform MDoH for approval on the new project cost. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2012-08-02 | 2012-08-04
| Local Municipality | Albert Luthuli |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [28 empty] | Principal Agent
| Budget Source | NHI-Holding Maintenance | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Project Description | Planning and Assessment of NHI phase 2 Project | Yes | Implementing Agent | Planning and Assessment of NHI phase 2 Project | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | Planning Start Date | Planning Completion Date | Contract Award Date | 1. MDoH to advise on the way forward. | 1. MDoH to finalise project list. | Implementing Agent
| Contract No. |  |  | DPWRT | [10 empty] | Planned Progress | [12 empty] | TBA | 2013-05-03 | 2013-08-19
| Local Municipality | TBA |  | Principal Agent | [28 empty] | Principal Agent
| Location / Village |  |  | TBA | [28 empty] | Principal Agent
| Budget Source | NHI-Holding Maintenance | [12 empty] | Actual Progress
| Responsible Senior Chief Project Manager | [13 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTALS |  | 29 | [6 empty] | 97942 | 104474.0356 | 108326.4584 | 64879.4584 | 162821.4584

## IMPLEMENTATION
KEY
0 | [8 empty] | Behind |  |  | Ahead of |  |  | On Schedule
DEPARTMENT OF HEALTH INFRASTRUCTURE PROJECTS | [8 empty] | Schedule |  |  | Schedule
DoH - PROJECTS ON CONSTRUCTION STAGE | [18 empty] | 0.001
0
No | Project Description |  | No. of Projects | Service Providers | Scope of Works | Estimate / Awarded Contract Price (R'000) | Estimate / Approved Consultants Fees (R'000) | Total Project Cost (Estimate) (R'000) | Total Exp (Previous Financial Years) | Allocated Budget 2013/14 (R'000) | Total Projected Exp 2013/14 (R'000) | Exp Todate 2013/14 (R'000) / (%) | Total Exp Todate (R'000) / (%) |  | Implementation 2013/14 | [11 empty] | Start date | Completion date | Final Account / Final Completion | Comments | Remedial Action / Acceleration Plan | Male |  |  | Female |  |  | Job Opp created | Man-Days Worked | [11 empty] | Total person days | FTE (1Full yr Eq)
[15 empty] | Apr'13 | May'13 | Jun'13 | Jul'13 | Aug'13 | Sept'13 | Oct'13 | Nov'13 | Dec'13 | Jan'14 | Feb'14 | Mar'14 | [5 empty] | Adult | Youth | Disabled | Adult | Youth | Disabled |  | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-12 | 2013-09-12 | 2013-10-12 | 2013-11-12 | 2013-12-12 | 2014-01-13 | 2014-02-13 | 2014-03-13
[15 empty] | 1st Qua |  |  | 2nd Qua |  |  | 3rd Qua |  |  | 4th Qua
HEALTH INFRASTRUCTURE GRANT - Construction Projects |  |  | 3 |  |  | 77134.9458 | 11544.2902 | 88679.236 | 44368 | 23303 | 27705.7863 | 23735.7863 | 68103.7863 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 1 |  |  | 17329 | 3119.22 | 20448.22 | 17203 | 1000 | 1000 | 30 | 17233 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Project Description | Mapulaneng Hospital (TB ward to Storage and Helip) | Yes | Implementing Agent | Mapulaneng Hospital: Renovations and additions to existing TB Ward. Construction of Storage and Helipad | 17329 | 3119.22 | 20448.22 | 17203 | 1000 | 1000 | 30 | 17233 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Contractor failling to complete the works. Recommendation to terminate await approval the Department Accounting Officer. 2. Revised completion date will be confirmed once termination and appointment of an alternative contractor is finalised. | 1. The Project manager to follow up on pending termination approval. 2. It was agreed during the December 2013 POMM meeting that the process of terminating underperforming contractors and the subsquent appointment of term contracotrs be closely monitored to avoid delays in project completion and service delivery. | [6 empty] | 0
| Contract No. | PW/613A/08/MP |  | DPWRT | [7 empty] | 3% | 84.28% | Planned Progress (%) | 100 | [11 empty] | 2009-01-23 | 2009-09-23 04:48 | 2009-12-22 04:48
| Local Municipality | Bushbuckridge |  | Principal Agent
| Location / Village |  |  | Ngonyama Okupanum Architects | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Infrastructure Grant |  | Contractor | [9 empty] | Actual Progress (%) | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 |  |  |  | 2009-01-23 | 2009-10-22 04:48 | 2009-12-22 04:48
| Responsible Senior Chief Project Manager | Joshua Lukhele |  | Riverqueen Trading 458 cc | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10
GERT SIBANDE DISTRICT |  |  | 1 |  |  | 10869.5051 | 1956.5109 | 12826.016 | 333 | 3000 | 3000 | 0 | 333 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Project Description | Standerton Hospital (New Structure) | Yes | Implementing Agent | STANDERTON HOSPITAL: Completion of new structure | 10869.5051 | 1956.5109 | 12826.016 | 333 | 3000 | 3000 | 0 | 333 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Cleaning of the ward, Internal Brickwork and internal plastering all complete | 1. None. | [6 empty] | 0
| Contract No. | PRE/033/13/MP |  | DPWRT | [7 empty] | 0% | 2.596% | Planned Progress (%) | [7 empty] | 5 | 10 | 25 | 40 | 55 | 2013-11-13 | 2014-05-14 09:36 | 2014-08-12 09:36
| Local Municipality | Lekwa |  | Principal Agent
| Location / Village |  |  | Chauke QS | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Infrastructure Grant |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 5 | 8 |  |  |  | 2013-11-13
| Responsible Senior Chief Project Manager | Albie Redman |  | Mpepere Construction and Project Managers | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 1 |  |  | 48936.4407 | 6468.5593 | 55405 | 26832 | 19303 | 23705.7863 | 23705.7863 | 50537.7863 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Project Description | KwaMhlanga Hospital (Phase 3C) | Yes | Implementing Agent | KwaMhlanga Hospital: Phase 3C Construction of new intensive care unit (ICU), and casuality. Renovations and additions to existing theatre block | 48936.4407 | 6468.5593 | 55405 | 26832 | 19303 | 23705.7863 | 23705.7863 | 50537.7863 | Planned Exp (R'000) | 0 | 3141.2506 | 3886.5949 | 0 | 868.5735 | 1579.9408 | 218.4264 | 0 | 14011 | 0 | 0 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Delays have been as a result fianlisation of septic theater requirements. | 1. Hospital requirement regarding septic theater have been resolved and handed over to the hospital. 2. Hospital exisiting theater facility will be vacated by the 13th January 2014 for work to start. 3. Planned completion date to be confirmed by the 14th of January 2014 site meeting. | [6 empty] | 0
| Contract No. | PW/612C/08/MP |  | DPWRT | [7 empty] | 122.8% | 91.22% | Planned Progress (%) | 85 | 85 | 85 | 85 | 85 | 88 | 88 | 93 | 100 |  |  |  | 2011-02-21 | 2013-12-08 | 2014-03-08
| Local Municipality | Thembisile Hani |  | Principal Agent
| Location / Village |  |  | Qualconsult Quantity Surveyors | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Infrastructure Grant |  | Contractor | [9 empty] | Actual Progress (%) | 85 | 85 | 85 | 85 | 85 | 88 | 88 | 93 | 93 |  |  |  | 2009-01-23 | To be Confirmed
| Responsible Senior Chief Project Manager | Joshua Lukhele |  | Moepi Construction | [9 empty] | Actual Exp (R'000) | 0 | 3141.2506 | 3886.5949 | 0 | 868.5735 | 1579.9408 | 218.4264 | 0 | 14011
HOSPITAL REVITALISATION GRANT - Construction Projects |  |  | 7 |  |  | 361480.1902 | 63614.5075 | 425094.6976 | 207259 | 159141 | 152800.8805 | 86115.8805 | 293374.8805 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 3 |  |  | 262029.3427 | 45713.3549 | 307742.6976 | 167638 | 118205 | 111865.1937 | 62635.1937 | 230273.1937 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Project Description | Themba hospital (CE workshop and general wards) | Yes | Implementing Agent | Themba hospital , construction of CE workshop and new general wards | 14093.2203 | 2536.7797 | 16630 | 39289 | 3137 | 3647 | 3647 | 42936 | Planned Exp (R'000) | 0 | 12 | 0 | 0 | 0 | 2320 | 698 | 0 | 617 | 0 | 0 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | None. | None. | [6 empty] | 0
| Contract No. | PWRT/1844B/11/MP |  | DPWRT | [7 empty] | 116.3% | 258.2% | Planned Progress (%) | 100 | [11 empty] | 2011-11-07 | 2012-05-07 09:36 | 2012-08-05 09:36
| Local Municipality | Mbombela |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 99 | 99 |  |  |  | 2011-11-07 | To be Confirmed
| Responsible Senior Chief Project Manager | Joshua Lukhele |  | Ndoma Mathlodi Trading & Enterprice | [9 empty] | Actual Exp (R'000) | 0 | 12 | 0 | 0 | 0 | 2320 | 698 | 0 | 617
5 | Project Description | Rob Ferreira Hospital (Phase 4D) | Yes | Implementing Agent | Rob Ferreira Hospital Phase 4D: Upgrading of Wards 9,10,11 and peadiatric ward, Rehabilitation centre | 54999.5932 | 8448 | 63447.5932 | 28024 | 24271 | 24271.4937 | 22376.4937 | 50400.4937 | Planned Exp (R'000) | 0 | 0 | 7017.675 | 0 | 15358.8187 | 0 | 0 | 0 | 0 | 0 | 1895 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | None | None | [6 empty] | 0
| Contract No. | To be Confirmed (IDT) |  | IDT | [7 empty] | 92.19% | 79.44% | Planned Progress (%) | [11 empty] | 100 | 2011-03-31 | 2014-03-24 | 2014-06-22
| Local Municipality | Mbombela |  | Principal Agent
| Location / Village |  |  | Cecillia Architects | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | 83 | 83 | 83 | 83 | 83 | 83 | 85 | 88 | 88 |  |  |  | 2011-03-31 | 2014-03-24
| Responsible Senior Chief Project Manager | Elias Mokwane |  | Ruwacon | [9 empty] | Actual Exp (R'000) | 0 | 0 | 7017.675 | 0 | 15358.8187 | 0 | 0 | 0 | 0
6 | Project Description | Rob Ferreira Hospital (Phase 4E Part 1) | Yes | Implementing Agent | Rob Ferreira Hospital Phase 4E: Part 1 : New Residence building with 150 units. | 192936.5292 | 34728.5752 | 227665.1044 | 100325 | 90797 | 83946.6999 | 36611.7 | 136936.7 | Planned Exp (R'000) | 0 | 4412.5186 | 20446.0698 | 0 | 198.5329 | 5838.6929 | 3611.8858 | 0 | 2104 | 12211 | 10088 | 25036 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Contractor is currently busy with the internal finishes. 2. Two contractors monthly certificates are still to be paid by the client department. | 1. Project Manager to follow up on contractor's outstanding payments. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 40.32% | 60.15% | Planned Progress (%) | 100 | [11 empty] | 2012-01-09 | 2013-02-13 | 2013-05-14
| Local Municipality | Mbombela LM |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | 55 | 57 | 60 | 64 | 67 | 67 | 73 | 78 | 78 |  |  |  | 2012-01-09 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Clear Choice Builders | [9 empty] | Actual Exp (R'000) | 0 | 4412.5186 | 20446.0698 | 0 | 198.5329 | 5838.6929 | 3611.8858 | 0 | 2104
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 4 |  |  | 99450.8475 | 17901.1525 | 117352 | 39621 | 40936 | 40935.6869 | 23480.6869 | 63101.6869 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Project Description | Ermelo Hospital (Orthopaedic Workshop) | Yes | Implementing Agent | Ermelo Hospital: Construction of a Orthopaedic workshop | 24089.8305 | 4336.1695 | 28426 | 449 | 8446 | 8446 | 1200 | 1649 | Planned Exp (R'000) | 0 | 0 | 0 | 256 | 0 | 0 | 944 | 0 | 0 | 2957 | 1449 | 2840 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Superstructure on the workshop and foundation of the administration block complete, 2. Progress behind schedule due to contractor having to rehabilitate site first. | 1. Contractor encouraged to fast track progress otherwise penalties will be imposed should the contractor fail to complete works within the approved contract period. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 14.21% | 5.801% | Planned Progress (%) |  | 5 | 15 | 25 | 35 | 45 | 55 | 65 | 75 | 80 | 85 | 90 | 2013-04-30 | 2014-04-29 19:12 | 2014-07-28 19:12
| Local Municipality | Msukaligwa |  | Principal Agent
| Location / Village |  |  | Mafulela Architect | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) |  |  | 2 | 2 | 2 | 2 | 6 | 27 | 30 |  |  |  | 2013-04-30 | To be Confirmed
| Responsible Senior Chief Project Manager | Tebogo Mabunda |  | Odirile investment and Construction JV | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 256 | 0 | 0 | 944 | 0 | 0
8 | Project Description | Ermelo Hospital (Surgical Wards) | Yes | Implementing Agent | Ermelo Hospital: Renovation of male & female surgical wards | 13728.8136 | 2471.1864 | 16200 | 1145 | 21714 | 21714 | 13459 | 14604 | Planned Exp (R'000) | 0 | 0 | 330 | 0 | 1048 | 562 | 5699 | 2971 | 2849 | 1888 | 1142 | 5225 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project ahead of schedule. | None. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 61.98% | 90.15% | Planned Progress (%) | 5 | 7 | 10 | 15 | 20 | 25 | 30 | 40 | 50 | 60 | 70 | 80 | 2013-04-23 | 2014-05-05 | 2014-08-03
| Local Municipality | Msukaligwa |  | Principal Agent
| Location / Village |  |  | Nxumalo and De Jager Architects | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | 3 | 5 | 10 | 15 | 45 | 45 | 55 | 70 | 70 |  |  |  | 2013-04-23 | 370482
| Responsible Senior Chief Project Manager | Tebogo Mabunda |  | Gaby Construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 330 | 0 | 1048 | 562 | 5699 | 2971 | 2849
9 | Project Description | Ermelo Hospital (New Stores, linen room) | Yes | Implementing Agent | Ermelo Hospital: Construction of new stores, linen room and demolition of old hospital | 28822.0339 | 5187.9661 | 34010 | 2536 | 9436 | 9436 | 7678 | 10214 | Planned Exp (R'000) | 0 | 0 | 2007 | 0 | 112 | 2709 | 1684 | 0 | 1166 | 452 | 484 | 822 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. The contractor busy with conctrete colomns 2. The contract period was extended to 24th June 2014 | 1. Progress being closely monitored. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 81.37% | 30.03% | Planned Progress (%) | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 50 | 60 | 70 | 80 | 2013-03-19 | 2014-03-18 | 2014-09-22
| Local Municipality | Msukaligwa |  | Principal Agent
| Location / Village |  |  | Nxumalo and De Jager Architects | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | 3 | 7 | 7 | 25 | 25 | 25 | 26 | 30 | 30 |  |  |  | 2013-03-19 | 2014-06-24
| Responsible Senior Chief Project Manager | Tebogo Mabunda |  | Atile Investment | [9 empty] | Actual Exp (R'000) | 0 | 0 | 2007 | 0 | 112 | 2709 | 1684 | 0 | 1166
10 | Project Description | Ermelo Hospital (OPD,Casualty, Theatres) | Yes | Implementing Agent | Ermelo Hospital : Renovation and Upgrading of OPD, Casualty and Theatres | 32810.1695 | 5905.8305 | 38716 | 35491 | 1340 | 1339.6869 | 1143.6869 | 36634.6869 | Planned Exp (R'000) | 0 | 286.2266 | 0 | 0 | 0 | 857.4603 | 0 | 0 | 0 | 196 | 0 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. General building works are complete while mechanical works are still outstanding. 2. Delay in completion of mechanical works are a result of prolonged finalisation of design and specifications by the project Engineer 3. Revised completion date to be confirmed after contractor revised programmed of works is assessed and approved by the Principal Agent. Matter to be dealt with during the next site meeting of February 2014. | 1. Project progress being monitored closely. 2. Project Manager will give the Engineer a warning letter failure to comply with terms of such letter may result in the Engineer's contract being terminated. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 85.35% | 94.62% | Planned Progress (%) | 100 | [11 empty] | 2008-07-16 | 2009-08-15 04:48 | 2009-11-13 04:48
| Local Municipality | Msukaligwa |  | Principal Agent
| Location / Village |  |  | Baloyi QS | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Hospital Revitalization Grant |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 90 |  |  |  |  | 2008-07-16 | To be Confirmed
| Responsible Senior Chief Project Manager | Tebogo Mabunda |  | Lumkani Construction | [9 empty] | Actual Exp (R'000) | 0 | 286.2266 | 0 | 0 | 0 | 857.4603 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EQUITABLE SHARE FUNDED PROGRAMME - Construction Projects |  |  | 8 |  |  | 124476.7797 | 23136.6203 | 147613.4 | 58684 | 45272 | 45271.8408 | 31584.8408 | 90268.8408 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 1 |  |  | 20338.9831 | 3661.0169 | 24000 | 870 | 12796 | 12796 | 12330 | 13200 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Project Description | Ntunda Community Health Centre (CHC) | Yes | Implementing Agent | Ntunda CHC: Construction of new CHC and 2x2 accommodation units. | 20338.9831 | 3661.0169 | 24000 | 870 | 12796 | 12796 | 12330 | 13200 | Planned Exp (R'000) | 0 | 505 | 756 | 1569 | 97 | 3583 | 1212 | 2844 | 1764 | 466 | 0 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Contractor is busy with finishes as well as external works 2. Contractor fast tracking activities on site to ensure progress is as planned. | 1. Contractor being closely monitored so that progress is as per the approved programme of works | [6 empty] | 0
| Contract No. | PWRT/1924/12/MP |  | DPWRT | [7 empty] | 96.36% | 55% | Planned Progress (%) | 5 | 10 | 15 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 85 | 90 | 2013-03-19 | 2014-04-24 06:43 | 2014-07-23 06:43
| Local Municipality | Nkomazi |  | Principal Agent
| Location / Village |  |  | ArchiConsult | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 3 | 9 | 17 | 30 | 30 | 57 | 60 | 65 | 66 |  |  |  | 2013-03-19 | To be Confirmed
| Responsible Senior Chief Project Manager | Anele Ngobe |  | Likhono Trading cc | [9 empty] | Actual Exp (R'000) | 0 | 505 | 756 | 1569 | 97 | 3583 | 1212 | 2844 | 1764
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 3 |  |  | 53393.5085 | 9610.8315 | 63004.34 | 35871 | 3700 | 3700 | 1894 | 37765 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Project Description | Piet Retief Hospital (Mortuary) | Yes | Implementing Agent | Piet Retief Mortuary | 20600 | 3708 | 24308 | 15062 | 1326 | 1326 | 326 | 15388 | Planned Exp (R'000) | 0 | 117 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 1000 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. General builders' works are 100% complete 2. Installation of fridges and air conditioning still outstanding. | 1. Penalties will be effected should the contractor fail to complete works within the approved contract period. 2. New target completion date is 24th January 2014 | [6 empty] | 0
| Contract No. | PWRT/1767/11/MP |  | DPWRT | [7 empty] | 24.59% | 63.3% | Planned Progress (%) | [12 empty] | 2012-01-21 | 2012-11-21 | 2013-02-19
| Local Municipality | Mkhondo |  | Principal Agent
| Location / Village |  |  | Talani Consulting (PTY) LTD | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 80 | 85 | 85 | 85 | 85 | 92 | 92 | 92 | 92 |  |  |  | 2011-11-21 | 30-May-13 24-Jan-14
| Responsible Senior Chief Project Manager |  |  | Riverqueen Trading 458 cc | [9 empty] | Actual Exp (R'000) | 0 | 117 | 0 | 0 | 0 | 0 | 209 | 0 | 0
13 | Project Description | Wakkerstroom Community Health Centre | Yes | Implementing Agent | Wakkerstroom CHC: Construction of new community Health Centre | 11213 | 2018.34 | 13231.34 | 5982 | 1100 | 1100 | 753 | 6735 | Planned Exp (R'000) | 0 | 114 | 339 | 0 | 0 | 219 | 0 | 0 | 81 | 0 | 347 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. The contractor motivated for the Department to charge penalties for delay in completion of works from his retention amount as opposed to monthly certificate amounts as this has been affecting the contractor cashflow and hence progress. Approval for such an arrangement has been granted. | 1. Revised project completion date is planned for end of January 2014 | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 68.45% | 50.9% | Planned Progress (%) | [12 empty] | 2009-01-23 | 2014-01-20 | 2014-04-20
| Local Municipality | Pixley ka Seme |  | Principal Agent
| Location / Village |  |  | Letchmiah Daya Mandindi QS | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 91 | 91 | 95 | 95 | 95 | 95 | 95 | 95 | 95 |  |  |  | 2009-01-23 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Bitline/Shuma Construction JV | [9 empty] | Actual Exp (R'000) | 0 | 114 | 339 | 0 | 0 | 219 | 0 | 0 | 81
14 | Project Description | Sinqobile Community Health Centre | Yes | Implementing Agent | Sinqobile CHC: construction of community health centre | 21580.5085 | 3884.4915 | 25465 | 14827 | 1274 | 1274 | 815 | 15642 | Planned Exp (R'000) | 0 | 93 | 0 | 0 | 0 | 0 | 722 | 0 | 0 | 0 | 459 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. The project is behind schedule as a result of the previously reported abandonment of site by the contractor. | 1. Contractor recovery plan with an anticipated completion date of end of April 2014 was received and is being analysed before approval is granted. | [6 empty] | 0
| Contract No. |  |  | IDT | [7 empty] | 63.97% | 61.43% | Planned Progress (%) | [12 empty] | 2012-02-06 | 2012-10-06 | 2013-01-04
| Local Municipality | Pixley ka Seme LM |  | Principal Agent
| Location / Village |  |  | MM Sakonda and Associates | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 49 | 49 |  |  |  | 2009-01-23 | 31-Aug-13 30-Apr-14
| Responsible Senior Chief Project Manager |  |  | Tsoshanang Trading Centre | [9 empty] | Actual Exp (R'000) | 0 | 93 | 0 | 0 | 0 | 0 | 722 | 0 | 0
NKANGALA DISTRICT |  |  | 4 |  |  | 50744.2881 | 9864.7719 | 60609.06 | 21943 | 28776 | 28775.8408 | 17360.8408 | 39303.8408 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Project Description | KwaMhlanga Hospital (Palisade Fencing) | Yes | Implementing Agent | KwaMhlanga Hospital: Erection of palisade fencing | 2940 | 1260 | 4200 | 0 | 4200 | 4200 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 2000 | 700 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Revised design specifications and positioning of boundary wall as per hospital master plan was measured and costed. 2. A submition was made to MDoH for approval. | None. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-09-25 | 2014-02-23 | 2014-05-24
| Local Municipality | Thembisile Hani LM |  | Principal Agent
| Location / Village |  |  | DPWRT | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 15 | 15 |  |  |  | 2013-09-25 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Ascul Construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Project Description | Wonderfontein Clinic (Accommodation Units) | Yes | Implementing Agent | Wonderfontein Clinic: Construction of 2x2 accommodation units | 1906.7797 | 343.2203 | 2250 | 0 | 1212 | 1212 | 0 | 0 | Planned Exp (R'000) | [8 empty] | 0 | 500 | 312 | 400 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. None. | 1. None. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [6 empty] | 5 | 15 | 30 | 45 | 60 | 75 | 2013-10-07 | 2014-04-21 14:24 | 2014-07-20 14:24
| Local Municipality | eMakhazeni |  | Principal Agent
| Location / Village |  |  | Phiri Group Architects | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 7 | 7 |  |  |  | 2013-10-07
| Responsible Senior Chief Project Manager |  |  | Bitupquip Construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Project Description | Mmamethlake Hospital (Bulk Services updrage) | Yes | Implementing Agent | Mmamethlake Hospital: Upgrading of bulk civil engineering services | 23417 | 4215.06 | 27632.06 | 0 | 21288 | 21288 | 16150 | 16150 | Planned Exp (R'000) | 0 | 0 | 1736 | 1972 | 3259 | 1715 | 2021 | 2769 | 2678 | 1230 | 1954 | 1954 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Mechanical equipment procured by the contracttor for the project is still to be delivered to site. 2. Initial borehole was estimated to be 80 to 100 m deep which has varied to about 300 meter deep upon site drilling, | 1. Principal Agent to advise timeously on the time and cost implication of change in borehole depth to be drilled. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 75.86% | 58.45% | Planned Progress (%) | [12 empty] | 2013-03-20 | 2013-09-18 | 2014-05-01
| Local Municipality | Dr JS Moroka |  | Principal Agent
| Location / Village |  |  | Afrisa Consultant (Pty) Ltd | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 7 | 15 | 45 | 55 | 58 | 58 | 68 | 73 | 73 |  |  |  | 2013-03-20 | 2014-01-31
| Responsible Senior Chief Project Manager |  |  | Lebeka Construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 1736 | 1972 | 3259 | 1715 | 2021 | 2769 | 2678
18 | Project Description | Tweefontein Community Health Centre | Yes | Implementing Agent | Tweefontein CHC: construction of community health centre | 22480.5085 | 4046.4915 | 26527 | 21943 | 2076 | 2075.8408 | 1210.8408 | 23153.8408 | Planned Exp (R'000) | 0 | 530.8772 | 605.6841 | 0 | 74.2796 | 0 | 0 | 0 | 0 | 865 | 0 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. MDoH has not taken possession of the building due to omitted items which compromise the functionality of the facility. 2. VO submitted to MDoH is still to be appoved. | 1. None | [6 empty] | 0
| Contract No. |  |  | IDT | [7 empty] | 58.33% | 87.28% | Planned Progress (%) | [12 empty] | 2012-02-06 | 2012-10-06 04:48 | 2013-01-04 04:48
| Local Municipality | Thembisile Hani |  | Principal Agent
| Location / Village |  |  | Takgalang Consulting | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | Equitable share |  | Contractor | [9 empty] | Actual Progress (%) | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 |  |  |  | 2012-02-06 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Ubuhlebethu Business Enterprise | [9 empty] | Actual Exp (R'000) | 0 | 530.8772 | 605.6841 | 0 | 74.2796 | 0 | 0 | 0 | 0
EPWP - Construction Projects |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COLLEGE INFRASTRUCTURE - Construction Projects |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NHI GRANT - Construction Projects |  |  | 10 |  |  | 13447.3082 | 1790.5155 | 15237.8236 | 0 | 11625 | 11625 | 64 | 64 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHLANZENI DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOHLABELA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GERT SIBANDE DISTRICT |  |  | 10 |  |  | 13447.3082 | 1790.5155 | 15237.8236 | 0 | 11625 | 11625 | 64 | 64 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Project Description | Embhuleni Hospital (Maintenance Works) | Yes | Implementing Agent | Embhuleni Hospital: Holding maintenance | 3500 | 0 | 3500 | 0 | 3500 | 3500 | 15 | 15 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 3485 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project on schedule and anticipated completion date 05 December 2013. | 1. None. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0.4286% | 0.4286% | Planned Progress (%) | [12 empty] | 2013-07-15 | 2013-12-14 | 2014-03-14
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Nkonki & Associates | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) |  |  | 9 | 10 | 40 | 60 | 75 | 90 | 90 |  |  |  | 2013-07-15 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Vatsakile | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0
20 | Project Description | Vlakplaas Clinic (Maintenance Works) | Yes | Implementing Agent | Vlakplaas Clinic: Holding maintenance in line with NHI Term Of Reference | 974.52 | 175.4136 | 1149.9336 | 0 | 844 | 844 | 0 | 0 | Planned Exp (R'000) | [8 empty] | 0 | 347 | 347 | 150 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project on schedule. Anticipated completion date 10 March 2014. | 1. None. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-08 | 2014-03-10 14:24 | 2014-06-07 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 25% |  |  |  |  | 2013-11-08 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Moyoyo Construction and Projects | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Project Description | Nhlazatshe Ext 4 Clinic (Maintenance Works) | Yes | Implementing Agent | Nhlazatshe Clinic Ext 4: Holding maintenance in line with NHI Term Of Reference | 942.914 | 169.7245 | 1112.6385 | 0 | 757 | 757 | 49 | 49 | Planned Exp (R'000) | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. Quality of work is satisfactory. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 6.473% | 4.404% | Planned Progress (%) | [12 empty] | 2013-11-08 | 2014-03-09 14:24 | 2014-06-07 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 10 |  |  |  |  | 2013-11-08 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Daphm Trading/ Xigombe Trading JV | [9 empty] | Actual Exp (R'000) | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Project Description | Tjakastad Clinic (Maintenance Works) | Yes | Implementing Agent | Tjakastad Clinic: Holding maintenance in line with NHI Term Of Reference | 947.45 | 170.541 | 1117.991 | 0 | 760 | 760 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. 2. Poor workmanship, project scope not well understood by the contractor. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-08 | 2014-03-09 14:24 | 2014-06-07 14:24
| Local Municipality | Albert Luthuli LM |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 2 |  |  |  |  | 2013-11-08 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Somthwalo JV Vusana construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Project Description | Betty's Goed Clinic (Maintenance Works) | Yes | Implementing Agent | Betty's Goed Clinic : Holding maintenance in line with NHI Term Of Reference | 1194.3663 | 214.9859 | 1409.3523 | 0 | 973 | 973 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 973 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. 2. Poor workmanship, project scope not well understood by the contractor. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-07 | 2014-03-08 14:24 | 2014-06-06 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 5 |  |  |  |  | 2013-11-07 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Ntiatia PA Construction | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Project Description | Hartbeeskop Clinic (Maintenance Works) | Yes | Implementing Agent | Hartbeeskop Clinic : Holding maintenance in line with NHI Term Of Reference | 963.96 | 173.5128 | 1137.4728 | 0 | 775 | 775 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. Quality of work is satisfactory. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-08 | 2014-03-09 14:24 | 2014-06-07 14:24
| Local Municipality | Albert Luthuli LM |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 2 |  |  |  |  | 2013-11-08 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Malibongwe Trading cc | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Project Description | Dundonald Clinic (Maintenance Works) | Yes | Implementing Agent | Dundonald clinic : Holding maintenance in line with NHI Term Of Reference | 937.926 | 168.8267 | 1106.7527 | 0 | 752 | 752 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. 2. Poor workmanship, project scope not well understood by the contractor. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-08 | 2014-03-09 14:24 | 2014-06-07 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 2 |  |  |  |  | 2013-11-08 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Leswinene Trading Enterprise | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Project Description | Glenmore Clinic (Maintenance Works) | Yes | Implementing Agent | Glenmore Clinic : Holding maintenance in line with NHI Term Of Reference | 1284.5134 | 231.2124 | 1515.7258 | 0 | 1050 | 1050 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project on schedule. Anticipated completion date 10 March 2014. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-07 | 2014-03-10 14:24 | 2014-06-06 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 25 |  |  |  |  | 2013-11-07 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Mayor Building and General | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Project Description | Fernie1 Clinic (Maintenance Works) | Yes | Implementing Agent | Fernie1 Clinic : Holding maintenance in line with NHI Term Of Reference | 1440.474 | 259.2853 | 1699.7594 | 0 | 1184 | 1184 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. Quality of work is satisfactory. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-07 | 2014-03-08 14:24 | 2014-06-06 14:24
| Local Municipality | Albert Luthuli LM |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 4 |  |  |  |  | 2013-11-07 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Crystal Sparkle Trading 101 | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Project Description | Diepdale Clinic (Maintenance Works) | Yes | Implementing Agent | Diepdale Clinic : Holding maintenance in line with NHI Term Of Reference | 1261.1844 | 227.0132 | 1488.1976 | 0 | 1030 | 1030 | 0 | 0 | Planned Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | Planned Start Date | Planned Completion Date | Final Completion Date (Planned) | 1. Project behind schedule. 2. Poor workmanship, project scope not well understood by the contractor. | 1. Principal Agent to monitor project Closely. | [6 empty] | 0
| Contract No. |  |  | DPWRT | [7 empty] | 0% | 0% | Planned Progress (%) | [12 empty] | 2013-11-07 | 2014-03-08 14:24 | 2014-06-06 14:24
| Local Municipality | Albert Luthuli |  | Principal Agent
| Location / Village |  |  | Consultium Project Planning & Management cc | [22 empty] | Actual Start Date | Revised Completion Date | Final Completion Date
| Budget Source | NHI-Holding Maintenance |  | Contractor | [9 empty] | Actual Progress (%) | [7 empty] | 2 |  |  |  |  | 2013-11-07 | To be Confirmed
| Responsible Senior Chief Project Manager |  |  | Rospa Trading 49CC JV Msuthu properties | [9 empty] | Actual Exp (R'000) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NKANGALA DISTRICT |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS: IMPLEMENTATION |  |  | 28 | [6 empty] | 239341 | 237403.5076 | 141500.5076 | [25 empty] | 0
Formulas:
Final Account / Final Completion = [Completion date]+90

## RETENTION
DEPARTMENT OF PUBLIC WORKS, ROADS AND TRANSPORT
DEPARTMENT OF HEALTH INFRASTRUCTURE PROJECTS
DoH - PROJECTS ON RETENTION STAGE
REPORTING DATE: 31 DEC 2013
No | Description | Contract Number | No. of Projects | Project Scope Description | Impl Agent | Circuit | Local Municipality | District Municipality | Physical Progress | Start Date | Duration (Months) | End Date | Award/ Estimated Cost | Consultants Fees | Total Project Cost | Exp (Prev Years) | Allocated Budget 2013/14/ (Table b.5) | Additional Budget 2013/14 R'000 | Revised Allocated Budget 2013/14 (R'000) | Apr 13 R'000 Actual | May 13 R'000 Actual | Jun 13 R'000 Actual | Jul 13 R'000 Actual | Aug 13 R'000 Actual | Sep 13 R'000 Actual | Oct 13 R'000 Actual | Nov 13 R'000 Actual | Dec 13 R'000 Actual | Jan 14 R'000 Projection | Feb 14 R'000 Projection | Mar 14 R'000 Projection | TOTAL ACTUAL EXP (Dec2013) | TOTAL PROJCTD EXP (Jan-Mar) | TOTAL INVOICES AT HAND 12.11.13 R'000 | TOTAL ANTICIPATED EXP 2013/14 | Remarks
| HEALTH INFRASTRUCTURE GRANT - Completed Projects |  | 6 | [9 empty] | 0 | 0 | 264946 | 236171 | 13000 | 1802 | 14802 | 0 | 2837.0592 | 5197.7506 | 0 | 689.7073 | 0 | 0 | 0 | 726 | 0 | 4771 | 1307 | 9450.5171 | 6078 | 0 | 15528.5171
| Retention/Final Account |  | 6 | [9 empty] | 0 | 0 | 264946 | 236171 | 13000 | 1802 | 14802 | 0 | 2837.0592 | 5197.7506 | 0 | 689.7073 | 0 | 0 | 0 | 726 | 0 | 4771 | 1307 | 9450.5171 | 6078 | 0 | 15528.5171
| Ehlanzeni District |  | 2 | [9 empty] | 0 | 0 | 113175 | 106737 | 2000 | 2802 | 4802 | 0 | 1009.2482 | 3103.5082 | 0 | 689.7073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4802.4637 | 0 | 0 | 4802.4637
1 | Barberton Hospital |  | 1 | Upgrade OPD, Casualty, Admission area, ablution facilities, repairing roof, disable facilities at entrance, and painting of whole hospital. | DPWRT |  | Umjindi | Ehlanzeni | [6 empty] | 83931 | 80138 | 1000 | 2793 | 3793 | 0 | 0 | 3103.5082 | 0 | 689.7073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3793.2155 | 0 | 0 | 3793.2155
2 | Bongani Hospital |  | 1 | Construction of MDR-TB ward | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 29244 | 26599 | 1000 | 9 | 1009 | 0 | 1009.2482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009.2482 | 0 | 0 | 1009.2482 | Project Closed
| Bohlabela District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0
| Gert Sibande District |  | 1 | [9 empty] | 0 | 0 | 21928 | 20428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Evander Hospital |  | 1 | Upgrading and construction of OPD, casualty, dispensary, admin block and threatre | DPWRT |  | Govan Mbeki | Gert Sibande | [6 empty] | 21928 | 20428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Closed
| Nkangala District |  | 3 | [9 empty] | 0 | 0 | 129843 | 109006 | 11000 | -1000 | 10000 | 0 | 1827.811 | 2094.2424 | 0 | 0 | 0 | 0 | 0 | 726 | 0 | 4771 | 1307 | 4648.0534 | 6078 | 0 | 10726.0534
4 | Witbank Hospital |  | 1 | Demolitions of existing building and construction of Neo-natal and kangaroo unit and renovation of old hospital roof. | DPWRT |  | Emalahleni | Nkangala | [6 empty] | 71434 | 52761 | 10000 | 0 | 10000 | 0 | 1827.811 | 2094.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4771 | 1307 | 3922.0534 | 6078 | 0 | 10000.0534
5 | Middelburg Hospital |  | 1 | Renovation of Existing roofs & two wards. Upgrading of Helipad, Theatres, Pharmacy and Casualty. Construction of ICU/High care | DPWRT |  | Steve Tshwete | Nkangala | [6 empty] | 58409 | 56245 | 1000 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 0 | 0 | 0 | 726 | 0 | 0 | 726
6 | Middelburg Pharmacital depot |  | 1 |  | DPWRT |  | Steve Tshwete | Nkangala | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Account Approved, Fees issue still to be resolved
[15 empty] | 0 | [16 empty] | 0 | 0 | 0 | 0
| HOSPITAL REVITALISATION GRANT - Completed Projects |  | 21 | [9 empty] | 141797 | 31195.34 | 586025.34 | 564609 | 69172 | 10148 | 79320 | 0 | 5093.0099 | 11987.1973 | 8856.7695 | 20509.3901 | 4388.5662 | 7320.1577 | 81.8229 | 792 | 8439 | 7833 | 4283 | 59028.9137 | 20555 | 81 | 79664.9137
| Retention/Final Account |  | 21 | [9 empty] | 141797 | 31195.34 | 586025.34 | 564609 | 69172 | 10148 | 79320 | 0 | 5093.0099 | 11987.1973 | 8856.7695 | 20509.3901 | 4388.5662 | 7320.1577 | 81.8229 | 792 | 8439 | 7833 | 4283 | 59028.9137 | 20555 | 81 | 79664.9137
| Ehlanzeni District |  | 11 | [9 empty] | 141797 | 31195.34 | 477359.34 | 473760 | 62020 | 10363 | 72383 | 0 | 4523.5471 | 10619.332 | 6364.8026 | 20509.3901 | 3968.8294 | 7320.1577 | 81.8229 | 792 | 8439 | 5827 | 4283 | 54179.8819 | 18549 | 0 | 72728.8819
7 | Rob Ferreira Hospital 4A |  | 1 | Major Renovations of existing units, creche,laboratory,theatre,x-ray,ICU,Specialist OPD,wards 2,3,4 & 8, cafeteria ,construction of medical waste and external parking | IDT |  | Mbombela | Ehlanzeni |  |  |  |  | 141797 | 31195.34 | 172992.34 | 160908 | 16518 | 10971 | 27489 | 0 | 0 | 0 | 0 | 19941.8575 | 0 | 3496.506 | 0 | 0 | 0 | 1150 | 2901 | 23438.3635 | 4051 | 0 | 27489.3635
8 | Themba Hospital |  | 1 | Renovations and Upgrading of Ophthalmic, orthopaedic, female surgical, male surgical , female and male medical - Final Account | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 25951 | 20193 | 2595 | 5469 | 8064 | 0 | 3497.7232 | 614.1789 | 0 | 0 | 1200.5642 | 2305.2782 | 0 | 792 | 0 | 0 | 0 | 8409.7444 | 0 | 0 | 8409.7444
9 | Themba Hospital |  | 1 | Renovations and upgrading of childrens wards, ICU/high care, trauma unit/casualty - Final Account | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 38195 | 35070 | 3820 | 357 | 4177 | 0 | 59.6064 | 1631.0882 | 1635.4196 | 0 | 0 | 850.5182 | 0 | 0 | 0 | 0 | 0 | 4176.6324 | 0 | 0 | 4176.6324
10 | Rob Ferreira Hospital Phase 4 Part 2 |  | 1 | New Learning Resource Centre building. | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 18989 | 39289 | 38862 | -15223 | 23639 | 0 | 0 | 8374.0649 | 4729.383 | 198.5329 | 2768.2652 | 667.8553 | 81.8229 | 0 | 2760 | 2677 | 1382 | 16819.9242 | 6819 | 0 | 23638.9242
11 | Themba Hospital |  | 1 | Bambanani ARV clinics | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 18989 | 39289 | 0 | 966 | 966 | 0 | 966.2176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966.2176 | 0 | 0 | 966.2176
12 | Themba Hospital |  | 1 | Construction of Doctors Accomodation 1 & 2 Bed Flats - Final Account | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 7189 | 6878 | 225 | -225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Rob Ferreira Hospital Phase 4 |  | 1 | Construction of new medical gas plant and renovation of medical gas plant | IDT |  | Mbombela | Ehlanzeni | [6 empty] | 5800 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 2000
14 | Rob Ferreira Hospital Phase 4B |  | 1 | Construction of a new trauma building with an admin block and helipad (Final Account) | IDT |  | Mbombela | Ehlanzeni | [6 empty] | 82028 | 77692 | 0 | 369 | 369 | 0 | 0 | 0 | 0 | 368.9998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.9998 | 0 | 0 | 368.9998
15 | Rob Ferreira Hospital Phase 4C |  | 1 | Upgrading of electrical rectification, internal roads, storm water,sewer, roof, gutters, mechanical works, landscaping and demolish of dilapidated double storey building | IDT |  | Mbombela | Ehlanzeni | [6 empty] | 96264 | 84519 | 0 | 5679 | 5679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5679 | 0 | 0 | 0 | 5679 | 0 | 5679
16 | Rob Ferreira Hospital Phase 3 |  | 1 |  | IDT |  | Mbombela | Ehlanzeni | [6 empty] | 6180 | 6140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Themba Hospital |  | 1 | Construction of a new medico legal laboratory | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 4782 | 3782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bohlabela District |  | 2 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 573 | 573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573 | 0 | 0 | 573 | 0 | 573
18 | Tintswalo Mortuary |  | 1 |  | DPWRT |  | Bushbuckridge | Bohlabela | [8 empty] | 0 | 573 | 573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573 | 0 | 0 | 573 | 0 | 573 | Project Closed
19 | Lydenburg mortuary |  | 1 |  | DPWRT |  | Thaba Chweu | Bohlabela | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Closed
| Gert Sibande District |  | 8 | [9 empty] | 0 | 0 | 108666 | 90849 | 7152 | -788 | 6364 | 0 | 569.4628 | 1367.8653 | 2491.9669 | 0 | 419.7368 | 0 | 0 | 0 | 0 | 1433 | 0 | 4849.0318 | 1433 | 81 | 6363.0318
20 | Ermelo Hospital |  | 1 | Repairs of Phamarcy defects, walkways and corridors (Final Account) | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 13405 | 6606 | 4805 | -2204 | 2601 | 0 | 386.8846 | 0 | 2213.8382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600.7227 | 0 | 0 | 2600.7227
21 | Ermelo Hospital |  | 1 | Repairs to admin building (Final account) | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 7374 | 3230 | 737 | 814 | 1551 | 0 | 182.5783 | 1367.8653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550.4436 | 0 | 0 | 1550.4436
22 | Ermelo Hospital |  | 1 | Upgrading of underground sewer pipes - Final Account | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 7100 | 5761 | 387 | 199 | 586 | 0 | 0 | 0 | 139.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 139.0644 | 447 | 0 | 586.0644
23 | Ermelo Hospital |  | 1 | Upgrading of water, fire and hot water reticulation- Final account | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 19098 | 17875 | 1223 | -98 | 1125 | 0 | 0 | 0 | 139.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 986 | 0 | 139.0644 | 986 | 0 | 1125.0644
24 | Ermelo medico-legal laboratory |  | 1 | Mortuary | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 23971 | 22115 | 0 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 81
25 | Ermelo Hospital |  | 1 | New health support block and balastrade fencing (Final Account) | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 18521 | 17763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Account Approved, Fees issue still to be resolved
26 | Ermelo Hospital |  | 1 | New paedriatric ward, walkway and staff parking paving | DPWRT |  | Msukaligwa | Gert Sibande | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Account Approved, Fees issue still to be resolved
27 | Ermelo Hospital |  | 1 | Upgrading of intensive care unit, maternity ward and gate house (Final Account) | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 19197 | 17499 | 0 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | 419.7368 | 0 | 0 | 0 | 0 | 0 | 0 | 419.7368 | 0 | 0 | 419.7368
| Nkangala District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
| EQUITABLE SHARE FUNDED PROGRAMME - Completed Projects |  | 28 | [9 empty] | 0 | 0 | 308885 | 271295 | 27330 | 28094 | 55424 | 0 | 11627.4496 | 12455.1172 | 4500 | 2224.505 | 7059.8926 | 2282.6592 | 2525.2701 | 3117 | 1568 | 3422 | 0 | 45791.8937 | 4990 | 1656 | 52437.8937
| Retention/Final Account |  | 28 | [9 empty] | 0 | 0 | 308885 | 271295 | 27330 | 28094 | 55424 | 0 | 11627.4496 | 12455.1172 | 4500 | 2224.505 | 7059.8926 | 2282.6592 | 2525.2701 | 3117 | 1568 | 3422 | 0 | 45791.8937 | 4990 | 1656 | 52437.8937
| Ehlanzeni District |  | 6 | [9 empty] | 0 | 0 | 55358 | 51397 | 3860 | 11296 | 15156 | 0 | 4328.8306 | 2085 | 4500 | 227.101 | 26.6603 | 0 | 33 | 261 | 644 | 0 | 0 | 11461.5919 | 644 | 0 | 12105.5919
28 | Masibekela Clinic |  | 1 | Construction of new CHC and accommodation units (Final account) | DPWRT |  | Nkomazi | Ehlanzeni | [6 empty] | 17273 | 17443 | 0 | 227 | 227 | 0 | 0 | 0 | 0 | 227.101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227.101 | 0 | 0 | 227.101
29 | Mthimba Clinic |  | 1 | Construction 2x2 accommodation units | DPWRT |  | Mbombela | Ehlanzeni | [6 empty] | 2211 | 1823 | 400 | -12 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 388 | 0 | 388
30 | M'afrika CHC |  | 1 | Construction of 2x2 accommodation units | DPWRT |  | Umjindi | Ehlanzeni | [6 empty] | 2249 | 1498 | 400 | -221 | 179 | 0 | 152.4402 | 0 | 0 | 0 | 26.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 179.1004 | 0 | 0 | 179.1004 | Final Account Approved, Fees issue still to be resolved
31 | Shongwe Hospital |  | 1 | Stabilisation of wards, General renovation and maintenance work | DPWRT |  | Nkomazi | Ehlanzeni | [6 empty] | 33625 | 30633 | 2000 | 662 | 2662 | 0 | 2406.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 2406.3904 | 256 | 0 | 2662.3904
32 | Tekwane CHC |  | 1 |  | DPWRT |  | Mbombela | Ehlanzeni | [8 empty] | 1060 | 10640 | 11700 | 0 | 1770 | 2085 | 4500 | 0 | 0 | 0 | 33 | 261 |  | 0 | 0 | 8649 | 0 | 0 | 8649
33 | Dwarsloop |  | 1 |  | DPWRT |  | Bushbuckridge | Ehlanzeni | [10 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
| Bohlabela District |  | 2 | [9 empty] | 0 | 0 | 46766 | 40611 | 2070 | 725 | 2795 | 0 | 738.0977 | 0 | 0 | 515.027 | 0 | 264.1544 | 0 | 0 | 0 | 1278 | 0 | 1517.2791 | 1278 | 0 | 2795.2791
34 | Hluvukani CHC |  | 1 | Construction of new CHC and accommodation units | DPWRT |  | Bushbuckridge | Bohlabela | [6 empty] | 26508 | 22944 | 1245 | -507 | 738 | 0 | 738.0977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738.0977 | 0 | 0 | 738.0977
35 | Mashishing CHC |  | 1 | Construction of new CHC and accommodation units | DPWRT |  | Thaba Chweu | Bohlabela | [6 empty] | 20258 | 17667 | 825 | 1232 | 2057 | 0 | 0 | 0 | 0 | 515.027 | 0 | 264.1544 | 0 | 0 | 0 | 1278 | 0 | 779.1814 | 1278 | 0 | 2057.1814
[32 empty] | 0 | 0 | 0 | 0
| Gert Sibande District |  | 12 | [9 empty] | 0 | 0 | 110321 | 88873 | 4817 | 11240 | 16057 | 0 | 2710.4495 | 6593.2047 | 0 | 107.4548 | 3559.6479 | 546.6963 | 0 | 2856 | 0 | 400 | 0 | 16373.4532 | 400 | 0 | 16773.4532
36 | Phola Park CHC |  | 1 | Construction of new CHC and 2x2 accommodation units | IDT |  | Mkhondo | Gert Sibande | [6 empty] | 22983 | 17471 | 1150 | 6499 | 7649 | 0 | 660 | 3186.1193 | 0 | 63.4548 | 2658.1409 | 7.3846 | 0 | 0 | 0 | 0 | 0 | 6575.0996 | 0 | 0 | 6575.0996
37 | Mbhejeka CHC |  | 1 | Construction of new CHC and 2x2 accommodation units | IDT |  | Albert Luthuli | Gert Sibande | [6 empty] | 23722 | 16246 | 1187 | 706 | 1893 | 0 | 97.5049 | 1260.188 | 0 | 0 | 534.9431 | 0 | 0 | 1259 | 0 | 0 | 0 | 3151.636 | 0 | 0 | 3151.636
38 | Warburton CHC |  | 1 | Construction of a new community health centre (Final account) | DPWRT |  | Msukaligwa | Gert Sibande | [6 empty] | 2764 | 2376 | 0 | 410 | 410 | 0 | 0 | 294.2595 | 0 | 0 | 116.0923 | 0 | 0 | 0 | 0 | 0 | 0 | 410.3517 | 0 | 0 | 410.3517 | Project Closed
39 | Evander Hospital |  | 1 | Renovations of roofing and kitchen | DPWRT |  | Govan Mbeki | Gert Sibande | [6 empty] | 15204 | 12087 | 1680 | 1420 | 3100 | 0 | 1861.12 | 700.218 | 0 | 0 | 0 | 539.3116 | 0 | 506 | 0 | 0 | 0 | 3606.6496 | 0 | 0 | 3606.6496
40 | Evander Hospital |  | 1 | Medico-Legal Laboratory | DPWRT |  | Govan Mbeki | Gert Sibande | [6 empty] | 15550 | 16005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Mayflower Clinic |  | 1 | Construction of 2x2 accommodation units | DPWRT |  | Albert Luthuli | Gert Sibande | [6 empty] | 2584 | 2282 | 400 | -289 | 111 | 0 | 91.8246 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.8246 | 0 | 0 | 135.8246 | Final Account Approved, Fees issue still to be resolved
42 | Swallowsnest Clinic |  | 1 | Construction of 2x2 accommodation units | DPWRT |  | Albert Luthuli | Gert Sibande | [6 empty] | 2406 | 2452 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 400
43 | Lebongang CHC |  | 1 | Major renovations (Final Account) | DPWRT |  | Govan Mbeki | Gert Sibande | [6 empty] | 12554 | 10222 | 0 | 1817 | 1817 | 0 | 0 | 475.7901 | 0 | 0 | 250.4716 | 0 | 0 | 1091 | 0 | 0 | 0 | 1817.2617 | 0 | 0 | 1817.2617
44 | Perdekop CHC |  | 1 | Major renovations (Final Account) | DPWRT |  | Pixley Ka Seme | Gert Sibande | [6 empty] | 12554 | 9732 | 0 | 164 | 164 | 0 | 0 | 163.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.6299 | 0 | 0 | 163.6299
45 | Embhuleni Hospital |  | 1 |  | DPWRT |  | Albert Luthuli | Gert Sibande | [6 empty] | 0 | 0 | 0 | 513 | 513 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 513
46 | Lochiel CHC |  | 1 |  | DPWRT |  | Albert Luthuli | Gert Sibande | [10 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
47 | Carolina Mortuary |  | 1 |  | DPWRT |  | Albert Luthuli | Gert Sibande | [10 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | Final Account Approved, Fees issue still to be resolved
| Nkangala District |  | 8 | [9 empty] | 0 | 0 | 96440 | 90414 | 16583 | 4833 | 21416 | 0 | 3850.0718 | 3776.9125 | 0 | 1374.9221 | 3473.5844 | 1471.8086 | 2492.2701 | 0 | 924 | 1744 | 0 | 16439.5695 | 2668 | 1656 | 20763.5695
48 | Delmas Hospital |  | 1 | Upgrading of existing theatre, Male and Female wards and Admin Block | DPWRT |  | Victor Khanye | Nkangala | [6 empty] | 0 | 0 | 0 | 2497 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 1376.948 | 1347 | 0 | 0 | 0 | 0 | 2723.948 | 0 | 1120 | 3843.948
49 | Moloto EMS |  | 1 | Construction of EMS station (Final account) | DPWRT |  | Thembisile Hani | Nkangala | [6 empty] | 24208 | 22208 | 0 | 2095 | 2095 | 0 | 0 | 0 | 0 | 0 | 0 | 94.8605 | 0 | 0 | 0 | 0 | 0 | 94.8605 | 0 | 0 | 94.8605
50 | Greenside CHC |  | 1 | Construction of new CHC and 2x2 accommodation units (Final account) | IDT |  | Dr J.S. Moroka | Nkangala | [6 empty] | 22889 | 21522 | 1145 | 373 | 1518 | 0 | 1018.2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 1018.2202 | 500 | 0 | 1518.2202
51 | Mammetlhake Hospital |  | 1 | Construction of Palisade Fencing | DPWRT |  | Dr J.S. Moroka | Nkangala | [6 empty] | 7202 | 3764 | 3438 | -568 | 2870 | 0 | 1477.8668 | 968.3594 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 0 | 0 | 2446.2262 | 424 | 0 | 2870.2262
52 | Belfast/HA Grove Hospital |  | 1 | Upgrade OPD, and Casualty, Construction of Pharmacy | DPWRT |  | Emakhazeni | Nkangala | [6 empty] | 42141 | 42920 | 12000 | 0 | 12000 | 0 | 917.9207 | 2808.5531 | 0 | 1374.9221 | 3473.5844 | 0 | 1145.2701 | 0 | 0 | 1744 | 0 | 9720.2504 | 1744 | 536 | 12000.2504
53 | Delmas Mortuary |  | 1 |  | DPWRT |  | Victor Khanye | Nkangala | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Closed
54 | Belfast Mortuary |  | 1 |  | DPWRT |  | Emakhazeni | Nkangala | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Account Approved, pending payment
55 | KwaMhlanga Hospital Phase 3A |  | 1 | Construction of bulk earthwork, roads and parking including new security gate house and construction of a new helipad | DPWRT |  | Thembisile Hani | Nkangala | [6 empty] | 0 | 0 | 0 | 436 | 436 | 0 | 436.0642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436.0642 | 0 | 0 | 436.0642
| EPWP - Completed Projects |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention/Final Account |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ehlanzeni District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Bohlabela District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Gert Sibande District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Nkangala District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
| COLLEGE INFRASTRUCTURE - Completed Projects |  | 1 | [9 empty] | 0 | 0 | 0 | 0 | 2195 | -1317 | 878 | 0 | 120.5617 | 695.6208 | 0 | 0 | 60.9603 | 0 | 0 | 0 | 0 | 0 | 0 | 877.1427 | 0 | 0 | 877.1427
| Retention/Final Account |  | 1 | [9 empty] | 0 | 0 | 0 | 0 | 2195 | -1317 | 878 | 0 | 120.5617 | 695.6208 | 0 | 0 | 60.9603 | 0 | 0 | 0 | 0 | 0 | 0 | 877.1427 | 0 | 0 | 877.1427
| Ehlanzeni District |  | 1 | [9 empty] | 0 | 0 | 0 | 0 | 2195 | -1317 | 878 | 0 | 120.5617 | 695.6208 | 0 | 0 | 60.9603 | 0 | 0 | 0 | 0 | 0 | 0 | 877.1427 | 0 | 0 | 877.1427
56 | Mpumalanga Nursing College |  | 1 |  | DPWRT |  | Mbombela | Ehlanzeni | [8 empty] | 2195 | -1317 | 878 | 0 | 120.5617 | 695.6208 | 0 | 0 | 60.9603 | 0 | 0 | 0 | 0 | 0 | 0 | 877.1427 | 0 |  | 877.1427
| Bohlabela District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 |  | 0
| Gert Sibande District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 |  | 0
| Nkangala District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 |  | 0
[15 empty] | 0 | [10 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0
| NHI GRANT - Completed Projects |  | 1 | [9 empty] | 0 | 0 | 3824 | 0 | 3823 | -1620 | 2203 | 0 | 1057.5564 | 345.587 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 1403.1434 | 800 | 0 | 2203.1434 | 0
| Retention/Final Account |  | 1 | [9 empty] | 0 | 0 | 3824 | 0 | 3823 | -1620 | 2203 | 0 | 1057.5564 | 345.587 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 1403.1434 | 800 | 0 | 2203.1434 | 0
| Ehlanzeni District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 |  | 0
| Bohlabela District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 |  | 0
| Gert Sibande District |  | 1 | [9 empty] | 0 | 0 | 3824 | 0 | 3823 | -1620 | 2203 | 0 | 1057.5564 | 345.587 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 1403.1434 | 800 | 0 | 2203.1434
57 | NHI Phase1 part 1-Final Account |  | 1 |  | DPWRT | [7 empty] | 0 |  | 3824 |  | 3823 | -1620 | 2203 | 0 | 1057.5564 | 345.587 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 1403.1434 | 800 | 0 | 2203.1434 | Project on final Accounts
[32 empty] | 0 | 0 |  | 0
| Nkangala District |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 0 | 0 | 0 | 0
[15 empty] | 0 | [10 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0
| TOTAL |  | 57 | [9 empty] | 141797 | 31195.34 | 1163680.34 | 1072075 | 115520 | 37107 | 152627 | 0 | 20735.6367 | 30681.2729 | 13356.7695 | 23423.6024 | 11509.4191 | 9602.8169 | 2607.093 | 4635 | 10807 | 16026 | 5590 | 116551.6106 | 32423 | 1737 | 150711.6106

## PROBLEMATIC PROJECTS (hidden)
Department of Health Problematic/Delayed Projects
No. | Project Name and description | Project Cost R0'000 | 2013-14 Allocated Budget R'000 | 2013-14 Revised Budget | 2013-14 Exp Dec 2013 R'000 | Project Exp to date | Project Current Stage | Project Targeted Stage by End FY | Challenges | Recommendation
Poor perfomance based on delayed Payment
1 | Rob Ferreira Hospital Phase 4E:Part 2 : New Learning Resource Centre building. | 88209.6977 | 38862 | NA | 15959.2062 | 82093.2062 | 97% | Final Account | Late payments to contractor is negatively affecting the project, due to extension of time caused by late payments. Construction activities are: Internal finishes, installation of auditorium chairs, mechanical and electrical works, external parking and cladding of retaining wall. | DoH to ensure that funds are available on time to avoid any additional cost and time to the project
Poor performance based on Service Provider Capacity
2 | ERMELO HOSPITAL: Construction of a Orthopaedic workshop | 0 | 8446 | NA | 0 | 0 | 2% |  | Project is behind schedule, the site is under rehabilitation contractor is required to submit revised program of work and cashflow. | Principal Agent has issued a second warning letter and consider termination.
3 | KwaMhlanga Hospital: Phase 3C Construction of new intensive care unit (ICU), and casuality. Renovations and additions to existing theatre block | 42405 | 19303 | NA | 8776.9409 | 35608.9408 | 88% |  | project is behind schedule, Poor work coordination. Contractor to complete new permanent theatre prior handover of existing theater by hospital management for upgrade. | revised completion date is set for the 8-dec-2013,contractor to submit an acceleration plan to complete the work earlier as per MDoH request.
4 | Mapulaneng Hospital: Renovations and additions to existing TB Ward. Construction of Storage and Helipad | 20448.22 | 1000 | NA | 0 | 17203 | 99% |  | The contractor is awaiting, delivery of helipad lights | Contractor given 3 weeks to receive and install the lights.
5 | Piet Retief Mortuary | 24308 | 7000 | NA | 117 | 15179 | 92% | Intervention meeting was held and resulution was taken for contractor claim to be processed to improve contractor cashflow and performance. | Project behind schedule, General building work schedule to complete by end of October 2013, Mechanical work is scheduled for completion by the end of November 2013. | Close monitoring of the project. DPWRT and all the stake holder in the project held a meeting to agree on how best to complete the project.
6 | Themba Hospital renovations and Upgrading of Ophthalmic, orthopaedic, female surgical, male surgical , female and male medical | 27670 | 2595 | NA | 1339.5642 | 55271.5642 | 94% |  | All ward have been completed and handed over. Outstanding Electricity connection to the pump. Delayed due awaiting revised cession to be submitted by QS. | follow up with the QS on the submission.
7 | Wakkerstroom CHC: Construction of new community Health Centre | 13231.34 | 1100 | NA | 671.7318 | 5982 | 92% |  | Project behind schedule. Contractor is busy with finishes. | Close monitoring of the project.
Delayed based on delayed Approval of VO
8 | Rob Ferreira Hospital Phase 4A: Major Renovations of existing units, creche,laboratory,theatre,x-ray,ICU,Specialist OPD,wards 2,3,4 & 8, cafeteria ,construction of medical waste and external parking | 154158 | 16518 | NA | 19941.8575 | 180849.8575 | FA |  | Project has been completed and reached practical completion. Final account has been approved in August 2013. Consultants outstanding fees are still to be paid by DoH and final delivery list to be finalised to close the project. | DoH to transfer funds for the fees to consultants so as to close the project.
9 | Rob Ferreira Hospital Phase 4D: Upgrading of Wards 9,10,11 and peadiatric ward, Rehabilitation centre | 45000 | 4613 | NA | 17051.1835 | 45075.1835 | 83% |  | Variation Orders 1-3 have been approved. Contractor started with site re-establishment on the 02 September 2013. Activities on site are re-establishment of the site, internal finishes in ward(s) 8,7 & 6, removal of floor tiles and other infected areas in rehabilitation centre | Contractor to prioratise to complete the three wards for the patients to start using them.
Delayed due to design dispute Client vs Implementing Agent
10 | Rob Ferreira Hospital Phase 4: Construction of a new medical gas plant and renovations to the existing medical gas plant | 5800 | Not in the IPMP | NA | 0 | 5800 | RT |  | Project not handed over due to design compliance issue. | DoH to advise on budget re adjustement
11 | Greenside CHC: construction of community health centre | 22889 | 1145 | NA | 1018 | 21841 | RT |  | Project on retention. | Refer IDT report
12 | Sinqobile CHC: construction of community health centre | 25465 | 1274 | NA | 93 | 14920 | 0.44 |  | Progress is very slow, contractor was issued with two warning letter with intention to terminate for none performance. Currently contractor abonded site | final warning was issued with intention to terminate and if contractor doesn’t returned to site by the expiry date therefore the termination will be effected
Projects with No Budget Allocation
13 | CAROLINA HOSPITAL : Construction of Admin Block, OPD, Paediatric ward and extension of theatre | 0 | 0 | 0 | 0 | 0 | PD |  | Master plan presented to MDoH and Site visit on various facilities have been conducted, to review and inform phasing of the project due to budgetary constrained,awaiting finding report from MDoH to inform the way forward. | MDoH to provide recommendation on way forward based on master plan and site visit to inform next financial year budget.
14 | Delmas Hospital: Upgrading of existing theatre, male/female wards and administration block | 27911.72 | 0 | 0 | 0 | 23112 | FA |  | Final account have been approved, Outstanding Prof Fees. | DoH to advise on budget readjustement.
15 | Dwarsloop CHC: Construction of Community Health Centre and 2 X 2 accomodation units | 16045.64 | 0 | 0 | 0 | 15960 | FA |  | Approval for the purchasing of the missing dental chair equipment. | DoH to advise on budget readjustement.
16 | Evander Hospital: Construction of new Medico -Legal Laboratory | 15550.04 | 0 | 0 | 0 | 16005 | FA |  | Project on Final Account.Awaiting submission from PA. | Follow up on FA submission from the QS DoH to advise on budget readjustement.
17 | Lebogang CHC: Major Renovation of Community Health Centre | 12554.02 | 0 | 726.4716 | 726.4716 | 10222 | FA |  | Final Account returned to the PA for correction around mid july 2013. Project wirh with no budget on the current Financial Year IPMP. | follow with the PA for anticipated resubmission date. DoH to advise on budget readjustement.
18 | Lochiel CHC: Construction of Community Health Centre and 2 X 2 bedroom accomodation units | 16512.92 | 0 | 0 | 0 | 16735 | FA |  | project on final account. | DoH to advise on budget readjustement.
19 | Masibekela CHC: Construction of Community Health Centre and 2 X 2 bedroom accomodation units | 17272.84 | 0 | 227.101 | 227.101 | 17443 | FA |  | Final account have been approved.awaiting final Amount certificate from the PA. | DoH to advise on budget readjustement.
20 | MATIBIDI HOSPITAL : Construction of admin block and 10x3 accommodation units.(Phase 1) | 0 | 0 | 0 | 0 | 0 | PD |  | Master plan presented to MDoH and Site visit on various facilities have been conducted, to review and inform phasing of the project due to budgetary constrained,awaiting finding report from MDoH to inform the way forward. | MDoH to provide recommendation on way forward based on master plan and site visit to inform next financial year budget.
21 | Moloto (Tweefontein) EMS : Construction of Emergency Medical Service Station | 24208.121 | 0 | 0 | 0 | 14811 | RT |  | Project on retention. | DoH to advise on budget readjustement.
22 | PANKOP CHC: Construction of new CHC and 2x2 accommodation units | 0 | 0 | 987 | 987 | 0 | PD |  | Planning delayed due to relocation of site.Planning has been reprioritized to commence in the 2014-15 financial year. | None.
23 | Perdekop CHC: Major Renovation of Community Health Centre | 12554.02 | 0 | 164 | 164 | 9732 | CL |  | Project Closed. Final account approved and Paid both contractor and QS. | None.
24 | SIYATHEMBA CHC: Construction of new CHC and 2x2 accommodation units | 0 | 0 | 0 | 0 | 0 | PD |  | Project to be implemented through National Department of Health. And Professionnal service provider have been appointed. | None
25 | Warburton CHC: Construction of Community Health Centre | 2764 | 0 | 410.0923 | 410.0923 | 2376 | CL |  | Project Closed. | None.
Projects Ommitted in the IPMP
26 | Belfast Mortuary | 2155.74 | Not in the IPMP | 0 | 0 | 2105 | FA |  | Project is on Final account. | DoH to advise on budget re adjustement
27 | Caroline Mortuary | 2542.9 | Not in the IPMP | 0 | 0 | 2101 | FA |  | Fee Claim have been submitted for approval. | DoH to advise on budget re adjustement
28 | Delmas Mortuary | 1949.4 | not in the IPMP | 0 | 0 | 1570 | FA |  | Project is on Final account. | DoH to advise on budget re adjustement
29 | Embhuleni Hospital: Construction of new palisade fencing | 5954.28 | not in the IPMP | 513 | 513 | 2289 | FA |  | Project is on Final account. Ommitted in the current IPMP and yet has incured expenditure. | DoH to advise on budget re adjustement.
30 | Ermelo Hospital : Medico legal laboratory | 23971 | Not in the IPMP | 0 | 0 | 22115 | FA |  | Final Account approved.and Fees Claim submitted for approval. | DoH to advise on budget re adjustement
31 | Ermelo Hospital : New Health support block and concrete palisade fencing | 25174 | Not in the IPMP | 960 | 0 | 24649 | FA |  | Final account Approved. | DoH to advise on budget re adjustement
32 | Ermelo Hospital : New paediatric ward, Walkways and Staff Parking paving | 26338 | Not in the IPMP | 0 | 0 | 27302 | FA |  | Final Account Approved and Contractor Paid, fee Claim outstanding. | DoH to advise on budget re adjustement
33 | Ermelo Hospital : Renovation and Upgrading of OPD, Casualy and Theatres | 38716 | Not in the IPMP | 2773.4603 | 1143.4603 | 36634.4603 | RT |  | Electrical Mechanical fees claim scale have been approved work completionschedule for mid October 2013. Project Omitted in the current IPMP. | Close monitoring of project. DoH to advise on budget re adjustement
34 | Ermelo Hospital : Renovations and Upgrading of Intensive care unit, maternity ward and gate house | 29026 | Not in the IPMP | 1367.8653 | 1367.8653 | 28415.8653 | FA |  | Final Account returned to the consultant for correction | Follow up on FA submission from the QS. DoH to advise on budget re adjustement
35 | Evander Hospital: Upgrading and construction of OPD, Casualty, Dispensary, Administration block & Theatres | 39971 | not in the IPMP | 0 | 0 | 41132 | CL |  | Project Closed. | DoH to advise on budget re adjustement
36 | Kwa Mhlanga Hospital: Construction of Bulk Earthworks, roads and parking including new security gatehouse and construction of new helipad | 13448.46 | not in the IPMP | 436 | 436 | 11412 | FA |  | The project is on final account. | DoH to advise on budget re adjustement
37 | Lydenburg Mortuary | 2299.82 | Not in the IPMP | 0 | 0 | 2623 | CL |  | Project closed. | DoH to advise on budget re adjustement
38 | Middelburg Pharmaceutical Depot | 86345.32 | not in the IPMP | 0 | 0 | 74511 | CL |  | Project closed. | DoH to advise on budget re adjustement
39 | Rob Ferreira Hospital Phase 4: Construction of a new medical gas plant and renovations to the existing medical gas plant | 5800 | Not in the IPMP | 0 | 0 | 5800 | RT |  | Project not handed over due to design compliance issue. | DoH to advise on budget re adjustement
40 | Rob Ferreira Hospital Phase 4B: Construction of a new Trauma Building with an admnistration block and a helipad on top. | 82028 | Not in the IPMP | 368.9998 | 368.9998 | 78060.9998 | RT |  | On retention | Final account to be finalised, still awaiting information from the QS
41 | Rob Ferreira Hospital Phase 4C: Upgrading of Electrical reticulation, Internal Roads, stormwater, sewer, roofs, gutters, mechanical works, landscaping and demolishing of a dilapidated double storey building | 96264 | not in the IPMP | 0 | 0 | 84519 | RT |  | Project is on retention | DoH to advise on budget re adjustement
42 | Rob ferreira Phase 3 | TBA | Not in the IPMP | 300 | 0 | 6180 | FA |  | Project on final account and contractor paid, Fees outstanding. | follow on fees claim with PA.
43 | Themba Hospital : Construction of new medico-legal laboratory | 2437 | not in the IPMP | 240 | 0 | 4782 | FA |  | Final account sent back to the QS for correction. | DoH to advise on budget re adjustement
44 | Tintswalo Mortuary | 2076.8 | Not in the IPMP | 194.7 | 0 | 1753 | FA |  | Final Account Apporoved and paid. | DoH to advise on budget re adjustement